INFLUENCE OF COST CONTROL STRATEGIES ON EFFECTIVENESS OF CONSTRUCTION PROJECT DELIVERY INNIGERIA
(A CASE STUDY OF LAGOS STATE)
BY

IBIKUNLE DEBORAH OMOTARA
HND/22/BLD/FT/0075
BEING A RESEARCH PROJECT SUBMITTED TO THE DEPARTMENT OF BUILDING TECHNOLOGY, INSTITUTE OF EVIRONMENTAL STUDIES, KWARA STATE POLYTECHNIC, ILORIN

IN PARTIAL FULFILLMENT OF THE REQUIREMENT FOR THE AWARD OF HIGHER NATIONAL DIPLOMA (HND) IN BUILDING TECHNOLOGY, KWARA STATE POLYTECHNIC, ILORIN

JULY, 2025

CERTIFICATION


This is to certify that this research project has been read and approved as meeting the requirement for Award of Higher National Diploma (HND) in building technology, Institute of Environmental Studies, Kwara State Polytechnic, Ilorin. 

________________________




_________________

BLDR. IYIOLA AKEEM SEYI (MNIOB)




DATE
 (Project Supervisor)

________________________



    
_________________

BUILDER A. ALEGE (MNIOB)





DATE
(Project Coordinator) 

________________________




_________________

BUILDER A. ALEGE (MNIOB)





DATE
(Head of Department)

________________________




_________________

BLDR ALIU SULAIMAN FUNSHO (MNIOB)



DATE

(External supervisor)

DEDICATION

This project is dedicate to Almighty God for seeing us throughout the stay in kwara state polytechnic. It is also dedicate to my parent who has been support me. The blessing and mercies of God we be with you always Ameen.
ACKNOWLEDGEMENTS

First and foremost, I express my profound gratitude to Almighty God for His guidance, protection, and strength throughout the duration of this project.

I sincerely appreciate my project supervisor, BLDR. IYIOLA AKEEM SEYI (MNIOB)
for their invaluable support, guidance, and constructive criticism which greatly contributed to the success of this research work. Your patience and encouragement have been a major driving force behind this accomplishment.

My heartfelt thanks also go to all the academic and non-academic staff of the Department for providing a conducive learning environment and for their collective efforts in shaping my academic journey.

I am immensely grateful to my beloved parents for their unwavering love, prayers, and moral and financial support. Your belief in me has been my greatest motivation.

To my family members and friends, thank you for your encouragement, understanding, and support throughout this project. Your words of motivation and constant check-ins did not go unnoticed.

This project would not have been possible without the collective support of all these wonderful individuals. I remain truly grateful

TABLE OF CONTENTS

Front page








i

Certification








ii

Dedication








iii

Acknowledgement







iv-v

Table of contents







vi-ix

Abstract








x

CHAPTER ONE

Introduction 

1.1
Background of the study





1-2

1.2
Statement of the problem





2-3

1.3
Aim and objectives of the study




3

1.3.1
Aim of the study






3

1.3.2
Objectives of the study





3-4

1.4
Research questions






4

1.5
Significance of the study





4

1.6
Scope of the study






5

1.7
Limitation of the study





5

1.8
Definition of terms






5-6

CHAPTER TWO

2.0 
Literature Review

CHAPTER THREE

Methodology

3.1    
Introduction







16

3.2
Research design






16

3.3
Population of the study





16

3.4
Method of data collection





17

3.5
Data Analysis Method






18

CHAPTER FOUR

4.0 
Data Presentation, Analysis and discussion of Result

4.1 
Introduction 







19

4.2
Analysis and Presentation of Results




19-32

CHAPTER FIVE

5.0
Summary, Conclusion and Recommendation

5.1
Summary of the findings





33

5.2
Conclusion







34

5.3
Recommendation






34

REFERENCES







35-40

APPENDIX








41

ABSTRACT
The contribution of the construction industry to national economic growth necessitates improved efficiency in the industry by means of cost effectiveness and timeliness, and would certainly contribute to cost savings for the country as a whole.  This study examined various cost control techniques used in construction projects and the impact they have on project delivery, identified cost control technique frequently used by contractors in construction projects, examined problems encountered by contractors in managing construction project cost and determined the impact of costcontrol techniques on the duration of construction projects. Simple random sampling was used to determine sample size (50 contractors) from the population. Structured questionnaire was used for data collection and this was supplemented with interview of key informants. Data were analyzed using Chi-square. Results showed that Cost Control techniques affect cost and time of a construction project. Cost Control problems lead to construction project delivery failures. In conclusion, the construction industry is a key industry to economic growth of any nation providing shelter for economic and social activities including on-site and off-site infrastructure to facilitate the smooth functioning of these activities. It was recommended that the industry should take advantage of advancement in ICTS to automate their cost information management systems.

CHAPTER ONE

INTRODUCTION

1.1 BACKGROUND OF THE STUDY

It is a known fact that the Nigerian construction industry continues to occupy an important position in the nation’s economy even though it contributes less than the manufacturing or other service industries, (Aibinu and Jagboro, 2002). The contribution of the construction industry to national economic growth necessitates improved efficiency in the industry by means of cost effectiveness and timeliness, and would certainly contribute to cost savings for the country as a whole. It is also common knowledge that the implementation of the construction project in the industry is usually accompanied with time delay and cost increase as well as owner dissatisfaction (Hafez, 2001).

In general most (if not all), construction projects experience time delays and cost overruns during their implementation phase (Koushki and Kartam,2004). Numerous researchers, both in the developed and developing nations have also examined and identified the causes of time and cost overrun in the construction industry. Mansfield, Ugwu and Doran (1994), for example performed a comprehensive analysis of most important factors responsible for project delays and cost overrun in Nigerian construction projects. This analysis indicated poor contract management, financing and payment of completed works, change in site conditions, shortages of materials, design changes, subcontractors and nominated suppliers, other factors were price fluctuation inaccurate estimates, delays and additional works as factors responsible for project delays and cost overrun.

A comprehensive classification of causes of construction delays has also been determined by Henesy (1993). The classification system included materials, labour, equipment and financial constraints, as the main contributory variable to causes of construction time overrun. The list of major factors causing construction delay in Thailand by Ogunlana and Proumkunting (1996) included the inadequacy of resources supplies, client and consultant shortcomings and incompetence. Koushki and Kartan (2004) studied the impact of construction materials on project time and cost in Kuwait and identified the project related variable affecting the on time delivery of materials as material selection, time, type of materials and their availability in the local market.

Time impacts are inevitable on construction projects, primarily because of the uniqueness of each project and the limited resources of time and money that can be spent on planning, executing and delivering the project. 

Time factors are inherent in all of project construction’s undertakings. Construction projects have long been recognized as particularly cost, time and risk-laden. Some of the time and cost factors associated with the construction process are fairly predictable or identifiable; others may be totally unforeseen. The constructed project may not perform as anticipated because the owner may have unrealistic expectations regarding the delivery time of construction forcing contractors into unrealistic gambles, corner-cutting or commitments that may not be realistic (Frimpong 2003). 

Project success can be defined as meeting goals and objectives as prescribed in the project plan. A successful project means that the project has accomplished its technical performance, maintained its schedule, and remained within budgetary costs. Project management tools and techniques play an important role in the effective management of a project. Therefore, a good project management lies in the management tools and techniques used to manage the project. Project management involves managing the resources—workers, machines, money, materials and methods used. Some projects are effectively and efficiently managed while others are mismanaged, incurring much delay and cost overruns and negatively affecting the economy (Frimpong 2003). 

Assessing construction projects’ delivery time is critical in today’s market-driven economy. 

1.2 STATEMENT OF RESEARCH PROBLEMS
Construction can be considered as a dynamic industry which is constantly facinguncertainties. These uncertainties and the many stakeholders in these kinds of projects, makethe management of costs difficult which consequently causes cost overruns. Therefore, costoverruns are considered one of the most critical issues during the execution of constructionprojects (Chan, et al., 2004; Doloi, 2011). 
As mentioned by Van Der Westhuizen andFitzgerald (2005), the presence of cost overruns can be a reason for project delays or possible project failures. Howeverthis idea has been refuted by many authors who considered that project success depends onmany other factors that should be assessed to conclude the success or failure of a project(Chan, et al., 2004). Moreover, there have been many studies that suggest that the success of aproject depends on the presence of certain critical factors which can also change depending onthe objective to be met (Iyer and Jha, 2005). In other words, some authors ascertained thatthere are some critical success factors that help to improve cost performance and prevent costoverruns.
1.3 OBJECTIVES OF THE STUDY
The main aim of the study is to examine various cost control techniques used in construction projects and the impact they have on project delivery. Specific objectives of the study are:

· To identify cost control technique frequently used by contractors in construction projects.
· To examine problems encountered by contractors in managing construction project cost.
· To determine the impact of costcontrol techniques on the duration of construction projects.
1.4 RESEARCH QUESTIONS

In-order to guide the study and achieve the above stated research objectives; the following research questions were formulated:

· What cost control techniques are frequently used by contractors in construction projects?

· What are the problems faced by contractors in controlling cost in the construction project process?

· What impact does cost controlling techniques have on the duration of construction projects?
1.5 RESEARCH HYPOTHESES

1. Ho:Cost control problems do not lead to project delivery failures.

Hi:Cost control problems lead to project delivery failures.

2. Ho:Cost Control techniques affect to construction delivery timing and cost
Hi: Cost Control techniques do not affect to construction 

delivery timing and cost
1.6 SIGNIFICANCE OF THE STUDY
This study will be of importance to building professionals and the general public because it would not only clarify but also create awareness of the extent to which inadequacies in cost control techniques can adversely affect project performance. The study will also help contractors, clients, consultants and all parties involved in construction projects about ways of improving their current method of cost management and control.
The study will also be of great benefit for other student researchers’ who may want to venture into the same subject matter. Having gotten results-both empirically and theoretically, the study will serve as a foundation for future research studies.

1.7 SCOPE OF THE STUDY
The study will cover some selected quantity surveyors from Lagos. All findings and recommendations from the study may not reflect the true view of the traditional roles and changing roles of quantity surveyors as the researcher could not cover a wider area due to financial and time constraints.

1.8 DEFINITION OF TERMS

1. Construction: In the fields of architecture and civil engineering, construction is a process that consists of the building or assembling of infrastructure. Far from being a single activity, large scale construction is a feat of human multitasking. Normally, the job is managed by a project manager, and supervised by a construction manager, design engineer, construction engineer or project architect.

2. Deliverable: Deliverable is a term used in project management to describe a tangible or intangible object produced as a result of the project that is intended to be delivered to a customer (either internal or external). A deliverable could be a report, a document, a server upgrade or any other building block of an overall project.

3. Project management: this is the discipline of planning, organizing, motivating, and controlling resources to achieve specific goals. A project is a temporary endeavour with a defined beginning and end (usually time-constrained, and often constrained by funding or deliverables),undertaken to meet unique goals and objectives, typically to bring about beneficial change or added value. 

4. Time: This is a dimension in which events can be ordered from the past through the present into the future, and also the measure of durations of events and the intervals between them.

5. Cost: A cost is the value of money that has been used up to produce something, and hence is not available for use anymore. In business, the cost may be one of acquisition, in which case the amount of money expended to acquire it is counted as cost.

6. Cost overrun: occurs when the final cost of the project exceeds the original contract value at the time of completion.

7. Good cost performance project: Project in which the cost overrun of the project does not exceed 10 percent of the initial budget.

8. Poor cost performance project: Project in which the cost overrun of the project exceeds 10 percent of the initial budget.

CHAPTER TWO
LITERATURE REVIEW

2.1 INTRODUCTION

This chapter gives an insight into various studies conducted by outstanding researchers, as well as explained terminologies with regards to the impact of cost control techniques on construction project delivery.
The chapter also gives a resume of the history and present status of the problem delineated by a concise review of previous studies into closely related problems.

2.2 COST MANAGEMENT AND COST CONTROL TECHNIQUES USED IN THE CONSTRUCTION INDUSTRY
Cost management is an approach used to realize decisions made for planning, controllingand developing competitive strategies, and it is noteworthy to say that making a balance betweenthis factor and other dimensions of competition such as quality and time is required. It is thecontrol of costs through the formal process of budget development, monitoring, and adjustment toachieve the maximum amount of work at a specified level of quality where unknowns anduncertainty may cause costs to increase beyond acceptable levels (Frimpong, 2006). The Project Management Institute considers cost management as primarily concerned with the cost of resources neededto complete project activities and would be achieved through a process involving estimating, budgeting, and cost control. However, cost management is much more than simply maintainingrecords of expenditure and issuing cost reports - it means understanding how and why costs occurand promptly taking the necessary response in light of all the relevant information. Thus thekey question to stay competitive in construction enterprise is cost management and control. 

Over the years, contractors developed several cost management strategies to assist them torecord all financial transactions that occur as well as giving managers an indication of theprogress and problems associated with a project (Davies, 2013). Some of the strategies, tools and techniquesused by contractors to manage cost are discussed below.
2.2.1 Cost Value Reconciliation

Cost Value Reconciliation (CVR) is the practice of determining and reporting profitability of a construction project on a regular basis. By comparing the costs with revenue at a certain date, it is possible to see the difference between the cumulative profit or the loss on the project. The application of cost value reconciliation (CVR) in the subcontracting construction industry is considered an important part of cost management for the financial control of construction projects. However despite its’ uses it is often not widely used by subcontracting organisations. This is generally due to the perceived resource requirements, the cost and technical skills necessary to incorporate the technique into small and medium size subcontractors.

2.2.2 The Project Budget

For cost control on a project, the construction plan and the associated cash flow estimates can provide thebaseline reference for subsequent project monitoring and control. For schedules, progress on individual activitiesand the achievement of milestone completions can be compared with the project schedule to monitor the progressof activities. Contract and job specifications provide the criteria by which to assess and assure the requiredquality of construction. The final or detailed cost estimate provides a baseline for the assessment of financialperformance during the project. To the extent that costs are within the detailed cost estimate, then the project isthought to be under financial control. Overruns in particular cost categories signal the possibility of problems andgive an indication of exactly what problems are being encountered. Expense oriented construction planning andcontrol focuses upon the categories included in the final cost estimation. This focus is particular relevant forprojects with few activities and considerable repetition such as grading and paving roadways.

For control and monitoring purposes, the original detailed cost estimate is typically converted to a project budget,and the project budget is used subsequently as a guide for management. Specific items in the detailed costestimate become job cost elements. Expenses incurred during the course of a project are recorded in specific jobcost accounts to be compared with the original cost estimates in each category. Thus, individual job cost accountsgenerally represent the basic unit for cost control. Alternatively, job cost accounts may be disaggregated ordivided into work elements which are related both to particular scheduled activities and to particular costaccounts. 

2.2.3 Cost Forecasting 
For the purpose of project management and control, it is not sufficient to consider only the past record of costsand revenues incurred in a project. Good managers should focus upon future revenues, future costs and technicalproblems. For this purpose, traditional financial accounting schemes are not adequate to reflect the dynamicnature of a project. Accounts typically focus on recording routine costs and past expenditures associated withactivities (Davies, 2013).Generally, past expenditures represent sunk costs that cannot be altered in the future and may ormay not be relevant in the future. For example, after the completion of some activity, it may be discovered thatsome quality flaw renders the work useless. Unfortunately, the resources expended on the flawed constructionwill generally be sunk and cannot be recovered for re-construction (although it may be possible to change theburden of who pays for these resources by financial withholding or charges; owners will typically attempt to haveconstructors or designers pay for changes due to quality flaws). Since financial accounts are historical in nature,some means of forecasting or projecting the future course of a project is essential for management control. In thissection, some methods for cost control and simple forecasts are described.

2.2.4 Schedule Control

In addition to cost control, project managers must also give considerable attention to monitoring schedules.

Construction typically involves a deadline for work completion, so contractual agreements will force attention toschedules. More generally, delays in construction represent additional costs due to late facility occupancy orother factors. Just as costs incurred are compared to budgeted costs, actual activity durations may be compared toexpected durations. In this process, forecasting the time to complete particular activities may be required.
2.2.5 Earned Value Analysis
Earned Value analysis is a method of performance measurement. Earned Value is a program management technique that uses “work in progress” to indicate what will happen to work in the future. Earned Value is an enhancement over traditional accounting progress measures. Traditional methods focus on planned accomplishment (expenditure) and actual costs. Earned Value goes one step further and examines actual accomplishment. This gives managers greater insight into potential risk areas. With clearer picture, managers can create risk mitigation plans based on actual cost, schedule and technical progress of the work. It is an “early warning” program/project management tool that enables managers to identify and control problems before they become insurmountable. It allows projects to be managed better – on time, on budget. Earned Value Management System is not a specific system or tool set, but rather, a set of guidelines that guide a company’s management control system.

2.2.6 Variance Analysis
Variance analysisis a tool of budgetary control by evaluation of performance by means of variances between budgeted amount, planned amount or standard amount and the actual amount incurred/sold. Variance analysis can be carried out for both costs and revenues.

Variance analysis is usually associated with explaining the difference (or variance) between actual costs and the standard costs allowed for the good output. For example, the difference in materials costs can be divided into a materials price variance and a materials usage variance. The difference between the actual direct labor costs and the standard direct labor costs can be divided into a rate variance and an efficiency variance. The difference in manufacturing overhead can be divided into spending, efficiency, and volume variances. Mix and yield variances can also be calculated.

Variance analysis helps management to understand the present costs and then to control future costs.

These tools may be used singularlyor in combination. However, apart from earned value, the other cost control techniques sufferfrom lack of real time reporting. Earned value management has gained more acceptance and usein developed countries. For example, in the USA, it is a requirement that contractors and subcontractorsworking on defence projects employ earned value analysis. On the other hand,traditional cost control processes, common with most developing countries, are criticized becausethey simply identify variances by monitoring actual performance against cost estimates. Forexample, cost projection is not usually taken into consideration. 

2.3 RELATIONSHIP BETWEEN CONSTRUCTION PROJECT DELIVERY AND COST
Chitkara (2005) said the relationship between time and cost is a very important aspect in thecontrol of costs on site as any variation in time has automatic implication on cost. It is importantto report and record all the works involving materials, plant and labour on sites. This enables thecontractor be able to know the costs and expenses of the resources used on site and compare withthe initial cost budget. Various report techniques used include; daily or weekly and monthlyrecording, schedule control, site daily diary report and the project budget.

2.4 FACTORS AFFECTING CONSTRUCTION COST AND TIME PERFORMANCE

Chan and Kumaraswamy (2002) remarked that studies in various countries appear tohave contributed significantly to the body of knowledge relating to time performancein construction projects over the past three decades, while Iyer and Jha (2005)remarked that project performance in term of cost is studied since 1960s. Thesestudies range from theoretical work based on experience of researcher on one end tostructured research work on the other end. Moreover, Pheng and Chuan (2006) statedthat there have been many past studies on project performance according to cost andtime factors.

Chan and Kumaraswamy (1996) stated that a number of unexpected problems andchanges from original design arise during the construction phase, leading to problemsin cost and time performance. It is found that poor site management, unforeseenground conditions and low speed of decision making involving all project teams arethe three most significant factors causing delays and problems of time performance inlocal building works. Okuwoga (1998) stated that cost and time performance has beenidentified as general problems in the construction industry worldwide. Dissanayakaand Kumaraswamy (1999) remarked that project complexity, client type, experienceof team and communication are highly correlated with the time performance; whilstproject complexity, client characteristics and contractor characteristics are highlycorrelated with the cost performance. Reichelt and Lyneis (1999) obtained that projectschedule and budget performance are controlled by the dynamic feedback process.

Those processes include the rework cycle, feedback loops creating changes inproductivity and quality, and effects between work phases.

Chan (2001) identified that the best predictor of average construction timeperformance of public sector projects in Malaysia is T = 269 C 0.32 . This relationshipcan serve as a convenient tool for both project managers and clients to predict theaverage time required for delivery of a construction project. Kuprenas (2003) statedthat process of a design team meeting frequency and the process of written reportingof design phase progress were found to be statistically significant in reducing designphase costs. Otherwise, the use of project manager training and a project managementbased organizational structure were found to be processes that do not create astatistically significant in reducing design phase costs.

Iyer and Jha (2005) remarked that the factors affecting cost performance are: projectmanager's competence; top management support; project manager's coordinating andleadership skill; monitoring and feedback by the participants; decision making;coordination among project participants; owners' competence; social condition,economical condition and climatic condition. Coordination among project participantswas as the most significant of all the factors having maximum influence on costperformance of projects. Love et al (2005) examined project time-cost performancerelationships by using project scope factors for 161 construction projects that werecompleted in various Australian States. It is noticed that gross floor area and thenumber of floors in a building are key determinants of time performance in projects.

Furthermore, the results indicate that cost is a poor predictor of time performance.Chan and Kumaraswamy (2002) proposed specific technological and managerialstrategies to increase speed of construction and so to upgrade the construction timeperformance. It is remarked that effective communication, fast information transferbetween project participants, the better selection and training of managers, anddetailed construction programs with advanced available software can help toaccelerate the performance. Jouini et al (2004) stated that managing speed inengineering, procurement and construction projects is a key factor in the competitionbetween innovative firms. It is found that customers can consider time as a resourceand, in that case, they will encourage the contractor to improve the time performance.
2.5 FACTORS CAUSING PROJECT COST OVERRUNS
Since the 1980s various studies have investigated the causes forproject cost overruns on construction projects.

Kaming, Olomolaiye, Holt & Harris (1997), who studied 31construction projects in Indonesia, found that from a contractor’spoint of view, cost overruns were mainly caused by “inaccuracy ofmaterial take-off”, “increase in material costs” and “cost increasedue to environmental restrictions”. Studying the cost overruns anddelays on groundwater projects in Ghana, Frimpong, Oluwoye& Crawford (2003) contractors found that “late monthlypayments from clients” were the most important cost and timedelay factors, with clients ranking “poor contractor performance”as the most important cost and time delay factor. Reviewing publicsector construction projects in Nigeria, Dlakwa&Culpin (1990)found that the three main reasons for cost overruns are “fluctuationsin material, labour and plant costs”, “construction delays” and“inadequate pre-planning”.

In another study on construction projects in Nigeria, conducted by

Okpala&Aniekwu (1988: 238), it was found that architects, consultantsand clients agreed that ‘shortage of materials’, ‘finance and paymentof completed works’ and ‘poor contract management’ werethe most important causes of cost overruns. Mansfield, Ugwu& Doran(1994: 258) studied the performance of transportation infrastructureprojects in Nigeria and concluded that ‘material price fluctuations’,‘inaccurate estimates’, ‘project delays’ and ‘additional work’contributed most to cost overruns. In a fourth study on construction projectsin Nigeria by Elinwa&Buba (1994), it was found that ‘cost ofmaterials’, ‘fraudulent practices’ and ‘fluctuations in materials prices’Baloyi&Bekker • Causes of construction cost and time overrunshad the most significant impact on project costs. During extensivestudies on construction project performance in European countries,Morris & Hough (1987) as well as Flyvbjerg, Bruzelius&Rothengatter(2003) found that ‘fluctuations in material cost’ and ‘additional work’contributed most to cost overruns.

In reviewing the literature an approach and trend towards thetype of questions and results could be observed. In calculating thenumber of times specific types of causes for cost overruns undereach category were observed, the following can be concluded:

• The most significant factor causing cost overruns due to clientaction is ‘additional work or changes to work’. This cause waslisted as a major factor in five of the seven (71%) reviewedarticles.

• From a contractor’s perspective the most significantcontributor to cost overruns is ‘time delays’, listed in three ofthe seven (43%) reviewed articles.

• The most significant factor for cost overruns is evident fromexternal factors and that is ‘material price changes’. Thisfactor was listed in six of the seven (86%) reviewed articles.

Other common factors listed among contractors, consultants andclients were ‘poor estimates and material take-off’ and ‘delay inpayments’.

It can be argued that the factors mentioned do not stand aloneand that the ultimate cost overruns can be a result of multiplefactors contributing to the final cause for cost overruns. For example,additional work requested by a client can result in a delay in orderingmaterial which, in the mean time, was subject to price increasesor shortages. The views of clients, contractors and consultants onreasons for cost overruns could also be conflicting with stakeholdersdefending their operating domain and ‘shifting the blame’.

2.6 FACTORS CAUSING CONTRUCTION TIME DELAYS
Unfortunately, time delays on construction projects are more thenorm than the exception. Supplementing their research on thecauses for cost overruns, Kaminget al. (1997) found that ‘designchanges’, ‘materials shortage’ and ‘inadequate planning’ were themost significant contributors to time delays on construction projects.Ogunlana et al (1996) investigated  highrisebuildings and categorised their findings into client/consultantrelated,contractor-related and external causes for time delays.

The weighted findings among these three categories indicated that‘material shortages’, ‘overstretching of technical personnel’ and‘design changes’ were the most important causes for project delays.

Assaf, Al-Khalil & Al-Hazmi (1995) used 56 questions in threecategories, namely owner, architects/engineers and contractors, todetermine the main causes of delays on large building projects in

Saudi Arlagos. Their survey showed that contractors believed that‘preparation of shop drawings’, ‘delays in contractor’s progress’and ‘payment by owners’ were the most important factorscontributing to time delays. According to architects/engineers,‘cash flow’, ‘subcontractors’ schedules’ and ‘slowness of ownerdecision-making’ caused the most delays. Finally, owners were ofthe opinion that ‘design errors’, ‘excessive bureaucracy in project owner organisation’ and ‘labour shortages’ contributed most totime delays.

Walker (1995) surveyed Australian project representatives andfound that the most important factors that affect time delays are ‘the ability of the organisation to manage risk’, ‘planning capabilities’and ‘effective resource coordination’. Kumaraswamy& Chan (1998) studied time delays on Hong Kong projects and foundthat ‘unforeseen ground conditions’, ‘poor site management’ and‘slow speed of decision-making’ were the most prominent causesof time delays. The results from a study of 130 public projects in

Jordan by Al-Momani (2000) indicated that ‘poor design andnegligence by the owner’, ‘change orders’ and ‘poor weather andsite conditions’ contributed most to delays. Al-Khalil & Al-Ghafly (1999) studied public utility projects in Saudi Arlagos andfound that contractors considered ‘delay in claim settlement’, ‘slowdecision-making’ and ‘delays in progress payments’ as the mostimportant delay factors. Owners believed that ‘poor early planning’,‘scope changes’ and ‘financial difficulties by the contractors’ werethe major causes of delay. The consultants somehow supported theowners’ views by indicating ‘financial difficulties by the contractor’,‘improper contract knowledge’ and ‘ineffective planning’ as themost significant delay factors.

Odeh & Battaineh (2002) used only two points of view, namelycontractors and consultants, to determine the causes of project Baloyi & Bekker • Causes of construction cost and time overrunsdelays in Jordan. The results showed that contractors believed that‘poor labour productivity’, ‘owner interference’ and ‘inadequatecontractor experience’ were the three most important causesof delays. The consultants, however, indicated ‘inadequatecontractor experience’, ‘late payment of completed work’ and‘poor subcontracting’ to be the main causes of delay. The inclusionof ‘late payment of completed work’ as a cause for delay referredto the result of late payment on continuing site activities andcontractors halting work unless payment for completed work hadbeen processed after the agreed date.

Studying the significant factors that cause delay of constructionprojects in Malaysia, Alaghbari, Kadir, Salim&Ernawati (2007) used four categories for analysis, namely contractor, consultant,owner and external. As far as causes related to contractor actionsare concerned, ‘financial problems’, ‘shortage of materials’ and‘poor site management’ were ranked among the top three. Ownercauses included ‘delayed payments’, ‘slow decision-making’and ‘contract scope changes’. The top three consultant causeswere ‘poor supervision’, ‘slowness to give instructions’ and ‘lack ofexperience’.

Finally, external causes of delay included ‘shortage of materials’,‘poor site conditions’ and ‘lack of equipment and tools in themarket’. Faridi& El-Sayegh (2006) studied project delays inthe United Arab Emirates and found that the three main causesof project delays were ‘preparation and approval of drawings’,‘inadequate early planning of the project’ and ‘slowness of owner’sdecision-making processes’.

2.7 EMPIRICAL LITERATURE

Studies conducted on construction project delivery and its relationship to cost control techniques reveal that determining projectsuccess varies with every project an perspectives (Davies, 2013), there is no establishedframework or specific criterion for judging construction project success which makes itdifficult to measure (Griffin and Page, 1996; Chen et al, 2010; Hughes, Tippet and Thomas,2003; Schenhar et al, 2003).

Studies confirm that, optimally integrating a PDS and the efforts of project management fromthe start, delivers expected project outcomes, particularly the achievement of “sustainabilitygoals” (Mollaoglu-Korkmaz, Swarup& Riley, 2011p. 71). Way (2005) in his “framework ofsoft landings”, introduces a systematic way of ensuring sustainability of projects byintegrating feedback of “continual assessment” of project design into the operation phase

(Way, 2005; BSRIA, 2009 p.8). Therefore in theory, regardless of the PDS adopted, positiveproject outcomes should be achieved when projects participants ensure effective projectmanagement practices (De Wit, 1988).

Toor and Ogunlanain their study of problems in large-scale construction projects in Thailand,reveal that design related problems contribute to project failure (Toor and Ogunlana, 2010).

They go on to suggest that in DBB sytems, where design is executed separately fromconstruction, “a complete and comprehensive design is critical in the success of implementing the project (Toor and Ogunlana, 2008 p.426). Abandoned projects, delayed projectcompletion, high operational and maintenance costs, unsustainable project facilities andproject knowledge gaps are attributed to failed PDSs (Anvuur, Kumaraswamy, Male, 2006;Ahadzie, Proverbs and Olomolaiye, 2007;Ren, Kwaw and Yang, 2012; Smith and Jaggar,

2007).Gisela Gaba September 2013

Doloi (2012) also identifies key risk attributes that influence cost, time and operationalperformance of projects, and they include the “financial structure, government policy and design complexity” (Doloi, 2012 p.316). He opines that, little emphasis is put on performanceof project facilities after completion due to the focus put on “project evaluation context”(Doloi, 2012 p.316).

However, De Wit (1988) suggests “it is essential that a distinction is made between projectsuccess and the success of the project management effort” (De Wit, 1988 p.164), whereproject success is dependent on the degree to which project objectives are met (i.e. the impactof the final project outcome), whiles project management success is dependent on meetingtime, cost and quality objectives (De Wit, 1988). Studies on project delivery do revealmajority of project fail as a result of poor management of PDS (Ren, Kwaw and Yang, 2012),but studies subsequent to his work integrate both project and project management success tomean the same due to the evolution of the scope and demand of CP in recent times (Dainty,Cheng and Moore, 2003). Heravi and Ilbeigi (2012), developed on the DeWits theory bydeveloping a quantitative model which evaluates project success based on the product success(effect of the final product) and project management success (meeting cost, time and qualityobjectives), and argues that the perspective considered in defining project success play acritical part (Heravi and Ilbeigi, 2012).

The different dimensions and perspectives of project success identified from existingliterature are listed in Table 2.2. Its concluded that stakeholders perceive success based onfactors considered critical to their area of interest (Diallo and Thuiller, 2004; Griffin andPage, 1996). For instance, an end users perspective of a successful project is based onsatisfaction derived (Lim and Mohamed, 1999).
In recent years, there have been numerous studies on the identification ofinfluencing factors of project time and cost overruns worldwide. Mansfield et al(1994) carried out a questionnaire survey amongst 50 contractor, consultant andclient organisations in Nigeria and found out that the most important variablescausing construction delays and cost overruns are poor contract management,financing and payment of completed works, changes in site conditions, shortage ofmaterials, imported materials and plant items, design changes, subcontractors andnominated suppliers. While the top variables causing only cost overruns wererevealed as price fluctuation, inaccurate estimates, delays, additional work. Kaminget al (1997) identified factors influencing construction time and cost overruns on high-rise building projects in Indonesia through a questionnaire survey administeredon 31 project managers. A total of 11 variables (design changes, poor labourproductivity, inadequate planning, material shortages, inaccuracy of materialestimate, skilled labour shortage etc) were identified for time overrun and seven(materials cost increased by inflation, inaccurate quantity take-off, lack ofexperience of project location, lack of experience of project type etc) for costoverrun. Kumaraswamy and Chan (1998) conducted a more extensive study in HongKong using 400 questionnaires after which follow up interviews were held. Thestudy revealed the top ten causes of construction delays from the contractors’ pointof view as delays in design information, long waiting time for approval of drawings,poor site management and supervision, mistakes and discrepancies in designdocuments, etc. Similar survey studies were reported by Frimpong et al (2003) inGhana and by Assaf and Al-Hejji (2006) in Sandi Arlagos. In addition toquestionnaire surveys, other researchers adopted a case study approach. Al-Momani(2000) examined 130 public projects in Jordan and concluded that the main causesof delays include changes initiated by designers, client requirement, weather, siteconditions, late deliveries, economic conditions, etc. Hsieh et al (2004) conducted astatistical analysis in 90 metropolitan public work projects in Taiwan and identifiedproblems in planning and design as main causes of change orders. Yogeswaran et al(1998) scrutinised 67 civil engineering projects in Hong Kong and suggested that atleast a 15-20% time overrun was due to inclement weather. Based on analysis of 46completed building projects in the UK, Akinsola et al (1997) identified andquantitatively examined factors influencing the magnitude and frequency of high-rise building projects in Indonesia through a questionnaire survey administeredon 31 project managers. A total of 11 variables (design changes, poor labourproductivity, inadequate planning, material shortages, inaccuracy of materialestimate, skilled labour shortage etc) were identified for time overrun and seven(materials cost increased by inflation, inaccurate quantity take-off, lack ofexperience of project location, lack of experience of project type etc) for costoverrun. 
Kumaraswamy and Chan (1998) conducted a more extensive study in HongKong using 400 questionnaires after which follow up interviews were held. Thestudy revealed the top ten causes of construction delays from the contractors’ pointof view as delays in design information, long waiting time for approval of drawings,poor site management and supervision, mistakes and discrepancies in designdocuments, etc. Similar survey studies were reported by 
Frimpong et al (2003) inGhana and by Assaf and Al-Hejji (2006) in Sandi Arlagos. In addition toquestionnaire surveys, other researchers adopted a case study approach. Al-Momani(2000) examined 130 public projects in Jordan and concluded that the main causesof delays include changes initiated by designers, client requirement, weather, siteconditions, late deliveries, economic conditions, etc. Hsieh et al (2004) conducted astatistical analysis in 90 metropolitan public work projects in Taiwan and identifiedproblems in planning and design as main causes of change orders. Yogeswaran et al(1998) scrutinised 67 civil engineering projects in Hong Kong and suggested that atleast a 15-20% time overrun was due to inclement weather. Based on analysis of 46completed building projects in the UK, Akinsola et al (1997) identified andquantitatively examined factors influencing the magnitude and frequency of variations in building projects. These factors include: client characteristics,especially lack of prior experience and knowledge of construction projectorganization and the production processes; project characteristics, such as type, size,complexity and duration of the project; and project organisation factors, such as;design duration, percentage of design completed before tender, procurement andcontract type, adequacy of information provided, and number of sub-contractors.

While all the above studies, to various extents, helped with the better understandingof the problems associated with cost and time overruns in construction projects,there are some limitations. (1) Some of these studies are over 10 years old. There is aneed for a more up to date investigation to reflect any development in recent years.

CHAPTER THREE

RESEARCHMETHODOLOGY

3.0 INTRODUCTION

This chapter covers the description and discussion on the various techniques and procedures used in the study to collect and analyse the data as it is deemed appropriate.

It is organized under the following sub-headings:

· Research Design

· Area of the Study

· Population of the study

· Sample and sampling procedure

· Instrument of Data Collection

· Validation of the Instrument

· Reliability of the Instrument

· Method of Data Collection  

· Method of Data Analysis

3.1 RESEARCH DESIGN

According to Asika (2009), research designs are often referred to as the structuring of investigation aimed at identifying variables and their relationships to one another. In this study, questionnaire serves as useful guide to the effort of generating data for this study. The questionnaire is a survey method and it is an exploratory research.

3.2 AREA OF THE STUDY

The study area for this research is Imo state in eastern Nigeria.

The choice of Imo state as the study area is because since the creation of the state in 1967 and in spite of the movement of Lagos state in the state creation exercise of 1991, it naturally enjoys the benefits of being the fulcrum of the eastern part of the country. Imo state is built with many roads, estates , government establishments, all kinds of private developments, schools, hospitals, theaters, shopping malls, hotels to mention a few. All these infrastructures are the handiwork of construction. As such there cannot be a better place to obtain data for this study.
3.3 POPULATION OF THE STUDY

The population of study consists of public and private contractors involving civil engineers and quantity surveyors in Imo State. According to the Imo state ministry of Works, Corporate affairs Commision data, total registered contractors” amount to 352.

3.4 SAMPLE OF THE STUDY

Random sampling technique was used in selecting 50 contractors from the entire population. This was chosen due to the financial strength of the researcher coupled with time constraints.

3.5 INSTRUMENT FOR DATA COLLECTION

These are the tools or methods used in getting data from respondents. In this study, questionnaires and interview are research instruments used. Questionnaire is the main research instrument used for the study to gather necessary data from the sample respondents. The questionnaire is structured type and provides answers to the research questions and hypotheses therein.

This instrument is divided and limited into two sections; Section A and B. Section A deals with the personal data of the respondents while Section B contains research statement postulated in line with the research question and hypothesis in chapter one. Options or alternatives are provided for each respondent to pick or tick one of the options.

3.6 RELIABILITY AND VALIDITY OF INSTRUMENT

Reliability means the accuracy of precision of a measuring instrument while validity means the extent to which the research instrument measures what it is supposed to measure. In order to determine the reliability and validity of the study, the test-retest method was used. To have a valid instrument, the questions in the questionnaire will be free from ambiguity (i.e the questions will not be too complex). To have reliable instrument, the questionnaire will be followed with interview of sample of respondents to know whether their view on the subject.

3.7 TECHNIQUES OF DATA ANALYSIS

Having gathered the data through the administration of questionnaire, the collected data will be coded, tabulated, and analyzed according to the research question and hypothesis.

In order to analyze the data collected effectively and efficiently for easy management and accuracy, the simple percentage method was the analytical tools used for this research project and a sample size of two hundred (200) will be represented by 100% for easy analysis of the responses.

Also, Chi-square statistical analytical method will be used in the research work chi-square as a statistical technique is used in testing of hypothesis so as to predict what the relationship between two variables should be. It is used in drawing and reaching conclusion by collecting the observed values from the questionnaire administered to respondents, testing the degree of freedom and carrying out a decision in determining the critical value of the hypothesis.

The formular being

X2
=
(F0-FE)2


    FE

Where O
=
Observed Frequency


E
=
Expected Frequency

The X2 value obtained from the formular is compared with the value of tabulated X2 for a given significance level and degree of freedom.

CHAPTER FOUR
DATA ANALYSIS AND INTERPRETATION

4.1 PRESENTATION OF TABLES

	Table 1

Age Distribution of Respondents

	
	
	Frequency
	Percent
	Valid Percent
	Cumulative Percent

	Valid
	18-30
	5
	10.0
	10.0
	10.0

	
	31-60
	40
	80.0
	80.0
	90.0

	
	61 and above
	5
	10.0
	10.0
	100.0

	
	Total
	50
	100.0
	100.0
	


Source: Field Survey,  2025
Table 1 shows the age distribution of the respondents. 5 respondents representing 10% fall between the ages of 18-30 years, 40 respondents representing 80% fall between ages 31-60, while 5 respondents representing 10% are 61 years and above.

This shows that majority of the respondents are between the ages 31 to 60 years as indicated above.

	Table 2

Gender Distribution of Respondents

	
	
	Frequency
	Percent
	Valid Percent
	Cumulative Percent

	Valid
	Male
	46
	92.0
	92.0
	92.0

	
	Female
	4
	8.0
	8.0
	100.0

	
	Total
	50
	100.0
	100.0
	


Source: Field Survey,  2025
Table 2 shows the gender distribution of the respondents used for the study. 46 respondents making 92% are male, while the remaining 4 respondents representing 8% are female. This clearly shows that male respondents are the majority for the study.
	Table 3

Category of Contractors

	
	
	Frequency
	Percent
	Valid Percent
	Cumulative Percent

	Valid
	Public Sector
	1
	2.0
	2.0
	2.0

	
	Private sector
	49
	98.0
	98.0
	100.0

	
	Total
	50
	100.0
	100.0
	


Source: Field Survey,  2025
Table 3 clearly shows the category of contractors’ used for the study.  Respondent representing 2% works for the public sector, while the remaining 49 respondents representing 98% are private contractors/surveyors. This clearly shows that majority of the respondents used for the study are contractors/quantity surveyors who work in the private sector i.e they own their own firms.
	Table 4

Educational Background of Respondents

	
	
	Frequency
	Percent
	Valid Percent
	Cumulative Percent

	Valid
	OND
	1
	2.0
	2.0
	2.0

	
	HND/BSC
	41
	82.0
	82.0
	84.0

	
	Masters
	3
	6.0
	6.0
	90.0

	
	PhD
	1
	2.0
	2.0
	92.0

	
	Professional
	4
	8.0
	8.0
	100.0

	
	Total
	50
	100.0
	100.0
	


Source: Field Survey,  2025
Table 4 shows educational background of the respondents. 1 respondent representing 2% is an OND holder, 41 respondents representing 82% are HND/B.Sc. Holders, 3 respondents representing 6% are Masters holders, another respondent representing 2% is a Doctorate Degree holder, while the remaining 4 respondents own various professional degrees and diplomas in their various capacities.

This strongly suggests that the respondents are well educated as majority own degree awards from tertiary institutions and professional bodies in Nigeria. This goes ahead to validate the qualification of the selected respondents for this study as they will give accurate and un-biased insights into cost control techniques and project delivery in Nigeria.

	Table 5

Years of Experience

	
	
	Frequency
	Percent
	Valid Percent
	Cumulative Percent

	Valid
	1-5 Years
	3
	6.0
	6.0
	6.0

	
	6-10 Years
	44
	88.0
	88.0
	94.0

	
	11-30 Years
	3
	6.0
	6.0
	100.0

	
	Total
	50
	100.0
	100.0
	


Source: Field Survey,  2025
Table 5 shows the years of working experience of the respondents. 3 respondents representing 6% have worked between 1 to 5 years, 44 respondents representing 88% have gotten 6-10 years of experience, while the remaining 3 respondents representing 6% have gotten 11-30 years of working experience.

This goes ahead to further validate the suitability of the selected respondents for the study, as majority have gained wealth of experience in the construction industry.
	Table 6

Have you successful embarked and delivered a construction project successfully?

	
	
	Frequency
	Percent
	Valid Percent
	Cumulative Percent

	Valid
	Yes
	50
	100.0
	100.0
	100.0


Source: Field Survey,  2025
Table 6 seeks to find out the failure-success ratio of the respondents in terms of successful construction projects carried out. All 50 respondents representing 100% indicated that they have successfully carried out a construction project in the various fields of work.

	Table 7

If 'Yes' are you aware of the various cost control techniques used in construction projects?

	
	
	Frequency
	Percent
	Valid Percent
	Cumulative Percent

	Valid
	Yes
	50
	100.0
	100.0
	100.0


Source: Field Survey,  2025
Table 7 shows responses gotten when the respondents were asked about their level of awareness on the various cost control techniques used in the construction industry. All respondents who indicated earlier on that they have successfully undertaken a construction project indicated that they are aware of the various cost control techniques used in the construction industry. This also shows the qualification of the respondents for this study as all of the respondents are well embraced with the various cost control techniques.

	Table 8

If 'yes' do you apply these techniques when undertaking a construction project?

	
	
	Frequency
	Percent
	Valid Percent
	Cumulative Percent

	Valid
	Yes
	50
	100.0
	100.0
	100.0


Source: Field Survey,  2025
Table 8 shows the application of cost control techniques by the respondents. All the 50 respondents representing 100% indicated that they apply cost control techniques when embarking on a construction project.
	Table 9

Who is responsible for the development of these cost control techniques?

	
	
	Frequency
	Percent
	Valid Percent
	Cumulative Percent

	Valid
	Quantity Surveyor
	41
	82.0
	82.0
	82.0

	
	Accountant
	8
	16.0
	16.0
	98.0

	
	Project manager
	1
	2.0
	2.0
	100.0

	
	Total
	50
	100.0
	100.0
	


Source: Field Survey,  2025
Table 9 shows the individual or agency responsible for the development of the cost control plans. 41 respondents representing 82% indicated that the quantity surveyor is responsible for the development and implementation of a cost control plan, while 8 respondents representing 16% indicated the accountant, while the remaining 1 respondent representing 2% indicated that the project manager is responsible for cost control techniques and plans.

This clearly shows that the quantity surveyor is the major individual responsible for the development and implementation of a cost control technique/plan for a construction project as indicated by the respondents.

	Table 10 Cost Control Techniques Adopted

	
	
	Responses
	Percent of Cases

	
	
	N
	Percent
	

	Valid
	Budget and Cash Forecasting
	50
	37.9%
	100.0%

	
	variance Analysis
	16
	12.1%
	32.0%

	
	Cost Value Reconciliation
	32
	24.2%
	64.0%

	
	Earned Value Analysis
	7
	5.3%
	14.0%

	
	Cost Scheduling
	27
	20.5%
	54.0%

	Total
	132
	100.0%
	264.0%

	Source: Field Survey,  2025

	
	


Table 10 shows the various cost control techniques employed by the respondents for the study in a multiple response format (Since two or more cost control techniques could be adopted by a respondent). All 50 respondents representing 100% of the total population/case have employed the budget and cash forecasting techniques, 16 respondents in the same population/case representing 32% have adopted the Variance analysis cost control technique, 32 respondents representing 64% have adopted the Cost value reconciliation technique, while another 7 have adopted the Earned Value Analysis technique, another 27 respondents have adopted the Cost scheduling technique.

This clearly shows that majority of the respondents apply the budget and forecast cost control techniques when undertaking construction projects.
	Table 11

As a contractor do you encounter problem(s) when managing the cost of construction?

	
	
	Frequency
	Percent
	Valid Percent
	Cumulative Percent

	Valid
	Yes
	50
	100.0
	100.0
	100.0


Source: Field Survey,  2025
Table 11 shows responses from respondents when asked if the encounter cost control problems during the construction project phase. Al the respondents representing 100% indicated that they encounter cost control problems when embarking on a construction project.

	Table 12

Which of these problems are mostly encountered by contractors?

	
	
	Frequency
	Percent
	Valid Percent
	Cumulative Percent

	Valid
	labour related problems
	7
	14.0
	14.0
	14.0

	
	Cost Estimate problems
	13
	26.0
	26.0
	40.0

	
	Variations in Cost
	13
	26.0
	26.0
	66.0

	
	Design Errors
	13
	26.0
	26.0
	92.0

	
	Material related problems
	4
	8.0
	8.0
	100.0

	
	Total
	50
	100.0
	100.0
	


Source: Field Survey,  2025
Table 12 shows cost control challenges/problems encountered by the respondents used for the study. 7 respondents representing 14 % have labour cost related problems, 13 respondents representing 26% have cost estimates problems, 13 respondents representing 26% have variation in cost problems, another 13 respondents representing 26% have design error problems, while the remaining 4 respondents representing 8% have materials related problems.

	Table 13

Cost Control Problems Encountered in the Construction Process

	
	
	Responses
	Percent of Cases

	
	
	N
	Percent
	

	Valid
	Labour Related problems
	50
	24.0%
	100.0%

	
	Cost Estimate problems
	50
	24.0%
	100.0%

	
	Design Error
	32
	15.4%
	64.0%

	
	Cost Control System problems
	29
	13.9%
	58.0%

	
	Cost Scheduling
	47
	22.6%
	94.0%

	Total
	208
	100.0%
	416.0%

	Source: Field Survey,  2025
	
	


Table 13 shows multiple responses on the cost control problems the respondents encounter during the construction project process. All the respondents representing 100% of the population/case indicated labour related problems and cost estimation problems. 32 of the same population indicated design error, 29 respondents indicated Cost Control System problem, while others numbering 47 indicated Cost scheduling as a problem.
	Table 14

Can Cost control problems lead to construction projects delivery failure?

	
	
	Frequency
	Percent
	Valid Percent
	Cumulative Percent

	Valid
	Strongly Agree
	49
	98.0
	98.0
	98.0

	
	Agree
	1
	2.0
	2.0
	100.0

	
	Total
	50
	100.0
	100.0
	


Source: Field Survey,  2025
Table 14 shows the effect of the identified problems in table 12 above on the delivery of a construction project. 49 respondents representing 98% indicated that final cost is affected, while the remaining respondent representing 2% indicated that final cost is not affected. This implies that cost related problems encountered during construction projects add up to the final cost of a construction project.

	Table 15
Do Cost Control techniques affect delivery of a construction Project?

	
	
	Frequency
	Percent
	Valid Percent
	Cumulative Percent

	Valid
	Strongly Agree
	32
	64.0
	64.0
	64.0

	
	Agree
	17
	34.0
	34.0
	98.0

	
	Neutral
	1
	2.0
	2.0
	100.0

	
	Total
	50
	100.0
	100.0
	


Source: Field Survey,  2025
Table 15 shows the effect of cost control techniques on the construction project. 32 respondents representing 64% strongly agree that cost control techniques affect the construction project, 17 respondents representing 34% agree, while the remaining respondent representing 2% was neutral on the subject matter.

This implies that there is a strong relationship between cost control techniques and the construction project delivery as majority of the respondents strongly agree that cost control techniques employed for a construction project can affect its delivery.

	Table 16
What major components facilitate a construction project?

	
	
	Frequency
	Percent
	Valid Percent
	Cumulative Percent

	Valid
	Labour
	25
	50.0
	50.0
	50.0

	
	Material
	17
	34.0
	34.0
	84.0

	
	Organization
	5
	10.0
	10.0
	94.0

	
	stakeholders
	3
	6.0
	6.0
	100.0

	
	Total
	50
	100.0
	100.0
	


Source: Field Survey,  2025
Table 16 highlights the major components that facilitate a construction project. 25 respondents representing 50% indicated labour, 17 respondents representing 34% indicated materials, 5 respondents representing 10% indicated the organization, while the remaining 3 respondents representing 6% indicated the stakeholders.

	Table 17

Are cost control techniques applied in within these components?

	
	
	Frequency
	Percent
	Valid Percent
	Cumulative Percent

	Valid
	Yes
	50
	100.0
	100.0
	100.0


Source: Field Survey,  2025
Table 17 shows responses on whether cost control techniques are being applied in the construction component. All 50 respondents indicated “Yes”.

	Table 18

Have cost control techniques affected labor?

	
	
	Frequency
	Percent
	Valid Percent
	Cumulative Percent

	Valid
	Yes
	49
	98.0
	98.0
	98.0

	
	No
	1
	2.0
	2.0
	100.0

	
	Total
	50
	100.0
	100.0
	


Source: Field Survey,  2025
Table 18 shows the effect of cost control technique on labour. 49 respondents indicated that cost control technique has effect on labour, while the remaining respondent representing 2% ndicated otherwise.
	Table 19

How have labour been affected?

	
	
	Frequency
	Percent
	Valid Percent
	Cumulative Percent

	Valid
	Money is adequately budgeted for wages and salaries
	22
	44.0
	44.9
	44.9

	
	Wages are paid on time
	14
	28.0
	28.6
	73.5

	
	Workers are paid early, hence motivation for work is increased and project delivered on time
	13
	26.0
	26.5
	100.0

	
	Total
	49
	98.0
	100.0
	

	Missing
	System
	1
	2.0
	
	

	Total
	50
	100.0
	
	


Source: Field Survey,  2025
Table 19 shows the various ways in which labour has been been affected by cost control techniques. 22 respondents representing 44% indicated that money is adequately budgeted for wages and salaries, 14 respondents representing 28% indicated that Wages are paid on time, 13 respondents representing 26% indicated that Workers are paid early, hence motivation for work is increased and project delivered on time.
	Table 20

Have material been affected?

	
	
	Frequency
	Percent
	Valid Percent
	Cumulative Percent

	Valid
	Yes
	50
	100.0
	100.0
	100.0


Source: Field Survey,  2025
Table 20 shows the effect of cost control technique on labour. All 50 respondents indicated that cost control technique has effect on Materials management. 

	Table 21

How have material for construction been affected?

	
	
	Frequency
	Percent
	Valid Percent
	Cumulative Percent

	Valid
	Quality Materials are sourced for at cheaper prices
	23
	46.0
	46.9
	46.9

	
	Needed materials are adequately budgeted for
	14
	28.0
	28.6
	75.5

	
	wastages are minimized
	12
	24.0
	24.5
	100.0

	
	Total
	49
	98.0
	100.0
	

	Missing
	System
	1
	2.0
	
	

	Total
	50
	100.0
	
	


Source: Field Survey,  2025
Table 21 highlights the effect of cost control techniques on materials management in the construction project. 23 respondents representing 46% indicated that quality materials are sourced at cheaper prices, 14 respondents representing 28% indicated that needed materials are adequately budgeted for, while the remaining 1 respondent indicated that wastages are minimized. One respondent failed to answer this question. 
CHAPTER FIVE
SUMMARY OF FINDINGS, CONCLUSION AND RECOMMENDATIONS

5.1 SUMMARY OF FINDINGS

The study observed that in the majority of cases, contractors’ efforts to manage projectscosts are centred on management of project resources. This resource-centric strategy premised onmaterials, plant and labour resources management is founded on the principle that resourcesconsumption stimulates building project costs. Statistical analysis performed through chi-squaretest at 95% shows that: cost reports, cost estimating and budgeting, variance analysis, cost valuereconciliation and resources management are the significant factors employed by contractors tomanage costs on construction projects in Nigeria. However, despite the existence of thesestrategies, most contractors admit that their projects would, in most cases, end with a cost overrun.

This may be inferentially explained by a host of challenges affecting cost management practice.Whereas several challenges were observed with respect to cost management, it is labour relatedchallenges, materials related challenges and organisationalproblems that impact significantly oncost management practice. The study also observed that the cost management process inNigeria, like in other developing countries in Africa and elsewhere is still dominated by thetraditional paper based system or ‘prematurely’ developed automated systems of managingproject cost information. In a nutshell, the problem in Nigeria is not about having the strategiesto manage costs but relates to ‘flawed’ implementation. The findings of this research suggest thatthe strategies instituted to manage project cost and, the challenges to such practice are notsignificantly different from the ones in other developing countries.
5.2 CONCLUSION

The construction industry is a key industry to economic growth of any nation providingshelter for economic and social activities including on-site and off-site infrastructure to facilitatethe smooth functioning of these activities. The industry does not only touch on the lives ofvirtually everyone on a daily basis; it occupies a fundamental national position in many nationaleconomies – hence the importance of this research. The study aimed at examining the impact of cost control techniques on construction projects and the challenges contractors face when implementing these cost control techniques.

5.3 RECOMMENDATIONS

To improve on the effectiveness of contractors’ costmanagement strategies in Nigeria, the research recommends that contractors pay particularattention to problem areas that significantly affect cost management (labour, material andorganisational related challenges),  engagement of experienced cost management personnel orupgrading of staff’s professional ingenuity through conventional training, refresher courses orparticipation in seminars; and regular review of cost management systems and strategies. Theindustry can also take advantage of advancement in ICTS to automate their cost informationmanagement systems. This study has provided baseline information on the strategies used tomanage project cost and related challenges; however, further research is needed to assess theeffectiveness of these strategies to manage project cost.
REFRENCES
Al-Khalil, M.I. & Al-Ghafly, M.A. 1999. Important causes of delay in public utility projects in 
Saudi Arlagos. Construction Managementand Economics, 17(5), pp. 647-655.

Al-Momani, A.H. 2000. Construction delay: A quantitative analysis. International Journal of 
Project Management, 18(1), pp. 51-59.

Chan Daniel w. m. and Kumaraswamy Mohan M., (2002),  Compressing constructiondurations: 
lessons learned from Hong Kong building projects, InternationalJournal of Project 
Management, Vol.20, PP. 23.35

DissanayakaSunnil M. and Kumaraswamy Mohan M., (1999),  Comparingcontributors to time 
and cost performance in building projects, Building andEnvironment, Vol. 34, PP. 31- 42

Faridi, A.S. & El-Sayegh, S.M. 2006. Significant factors causing  delayin the UAE construction 
industry. Construction Management andEconomics, 24(11), pp. 1167-1176.

Iyer K.C. and Jha K.N., (2005), Factors affecting cost performance:  evidence fromIndian 
construction projects, International Journal of Project Management, Vol. 23, PP. 283.295

JouiniSihem Ben Mahmoud, Midler Christophe and Garel Gilles, (2004), Time-to marketvs. 
time-to-delivery; managing speed in engineering, Procurement andConstruction projects, 
International Journal of Project Management, Vol.22,PP. 359.367

Kaming, P.F., Olomolaiye, P.O., Holt, G.D. & Harris, F.C. 1997. Factors influencing 
construction 
time and cost overruns on high-rise projects in Indonesia. Construction 
Management 
Economics, 15(1),pp. 83-94.

Kuprenas John A., (2003), Project management actions to improve  design phase 
costperformance, Journal of Management in Engineering, Vol. 19, No.1, PP. 25-32

Love Peter E. D., Tse Raymond Y. C. and Edwards David J., (2005),  Time-Cost Relationships 
in Australian Building Construction Projects, Journal ofConstruction Engineering and 
Management, Vol. 131, No. 2, PP. 187-194.
Odeh, A.M. &Battaineh, H.T. 2002. Causes of construction delay: Traditional 
contracts.International Journal of Project Management,20(1), pp. 67-73.

Ogunlana, S.O., Promkuntong, K. &Jearkjirm, V. 1996. Constructiondelays in a fast-growing 
economy: Comparing Thailand with othercountries. International Journal of Project 
Management, 14(1),pp. 37-45.

OkuwogaAdeyinka A., (1998), Cost .time performance of public  sector housingprojects in 
Nigeria, Habital Intl., Vol. 22, No. 4, PP. 389 . 395

Pheng Low Sui and ChuanQuek Tai, (2006), Environmental factors  and workperformance of 
project managers in the construction industry, InternationalJournal of Project 
Management, Vol. 24, PP. 24.37

Reichelt Kimberly and Lyneis James, (1999), The dynamic of project 




 performance: Benchmarking the drivers of cost and schedule overrun, 
Europeanmanagement journal, Vol. 17, No.2, PP. 135-150

Walker, D.H.T. 1995. An investigation into construction time performance. Construction 
Management and Economics, 13(3), pp. 263-274.

APPENDIX

QUESTIONNAIRE

SECTION A

PERSONAL INFORMATION

1. AGE:
 a) 18-30


b) 31-60


C) 61 and Above

2. GENDER A) MALE

`
  B) FEMALE

3. CATEGORY A) PRIVATE CONTRACTOR

      B) PUBLIC CONTRACTOR

4. EDUCATIONAL LEVEL OND HND/BSC MASTERS PROFESSIONAL PHD

5. YEARS OF EXPERIENCE
1-5   6-10   10 AND ABOVE

SECTION B

6. Have you successful embarked and delivered a construction project successfully?

YES   NO

7. If 'Yes' are you aware of the various cost control techniques used in construction projects?

YES NO

8. If 'yes' do you apply these techniques when undertaking a construction project?

YES NO

9. Who is responsible for the development of these cost control techniques?

QUANTITY SURVEYOR

ACCOUNTANT

PROJECT MANAGER

10. WHAT COST CONTROL TECHNIQUE(S) DO YOU ADOPT WHEN EMBARKING ON A CONSTRUCTION PROJECT?

Budget and Cash Forecasting

Variance Analysis

Cost Value Reconciliation

Earned Value Analysis

Others……………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………..

11. As a contractor do you encounter problem(s) when managing the cost of construction?

Yes

No

12. If yes what are the problems?

………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………

13. Which is the most pressing problem?

……………………………………………………………………………………………………………………………………………………………………………..

14, Can Cost control problems lead to construction projects delivery failure?

STRONGLY AGREE

AGREE

NEUTRAL

DIS-AGREE

STRONGLY DISAGREE

15. Do Cost Control techniques affect delivery of a construction Project?
STRONGLY AGREE

AGREE

NEUTRAL

DIS-AGREE

STRONGLY DISAGREE

16. What major components facilitate a construction project?

……………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………..

17. Are cost control techniques applied in within these components?

YES

NO

18.  Have cost control techniques affected labor?

YES

NO

19. IF YES HOW HAVE LABOUR BEEN AFFECTED?

……………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………….

20. HAS MATERIAL MANAGEMENT BEEN AFFECTED BY COST CONTROL TECHNIQUES?

YES

NO

21 IF YES HOW?

…………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………….
i

