ASSESSMENT OF CONSTRUCTION MANAGEMENT TECHNIQUES IN NIGERIA CONSTRUCTION INDUSTRY

(A Case Study of Ibadan, Oyo State)

BY

ABDULFATAI SHAKIRAT OLUWANIFEMI

HND/23/BLD/FT/0081

BEING A RESEARCH PROJECT SUBMITTED TO THE DEPARTMENT OF BUILDING TECHNOLOGY INSTITUTE OF ENVIRONMENTAL STUDIES KWARA STATE POLYTECHNIC, ILORIN

IN PARTIAL FULFILLMENT OF THE REQUIREMENT FOR THE AWARD OF HIGHER NATIONAL DIPLOMA (HND) IN  BUILDING TECHNOLOGY,  KWARA STATE POLYTECHNIC, ILORIN

JULY, 2025

CERTIFICATION

This research project has been read and approved as meeting the requirement for Award of Higher National Diploma (HND) in Building Technology, Institute of Environmental Studies, Kwara State Polytechnic, Ilorin.

________________________					_________________

MR. ATOLAGBE VICTOR OLADIMEJI				DATE

(Project Supervisor)

________________________				    	_________________

BLDR. ABDULGANIYU ALEGE						DATE

(Project Coordinator)

________________________					_________________

BLDR. ABDULGANIYU ALEGE						DATE

(Head of Department)

________________________					_________________

BLDR. ALIYU SULAIMAN FUNSHO (MNIOB)			DATE

EXTERNAL EXAMINER

# DEDICATION

# I dedicate this project to Almighty God for the successful completion. It is also been dedicated to my parent

# AKNOWLEDGEMENT

# I ultimately use this medium to express my profound gratitude to Almighty God who has been my source of inspiration and has been with me through my project the maker of heaven and earth for his clemency on me all the times and whose mercies and protection sustained me all through the course of project.

# My appreciation goes to my kind supervisor ATOLAGBE VICTOR OLADIMEJI and also other lecturer like BLDR. AKEEM and many more of them the teaching and non-teaching staffs. May the almighty God reward them for all their Good.

# From the depth of my heart I express my profound gratitude to my lovely, caring parent MR and MRS ABDULFATAI for their moral, financially, and spiritually support, May God almighty show his love towards them and not forget my lovely family. I pray to God to continue to enhance you more and your effort on me wont go in vain and I pray also that may you reap the fruit of your labor.

TABLE OF CONTENTS

Title page										i

Certification										ii

Dedication										iii

Acknowledgement 									iv

Table of contents									vi

Abstract										vii

CHAPTER ONE: INTRODUCTION

  - 1.1	Background to the Study 							1-2

# 1.2	Statement of the Research Problem                                                                 2-3

1.3	Research Questions							 	3

1.4	Aim and Objective of the study	Area						4

# 1.5	Justification for the Study							4

# 1.6       Scope of the Study								4-5

1.7 	Limitation of the Study							5

1.8	Definition of terms								5

# CHAPTER TWO: LITERATURE REVIEW

  - 2.1	Construction Project Management						6

  - 2.1.1	Construction Project Integration Management					7

  - 2.1.2	Construction Project Scope Management						7

## 2.1.3	Construction Project Time Management					7-8

2.1.4	Construction Project Cost Management					9-10

2.2	functions of construction project management				10

2.2.1	The Role of Construction Project Managers					10-11

2.2.2	Construction management techniques and tools				11-22

2.3	Construction Project Management Phases					22-24

CHAPTER THREE: RESEARCH METHODOLOGY

3.1	Research Strategy								25

3.2	Research design								25

3.3	Research Population								25

3.4	Sample frame									26

3.5	Sample size									26

3.6	Sampling Technique								26

3.7	Data Collection Instrument							26-27

3.8	Approach/Procedure for Data Collection					27

3.9	Method of Data Analysis							27-28

CHAPTER FOUR: DATA PRESENTATION, ANALYSIS AND DISCUSSION OF RESULTS

4.0	Introduction									29

4.1	Levels of Measurement							29

4.2	Analysis and Presentation of Results						29-37

CHAPTER FIVE: SUMMARY, CONCLUSION AND RECOMMENDATIONS

5.1	Summary of Findings								37-38

5.2	Conclusion									39-40

5.3	Recommendation								40-41

References									42-43

Abstract

Construction Management is the art of directing and coordinating human and material resources throughout the life of a construction project by using modern construction management techniques to achieve predetermined objectives of scope, cost, time, and quality and participation satisfaction. Project management in construction encompasses a set of objectives which may be accomplished by implementing a series of operations subject to resource constraints. There are potential conflicts between the stated objectives with regard to scope, cost, time and quality, and the constraints imposed on human material and financial resources. These conflicts should be resolved at the onset of a project by making the necessary tradeoffs or creating new alternatives. The construction management techniques are useful to professionals in the construction field in their day to day construction endeavours. 10 architects, 10 quantity surveyors, 10 builders, 20 engineers and 15 other professionals giving a total of 65 questionnaires were distributed while 60 respondents were returned. This study had necessitated the assessment of the various Construction Management Techniques in the Nigeria Construction Industry taking Ibadan in Oyo State as a case study. The technique discussed in this study include Gantt chart, Programme Evaluation and Review Technique ( PERT), Critical Path Method ( CPM), Line of Balance, Work Breakdown Structure, PRINCE 2 , Network Analysis, Graphical Evaluation and Review Technique (GERT), Project Sensitivity Analysis, Cost Benefit Analysis and lot of others and factors such as Size of the project, Location of the project, Type of Client Source of finance , Complexity of the project, Vitality of the materials, Poor planning, Materials storage, Cost of transportation and storage and so on constitute the factors affecting construction Management Techniques in the Nigeria Construction Industry.

CHAPTER ONE

INTRODUCTION

# 1.1	BACKGROUND TO THE STUDY

A major concern of stakeholders (clients, consultants, contractors, e.t.c) in Nigerian construction industry is how to improve service delivery. Mitullah and Wachira (2003) have reported that the development of an efficient construction industry is an objective of policy in most countries.

The construction industry is the pivot of any economy and a belief held in both the developed and developing countries (Nubi. 2003). Adam (1992) emphasized that through its contribution v to National Gross Domestic Product (GDP), labour, employment and gross fixed capital formation (GFCF) construction industry’s importance in the overall economy cannot be underestimated. The industry provides the infrastructure, buildings, roads, bridges, dams, ports and other construction products that are required for economic development.

Construction is a $ 1.7 trillion industry worldwide (Bray, 2005). Global construction is said to have contribution amounting to between 5 and 7 percent of GDP in most countries and accounts for a significant part of global cross capital formation-a little under one third (Brays, 2005). The United Nations Environment programme (UNEP) has noted that about one-tenth of the global economy is dedicated to construction and operating homes and offices (UNEP, 1996). Mitullah and Wichira (2003) also stated that construction activity plays a vital role in the process of economic growth and development, both through its products (infrastructure, buildings) and through the employment created in the process of construction itself.

The construction industry in Nigeria is of paramount importance for employment and economic growth (Ogunsemi and Jagboro, 2006). Presently, the construction industry in Nigeria contributes about3percenttothenation’s Gross Domestic Product (GDP) (Aganga, 2010).This is far below between 5 and 7 percent of GDP in most countries. Therefore, effort gears towards improving the efficiency of the construction industry in Nigeria in terms of improving on construction management techniques is worthwhile and will contribute to better performance of the industry. This study therefore examines the construction management techniques among contracting firms in Ibadan, Oyo State.

A project is made up of a group of interrelated work activities constrained by a specific scope, budget, and schedule to deliver capital assets needed to achieve the strategic goals of an Agency (Idoro and Patunola – Ajayi, 2009). All projects must have a beginning and an end. The management of construction projects requires knowledge of modern management as well as an understanding of the design and construction process. Construction projects have a specific set of objectives and constraints such as a required time frame for completion. While the relevant technology, institutional arrangements or processes will differ, the management of such projects has much in common with the management of similar types of projects in other specialty or technology domains such as aerospace, pharmaceutical and energy developments (Muller and Turner, 2007). Construction Project management is the art of directing and coordinating human and material resources throughout the life of a construction project by using modern construction management techniques to achieve predetermined objectives of scope, cost, time, quality and participationsatisfaction(IdoroandPatunola–Ajayi,2009).Bycontrast,thegeneral management of business and industrial corporations assumes a broader outlook with greater continuity of operations. Nevertheless, there are sufficient similarities as well as differences between the two so that modern management techniques developed for general management may be adapted for project management. (Arnaboldi et.al, 2004)

A working knowledge of general management and familiarity with the special knowledge domain related to the project are indispensable. Supporting disciplines such as computer science and decision science may also play an important role. In fact, modern management practices and various special knowledge domains have absorbed various techniques or tools which were once identified only with the supporting disciplines. (Arnaboldi et.al, 2004). For example, computer- based information systems and decision support systems are now common-place tools for general management. Similarly, many operations research techniques such as linear programming and network analysis are now widely used in many knowledge or application domains.

Construction project management encompasses a set of objectives which may be accomplished by implementing a series of operations subject to resource constraints. There are potential conflicts between the stated objectives with regard to scope, cost, time and quality, and the constraints imposed on human material and financial resources. (Idoro and Patunola – Ajayi, 2009) These conflicts should be resolved at the onset of a project by making the necessary tradeoffs or creating new alternatives.

# 1.2	STATEMENT OF RESEARCH PROBLEM

The construction business in Nigeria is a multi-billion dollar industry with hardly any year falling short of expected windfalls befalling successful contractors who bid for construction projects, the last 5years has witnessed increasing patronage and profit for most construction companies in Nigeria (Business Day Nigeria, 2010). This is especially seen with some publicly quoted companies like Julius Berger Plc. Costain West Africa and G. Cappa Plc which have recorded steadily rising profits with the last two just recovering from years of consistent loses. Many others which are not publicly quoted are rapidly expanding their operations to meet up with greater challenges such as PW limited, Lekki Concession Company and Hitech all of which are handling major infrastructural projects like roads and drainage reconstruction/expansion and Land reclamation ( from the Lagos Lagoon) projects ( Business Day Nigeria, 2010).

Recently a number of development projects by government and private sector companies have created opportunities for construction companies to reap massive revenues. For instance, in recent times in most states of Nigeria infrastructural projects like road reconstruction, housing projects, bridge building, construction of drainage, dams rural electrification, city expansion and beautification projects among others have been on the increase especially in Lagos, Rivers and Akwa Ibom states where massive amounts of money running into tens of billions of dollars have been voted for capital projects. Against this background, with more capital investment in the construction industry in Nigeria because the nation is at the developing stage, there is a need to investigate construction management techniques in use among contracting firms or organization in Ibadan, Oyo State.

# 1.3	RESEARCH QUESTIONS

From the above information, the research question generated which this study provides answers to are:

- What are the construction management techniques in the construction industry in Ibadan, Oyo state?

- What are the factors affecting the construction management techniques in Ibadan, Oyo state?

- What are the impact of construction management techniques on construction cost, time and overall performance in Ibadan, Oyo State?

# 1.4	AIM AND OBJECTIVES OF THE STUDY AREA

The aim of this study is to evaluate tools / techniques for managing construction project with a view to improving project delivery process in Ibadan, Oyo State. The study specific objectives are to:

- identify and assess construction management techniques in the construction industry in Ibadan, Oyo State,

- identify and assess factors affecting the construction management techniques in Oyo state, and

- Examine the impact of construction management techniques on construction cost, time and quality in Ibadan, Oyo state.

# 1.5	JUSTIFICATION FOR THE STUDY

Nigeria has large expanse of undeveloped land requiring road construction to link many part of the country with other parts and construction of low cost housing to accommodate many of its city dwellers. Also that many state governments are coming to terms with the importance of sticking to master plans and town planning laws means that in coming years many large scale construction projects will be embarked upon. Major infrastructures like good road networks, that will support development are lacking and hence is major cause of in adequate foreign investments (Business Day Nigeria, 2010).

This has prompted governments at both state and federal levels to embark on long term infrastructure projects. State and Federal governments are looking for alternative sources of revenue (non-oil based sources) like taxation which depends largely on available infrastructure. Of recent, crude oil deposits have been found in some parts of Nigeria implying that very soon infrastructural work would begin in surrounding areas. However, this is also dependent on security as the Niger delta is highly notorious for security threats from militants. Therefore, good management techniques will definitely determine the kind of output of the industry and measure the efficiency of the industry in Nigeria with Ibadan in Oyo State as a case study.

# 1.6	SCOPE OF THE STUDY

The management of construction project is a tool for achieving an efficient construction industry. The scope of construction projects ranging from buildings (institutional, commercial, public buildings e.t.c), civil engineering (roads, culverts, bridges e.t.c) among others. The scope of this study is limited to some Construction Industries some Construction Industries in Oyo State in Oyo State.

1.7	LIMITATION OF THE STUDY

The dissertation covers the Assessment of Construction Management Techniques in the Nigeria Construction Industry taking Ibadan, Oyo State as the case study area. The essay is however limited to the following:

- Financial constraints

- Time constraints and

- Lack of access to some information needed for the project work.

1.8	Definition of terms

Construction: is the process involved in delivering buildings, infrastructure, industrial facilities, and associated activities through to the end of their life. It typically starts with planning, financing, and design that continues until the asset is built and ready for use. Construction also covers repairs and maintenance work, any works to expand, extend and improve the asset, and its eventual demolition, dismantling or decommissioning.

Management:  refers to the process of planning, organizing, leading, and controlling resources to achieve specific goals within an organization.

Construction industry: refers to the industrial branch of manufacturing and trade related to building, repairing, renovating, and maintaining infrastructures.

Technique: a way of carrying out a particular task, especially the execution or performance of an artistic work or a scientific procedure.

CHAPTER TWO

LITERATURE REVIEW

## 2.0		Introduction

This chapter describes the review of relevant literatures that are related to this study. Among issues addressed by the chapter include the understanding of the term “Construction Project Management, Construction Management Techniques and Tools, Construction Managers among others. This review provides a holistic situation and app5oach to management techniques applicable in construction industry.

## 2.1	Construction Project Management

Construction project management according to Opara, (1986) is the overall planning, co- ordination and control of a project from inception to completion aimed at meeting a client’s requirements in order to produce a functionally and financially viable project that will be completely feasible. Construction Project Management is that which applies to the construction sector (Lewis J.P (2007). The most common responsibilities ofa Construction Manager according to The Construction Management Association of America (CMAA) fall under the following seven (7) categories: Project Management Planning, Cost Management, Time Management, Quality Management, Contract Administration, Safety Management and CM Professional Practice which includes specific activities like defining the responsibilities and management structure of the project management team, organizing and leading by implementing project controls, defining roles and responsibilities and developing communication protocols and identifying elements of project design and construction likely to give rise to disputes and claims. Arnaboldi et.al, 2004).

A project manager is a professional in the field of project management having the responsibility of planning, execution and closing of any project, typically relating to construction industry, architecture e.t.c (Muller and Turner, 2007). Project Management according to PMBOK (2004) is application of knowledge, skills, tools and techniques to project activities to achieve project requirements. Project management is accomplished through the application and integration of the project management processes of initiating, planning, monitoring, controlling and closing. (Wysocki and Lewis, 2001).

PMBOK (2004) identifies nine knowledge areas that Construction Project Managers should be familiar with in order to be considered professionals. These are as follows:

## 2.1.1	Construction Project Integration Management

Project integration management ensures that the project is properly planned, executed and controlled, including the exercise of formal project change control. As the term applies, every activity must be co-ordinated or integrated with every other one in order to achieve the desired project outcomes. (Muller and Turner, 2007)

## 2.1.2	Construction Project Scope Management

Changes to project scope are often the factors that “kill” a project. Scope management includes authorizing the job, developing a scope management that will define the boundaries of the project, sub-dividing the work into manageable components with deliverables, verifying that the amount of work planned has been achieved and specifying scope change control procedures. (Muller and Turner, 2007).

## 2.1.3	Construction Project Time Management

Time management implies personal efforts to manage one’s time. For Construction projects, it refers to developing a schedule that can be met, then controlling work to ensure that this happens. Project Time Management in construction can be called schedule management (Patel2008)

This is however a powerful technique, particularly for white collar, supervisory and management personnel Time management involves minimization of wasteful elements of person’s administrative work. Lack of efficient and efficient time management leads to:

- Interruptions by drop-in visitors (without appointment)

- Attending lengthy and unnecessary meetings that accomplish very little

- Inability to say “no” for some tasks

- Procrastination and lack of decisiveness

- In ability to delegate work

- Taking on much more than can be handled

- Lack of responsibility and authority to do certain jobs

- Delayed, in accurate or inadequate information

- Taking orders from too many people

- Handling too many “crisis” situations

- Lack of organization of tasks by priority or target dates

- Lack of determination to complete tasks assigned

- Lack of organization on and around desk

- Unnecessary socialization

- Poor filling system

- Making unnecessary trips to people, departments, copy machines etc.

- Excessive conversation time

- Too many rescheduling of meeting, personal engagements etc. (Stukenbruck & Zomorrodian, 1987)

All these does not encourage and will never improve productivity level in construction industry because time they say is money. Efficient use of time during construction however will always improve human productivity level in a construction industry. It is too often ignored, particularly by management people who preach productivity to their subordinates.

To minimize these “time-wasters”, time management applies simple, common-sensible but very effective programming rules to very item of work, one of which is: “never handle same task twice”. (Stukenbruck & Zomorrodian, 1987) Employees are given freedom in determining their hours of work. The schedule of the time series can be given as:

- Core time (hours when all employees must be at work)

- Flexibletime(hourswhenemployeescanvarytheirtimeofarrivalanddeparture)Compressed Work Week: Working for same number of hours but for fewer days /week

- 08hours 05 days

- 10hours 04 days

This time schedule series is a concept of time management knowing when to work, the time allocated in hours for each tasks to be done and the relaxation period to cool down heels. (Stukenbruck & Zomorrodian, 1987)

## 2.1.4	Construction Project Cost Management

This involves estimating the cost of resources, including people, equipment, materials and such things as travel and other support details. Costs are budgeted and tracked to keep the project within the budget. (Patel, 2008)

Construction Project Quality Management: As commented by Pinto (2005), one cause of project failure is that quality is overlooked or sacrificed so that a tight deadline can be met. It is not very helpful to complete a project on time, only to discover that the thing delivered won’t work properly. Quality Management included both quality assurance (planning to meet quality requirements) and quality control (steps taken to monitor results to see if they conform to requirements).

## Construction Project Human Resource Management

Managing human resources is often overlooked in construction projects. It involves identifying the people needed to do the job, defining their roles, responsibilities and reporting relationships, acquiring those people and then managing them as the project is executed. (White & Fortune, 2002)

## Construction Project Communications Management

Communication management involves planning, executing and controlling the acquisition and dissemination of all information relevant to the needs of all project stakeholders. This information will include project status, accomplishments events that may affect other stakeholders or projects and so on. (White & Fortune, 2002)

## Construction Project Risk Management

Risk Management is the systematic process of identifying, quantifying, analyzing and respondingtoprojectrisk.Itincludesmaximizingtheprofitabilityandconsequencesofpositive events and minimizing the profitability and consequences of adverse events to project objectives. This is an extremely important aspect of project management that is sometimes overlooked by novice project managers. (White & Fortune, 2002)

## Construction Project Procurement Management

Procurement of necessary goods and services for the project is the logistics aspects of managing a job. It involves deciding what must be procured, issuing request for bids or quotations, selecting vendors, administering contracts and closing them when the job is finished.

2.2	FUNCTIONS OF CONSTRUCTION PROJECT MANAGEMENT

The functions of project management for construction generally include the following:

- Specification of project objectives and plans including delineation of scope, budgeting, scheduling, setting performance requirements, and selecting project participants.

- Maximization of efficient resource utilization through procurement of labor, materials and equipment according to the prescribed schedule and plan.

- Implementation of various operations through proper coordination and control of planning, design, estimating, contracting and construction in the entire process.

- Development of effective communications and mechanisms for resolving conflicts among the various participants.

According to Adedeji (1989), Construction planning is a fundamental and challenging activity in the management and execution of construction projects. It involves the choice of technology, the definition of work tasks, the estimation of the required resources and durations for individual tasks, and the identification of any interactions among the different work tasks. A good construction plan is the basis for developing the budget and the schedule for work. Developing the construction plan is a critical task in the management of construction, even if the plan is not written or otherwise formally recorded. In addition to these technical aspects of construction planning, it may also be necessary to make organizational decisions about the relationships between project participants and even which organizations to include in a project. For example, the extent to which sub-contractors will be used on a project is often determined during construction planning.

# 2.2.1	THE ROLE OF CONSTRUCTION PROJECT MANAGERS

A construction project’s execution is planned and controlled by the project manager. The project manager is assigned by the Agency or the contractor (Westland, 2003). The project manager must have adequate authority to exercise the responsibility of forming and managing a team for support of the project. The project manager must have prior experience managing similar projects in the past. If an Agency cannot commit such an individual with adequate time and resources, the Agency is well advised to outsource project management services for management of the project. The project manager may be tasked with management of multiple projects that may require assignment of additional project managers for support. In such cases the project manager is taking on the role of project manager activities without a project manager. It shows the multiple interactions an Agency faces without a project manager to manage the work activities involved in delivering a new capital asset (Westland, 2003). Project management organization is structured with the assignment of a project manager to manage project work activities. (White and Fortune, 2002).

# 2.2.2	CONSTRUCTION MANAGEMENT TECHNIQUES AND TOOLS

Different techniques and tools are used in managing projects for a describable outcome. Some of these techniques are Work Breakdown Structure, Gantt Charts, PRINCE 2, Project Networks (Critical path Networks and Programme Evaluation and Review Techniques), Project Sensitivity Analysis, Cost Benefit Analysis, Graphical Evaluation and Review Technique( GERT) and Construction Project Software.

Work Breakdown Structure (WBS) deals with breaking down of the project into manageable individual components din a hierarchical structure. Such a structure defines tasks that can be completed independently of other tasks, facilitating resource allocation, assignment of responsibilities and measurement and control of project. Wysocki (2009) also observed that it is a veritable tool for defining work packages and developing and tracking the cost and schedule for the project. Work Breakdown Structure (WBS) provides a common framework for the natural development of the overall planning and control of a project and it is the basis for dividing work into definable increment from which the Statement of Work can be developed and technical, schedule cost and labour hour reporting can be established. (Abbasi & Al- Mharmah, 2000)

Gantt chart is a useful construction technique for planning and scheduling projects. It shows graphical representation of the duration of the duration of tasks against progression of time. It was developed by Henry Gantt in 1915 purposely for monitoring projects progression and tracki8ng. Gantt charts have become a common technique for representing the phases and activities of a project Work Breakdown Structure (WBS) sop they can be understood by a wide audience all over the world (Wysocki, 2009). The Gantt chart is a popular type of bar chart that illustrates a project schedule. Gantt charts illustrate the start and finish dates of the activities and summary elements of a project. Activities and summary elements comprise the work breakdown structure of the project. Some Gantt charts also show the dependency (i.e. precedence network) relationships between activities. Henry Laurence Gantt (1861-1919) was a mechanical engineer, industry advisor and management consultant. He developed first examples of Gantt chartsin 1910. Gantt charts were used as a visual tool to illustrate the start and finish dates of the terminal elements and summary elements of a project. Accepted as a commonplace project management tool today, it was an innovation of world-wide importance at that time. Gantt charts were used in large construction projects like the Hoover Dam started in 1931, and the USA interstate highway system started in 1956. In the 1980s, personal computers eased the creation and editing of elaborate Gantt charts, and they have since been developed from simple linked bar charts into network (or precedence) diagrams and are widely used for planning and scheduling projects. The Gantt chart is the most widely used of the techniques; perceived by the Construction Industry as being the easiest and most recognizable form of programming.

### The Current Application of these Methods:-

Today, the Gantt chart is accepted as a commonplace project management tool. This method, via the numerous desktop computer applications that are available, is primarily used by construction project managers and project planners in the management of projects. It is popular because it allows you to estimate how long a construction project should take, lays out the order in which tasks need to be carried out, helps manage dependencies between tasks, determines the resources needed, monitors progress and helps to see how remedial action may bring the project back on course.

The Line of Balance (LOB) technique was originated by the Goodyear Company in the early 1940's and was developed by the U.S. Navy in the early 1950's for the programming and control of both repetitive and non-repetitive construction projects. LOB was first applied to industrial manufacturing and production control, where the objective was to attain or evaluate a production line flow rate of finished products. The basic concepts of LOB have since been applied in the construction industry as a planning and scheduling method. Several attempts either to modify the basic LOB technique or to develop variations named differently have also been made (Examples, to name a few include: velocity diagrams, the construction planning technique, the vertical production method, the linear scheduling method, time space scheduling method, and repetitive project model). Lines of Balance diagram are techniques used in the construction industry to illustrate the planned sequence of work and to allow adjustments due to changed circumstances. There are potentially very few projects where a LOB diagram cannot be used and be of benefit. As seen above though, for more complex projects this perhaps may only be at a summarized level. Generally, for all main works and main subcontractors, it will assist in the management of both the subcontractor and the project. The diagrams are usually much easier to read than a detailed Gantt chart, making it a good tool for reporting purposes and for illustrating the inter-relationship between different activities. The LOB method is not simple though when dealing with a construction project that is broken down into a large number of activities that are bound by numerous and complicated relationships and other constraints. The ensuing diagram is not as effective and can prove more complicated to read than the traditional Gantt chart.

Network Analysis methods are very popular in larger projects but present complications in projects of repetitive nature such as high-rise building construction. Critical Path Method (CPM) based techniques have been criticized for their inability to model repetitive projects. The first problem is the sheer size of the network. In repetitive projects of n units, the network prepared for one unit has to be repeated n times and linked to each other; this results in a huge network that is difficult to manage. This may cause difficulties in communication among the members of the construction management team and difficulties in foreseeing the likely effect of delays. The second problem is that the Critical Path Method of analysis used in network analysis is designed primarily for optimizing project duration rather than adequately dealing with the special resource constraints of repetitive projects. Indeed, the critical path method has no capability to assure a smooth procession of labour teams from unit to unit with no conflict and no idle time for workers and equipment. This leads to hiring and procurement problems in the flow of labour and material during construction.

Prince 2 which connotes Project In Controlled Environment 2 is a process based method for effective project management. It is a de facto standard used extensively by the UK government and is widely recognized in the private and public sector, both in the UK and internationally. Its features include focus on business justification, division of project into manageable and controllable stages, flexible in application at a level appropriate to the project management team. PRINCE 2 basically describes product based planning, change control technique and quality review technique.

Project Sensitivity Analysis determines which variable have the most potential to affect project. Variables include task duration, success rate and costs, risks, lags between predecessors and successors, project duration, total project cost and so on. It is also useful in decision making under uncertainty and risk (Abbasi & Al- Mharmah, 2000)

Cost Benefit Analysis (CBA) is one of the most widely accepted and applied methods for project appraisal for large scale infrastructure in the public and private sector. CBA is a prescriptive technique that provides guidance on the criteria to take account in decision making, ensuring that the net aggregate benefits to society outweigh net aggregate cost ( Patel, 2008)

Graphical Evaluation and Review Technique (GERT) is a network analysis technique used in construction project management that allows probabilistic treatment of both network logic and activity duration estimates. It is a useful management tool for planning, coordinating and controlling complex projects (Westland, 2003). The key objective of GERT is to evaluate on the basis of the network logic and estimated duration of the activity and derive inference about some activities that may not be performed. GERT can be used with a complimentary network analysis evaluation of activities (path) has the least amount of scheduling flexibility and therefore will most likely determine when the project can be completed. (Muller & Turner, 2007).

Programmne Evaluation and Review Technique (PERT) is an event-and-probability based network analysis system generally used in projects where activities and t heir durations are difficult to define. PERT is often used in large programme where the project involves numerous organizations at widely different locations. (Abbasi & Al- Mharmah, 2000) An alternative to CPM is the PERT project planning model, which allows a range of durations to be specified for each activity. In Program evaluation and review technique (PERT), complex projects require a series of activities, some of which must be performed sequentially and others that can be performed in parallel with other activities. This collection of series and parallel tasks can be modeled as a network. While CPM is easy to understand and use, it does not consider the time variations that can have a great impact on the completion time of a complex project. The Program Evaluation and Review Technique (PERT) is a network model that allows for randomness in activity completion times. PERT was developed in the late 1950's for the U.S. Navy's Polaris project having thousands of contractors. It has the potential to reduce both the time and cost required to complete a project. (Pinto, 2007). The Network Diagram In a project, an activity is a task that must be performed and an event is a milestone marking the completion of one or more activities. Before an activity can begin, all of its predecessor activities must be completed. Project network models represent activities and milestones by arcs and nodes. PERT originally was an activity on arc network, in which the activities are represented on the lines and milestones on the nodes. Overtime, some people began to use PERT as an activity on node network. The PERT chart may have multiple pages with many sub-tasks.

### Steps in the PERT Planning Process

PERT planning involves the following steps:

- Identify the specific activities and milestones.

- Determine the proper sequence of the activities.

- Construct a network diagram.

- Estimate the time required for each activity.

- Determine the critical path.

- Update the PERT chart as the project progresses.

- Identify Activities and Milestones: The activities are the tasks required to complete the project. The milestones are the events marking the beginning and end of one or more activities. It is helpful to list the tasks in a table that in later steps can be expanded to include information on sequence and duration.

- Determine Activity Sequence: This step may be combined with the activity identification step since the activity sequence is evident for some tasks. Other tasks may require more analysis to determine the exact order in which they must be performed.

- Construct the Network Diagram: Using the activity sequence information, a network diagram can be drawn showing the sequence of the serial and parallel activities. For the original activity- on-arc model, the activities are depicted by arrowed lines and milestones are depicted by circles or "bubbles". If done manually, several drafts may be required to correctly portray the relationships among activities. Software packages simplify this step by automatically converting tabular activity information into a network diagram.

- Estimate Activity Times: Weeks are a commonly used unit of time for activity completion, but any consistent unit of time can be used. A distinguishing feature of PERT is its ability to deal with uncertainty in activity completion times. For each activity, the model usually includes three time estimates:

  - Optimistic time - generally the shortest time in which the activity can be completed. It is common practice to specify optimistic times to be three standard deviations from the mean so that there is approximately a 1% chance that the activity will be completed within the optimistic time.

  - Most likely time - the completion time having the highest probability. Note that this time is different from the expected time.

  - Pessimistic time - the longest time that an activity might require. Three standard deviations from the mean are commonly used for the pessimistic time. PERT assumes a beta probability distribution for the time estimates. For a beta distribution, the expected time for each activity can be approximated using the following weighted average: Expected time = (Optimistic + 4 x Most likely + Pessimistic ) / 6 This expected time may be displayed on the network diagram. To calculate the variance for each activity completion time, if three standard deviation times were selected for the optimistic and pessimistic times, then there are six standard deviations between them, so the variance is given by: [ ( Pessimistic - Optimistic ) / 6 ]2 The variance in the project completion time can be calculated by summing the variances in the completion times of the activities in the critical path. Given this variance, one can calculate the probability that the project will be completed by a certain date assuming a normal probability distribution for the critical path. The normal distribution assumption holds if the number of activities in the path is large enough for the central limit theorem to be applied. Make adjustments in the PERT chart as the project progresses. As the project unfolds, the estimated times can be replaced with actual times. In cases where there are delays, additional resources may be needed to stay on schedule and the PERT chart may be modified to reflect the new situation.

### Benefits of PERT

PERT is useful because it provides the following information: • Expected project completion time.

        - Probability of completion before a specified date. •The critical path activities that directly impact the completion time.

        - The activities that have slack time and that can lend resources to critical path activities.• Activity start and end dates.

### Limitations of PERT

The following are some of PERT's weaknesses:

        - The activity time estimates are somewhat subjective and depend on judgments. In cases where there is little experience in performing an activity, the numbers may be only a guess. In other cases, if the person or group performing the activity estimates the time there may be bias in the estimate.

        - Even if the activity times are well-estimated, PERT assumes a beta distribution for these time estimates, but the actual distribution may be different.

        - Even if the beta distribution assumption holds, PERT assumes that the probability distribution of the project completion time is the same as that of the critical path. Because other paths can become the critical path if their associated activities are delayed, PERT consistently underestimates the expected project completion time. The underestimation of the project completion time due to alternate paths becoming critical is perhaps the most serious of these issues. To overcome this limitation, Monte Carlo simulations can be performed on the network to eliminate this optimistic bias in the expected project completion time.

Lean construction Management Technique: Managing construction under Lean is different from typical contemporary practice because it has a clear set of objectives for the delivery process, is aimed at maximizing performance for the customer at the construction project level, designs concurrently product and process, and applies production control throughout the life of the project. By contrast, the current form of production management in construction is derived from the same activity centered approach found in mass production and project management. (Arnabodi, Azzone, & Savoldelhi, 2004) It aims to optimize the project activity by activity; assuming customer value has been identified in design. Production is managed throughout a project by first breaking the project into pieces, i.e. design and construction, then putting those pieces in a logical sequence, estimating the time and resources required to complete each activity and therefore the project. Each piece or activity is further decomposed until it is contracted out or assigned to a task leader, foreman or squad boss. Control is conceived as monitoring each contract or activity against its schedule and budget projections (Arnabodi, Azzone, &Savoldelhi, 2004). These projections are rolled up to project level reports. If reliable workflow was a consequence of stopping the line rather than a stated objective. Activities or chains along the critical path fall behind, efforts are made to reduce cost and duration of the offending activity or changing the sequence of work. If these steps do not solve the problem, it is often necessary to trade cost for schedule by working out of the best sequence to make progress. The focus on activities conceals the waste generated between continuing activities by the unpredictable release of work and the arrival of needed resources. Simply put, current forms of production and construction project management focus on activities and ignore flow and value considerations (Koskela 1992, Koskela and Huovila 1997). Managing the combined effect of dependence and variation is a first concern in lean production.

### Just In Time Method (JIT)

The acronym JIT has been highly visible since the late 1980's, as manufacturing attempted to meet competitive challenges by adopting newly emerging management theories and techniques. Manufacturing JIT is a method of pulling work forward from one process to the next "just-in-time"; i.e. when the successor process needs it, ultimately producing throughput. One benefit of manufacturing JIT is reducing work-in-process inventory, and thus working capital. An even greater benefit is reducing production cycle times, since materials spend less time sitting in queues waiting to be processed (Arnabodi, Azzone, & Savoldelhi, 2004)However, the greatest benefit of manufacturing JIT is forcing reduction in flow variation, thus contributing to continuous, ongoing improvement. Can this approach be applied to construction?

Construction JIT:JIT is a technique developed by Taichi Ohno and his fellow workers at Toyota. Ohno's fundamental purpose was to change production's directives from estimates of demand to actual demand--a purpose originally rooted in the absence of a mass market and the need to produce small lots of many product varieties. In assembly line production systems managed by lean production concepts, the directives for production are provided by means of kanban from downstream processes. This system insures that whatever is produced is throughput, i.e. is needed for the production of an order. The application of JIT to construction differs substantially from its application to manufacturing because construction and manufacturing are different types of production, and because of the greater complexity and uncertainty of construction. The extent and significance of uncertainty in construction has been adequately addressed in earlier papers but a moment's reflection supports the view that construction is complex. The number of parts, relative lack of standardization, and the multiple participants and constraining factors easily make the construction of an automobile factory more difficult than the production of an automobile in that factory. When this complexity is joined with economic pressures to minimize time and cost, that uncertainty results is not surprising. But is construction really a different type of production than manufacturing, or simply a more complex and uncertain version of manufacturing itself? What kind of production is construction? Construction according to Akpan and Chizea (2002) is the final component in manufacturing's product development process. Construction is complete before manufacturing's production begins. Consequently, it is misleading to conceive construction as analogous to factory production (although some aspects of construction fit better in that analogy; i.e. fabrication). Construction is best conceived as a product development process, extending from product design through process design to facility (the manufacturing process tool) construction, the end result of which is readiness for manufacturing (Akpan and Chizea, 2002). Admittedly, this is a best fit in the case of industrial construction, and becomes less plausible as we move toward the cookie cutter end of the industry spectrum, e.g. manufactured housing. There seems to be a gray zone between manufacturing and construction, where the work looks like construction because final assembly is done where the facility is to be used, but looks like manufacturing because all that remains of the process is to match production output with sales. This gray zone is obviously ripe for industrialization and mechanization, which ultimately pushes it over into the camp of manufacturing. The proper business of construction is completing product and process design.

Once that is done, it is but a matter of time before wit and invention capture mere assembly for manufacturing. Uncertainty is a necessary component in construction conceived as a product development process. The very purpose of the process is to surface and resolve trade-offs between means and ends, all the way from product design through facility construction. The management of projects so conceived is the proper terrain for lean construction concepts and techniques. So, construction is a different type of production than manufacturing, and has greater uncertainty and flow variation. (Akpan and Chizea 2002).

### Monte Carlo Technique

Monte Carlo simulation, or probability simulation, is a technique used to understand the impact of risk and uncertainty in financial, project management, cost, and other forecasting models. How It Works: In a Monte Carlo simulation, a random value is selected for each of the tasks, based on the range of estimates. The model is calculated based on this random value. The result of the model is recorded, and the process is repeated. A typical Monte Carlo simulation calculates the model hundreds or thousands of times, each time using different randomly- selected values. When the simulation is complete, we have a large number of results from the model, each based on random input values. These results are used to describe the likelihood, or probability, of reaching various results in the model.

Critical Path Method (CPM):- In 1957, DuPont developed a construction project management technique designed to address the challenge of shutting down chemical plants for maintenance and then restarting the plants once the maintenance had been completed. Given the complexity of the process, they developed the Critical Path Method (CPM) for managing such projects.

The most widely used scheduling technique in Construction Project Management is the critical path method. (CPM) for scheduling, often referred to as critical path scheduling. (Arnabodi, Azzone, & Savoldelhi, 2004).

This method calculates the minimum completion time for a project along with the possible start and finishes times for the project activities. Indeed, many texts and managers regard critical path scheduling as the only usable and practical scheduling procedure. Computer programs and algorithms for critical path scheduling are widely available and can efficiently handle projects with thousands of activities.

The critical path

It represents the set or sequence of predecessor/successor activities which will take the longest time to complete. The duration of the critical path is the sum of the activities' durations along the path. Thus, the critical paths can be defined as the longest possible path through the "network" of project activities. The duration of the critical path represents the minimum time required to complete a project. (Arnabodi, Azzone, & Savoldelhi, 2004).Any delays along the critical path would imply that additional time would be required to complete the project. There may be more than one critical path among all the project activities, so completion of the entire project could be delayed by delaying activities along any one of the critical paths. For example, a project consisting of two activities performed in parallel that each requires three days would have each activity critical for a completion in three days. Formally, critical path scheduling assumes that a project has been divided into activities of fixed duration and well defined predecessor relationships. A predecessor relationship implies that one activity must come before another in the schedule. No resource constraints other than those implied by precedence relationships are recognized in the simplest form of critical path scheduling. To use critical path scheduling in practice, construction planners often represent a resource constraint by a precedence relation. A constraint is simply are striction on the options available to a manager, and a resource constraint is a constraint deriving from the limited availability of some resource of equipment, material, space or labor. For example, one of two activities requiring the same piece of equipment might be arbitrarily assumed to precede the other activity. This artificial precedence constraint insures that the two activities requiring the same resource will not be scheduled at the same time. Also, most critical path scheduling algorithms impose restrictions on the generality of the activity relationships or network geometries which are used. In essence, these restrictions imply that the construction plan can be represented by a network plan in which activities appear as nodes in a network.

CPM provides the following benefits:

- Provides a graphical view of the project.

- Predicts the time required to complete the project.

- Shows which activities are critical to maintaining the schedule and which are not. CPM models the activities and events of a project as a network. Activities are depicted as nodes on the network and events that signify the beginning or ending of activities are depicted as arcs or lines between the nodes. (Arnabodi, Azzone, & Savoldelhi, 2004).

The following is an example of a CPM network diagram: CPM Diagram Steps in CPM Project Planning

- Specify the Individual Activities: From the work breakdown structure; a listing can be made of all the activities in the project. This listing can be used as the basis for adding sequence and duration information in later steps.

- Determine the Sequence of the Activities: Some activities are dependent on the completion of others. A listing of the immediate predecessors of each activity is useful for constructing the CPM network diagram.

- Draw the Network Diagram: Once the activities and their sequencing have been defined, the CPM diagram can be drawn. CPM originally was developed as an activity on node (AON) network, but some project planners prefer to specify the activities on the arcs.

- Estimate Activity Completion Time: The time required to complete each activity can be estimated using past experience or the estimates of knowledgeable persons. CPM is a deterministic model that does not take into account variation in the completion time, so only one number is used for an activity's time estimate.

- Identify the Critical Path: The critical path is the longest-duration path through the network.

The significance of the critical path is that the activities that lie on it cannot be delayed without delaying the project. Because of its impact on the entire project, critical path analysis is an important aspect of project planning. The critical path can be identified by determining the following four parameters for each activity:

  - ES - earliest start time: the earliest time at which the activitycan start given that its precedent activities must be completed first.

  - EF - earliest finish time: equal to the earliest start time for the activity plus the time required for completing the activity.

  - LF - latest finish time: the latest time at which the activity can be completed without delaying the project.

  - LS - latest start time: equal to the latest finish time minus the time required to complete the activity. The slack time for an activity is the time between its earliest and latest start time, or between its earliest and latest finish time. Slack is the amount of time that an activity can be delayed past its earliest start or earliest finish without delaying the project. The critical path is the path through the project network in which none of the activities have slack, that is, the path for which ES=LS and EF=LF for all activities in the path. A delay in the critical path delays the project. Similarly, to accelerate the project it is necessary to reduce the total time required for the activities in the critical path.

- Update CPM Diagram: As the project progresses, the actual task completion times will be known and the network diagram can be updated to include this information. A new critical path may emerge, and structural changes may be made in the network if project requirements change. (Arnabodi, Azzone, & Savoldelhi, 2004).

### CPM Limitations

CPM was developed for complex but fairly routine projects with minimal uncertainty in the project completion times. For less routine projects there is more uncertainty in the completion times, and this uncertainty limits the usefulness of the deterministic CPM model.

# 2.3	CONSTRUCTION PROJECT MANAGEMENT PHASES

Project management phases otherwise known as project lifecycle refers to the stages in a project’s development. Project life cycle is important because it demonstrates the logic that governs a project. It also helps in developing plans for carrying out the project. (Pinto, 2007) identified four distinct project life cycle phases which are:

Conceptualization: According to Pinto (2007) refers to the development of the initial goal and technical specification for a project. The scope of work is determined, necessary resources (people, money, material and machine) identified and important organizational contributions to stakeholders signed on. Also feasibility study is conducted at this stage to investigate whether the project can be continued or not.

Planning: Is the stage in construction in which detailed specifications, schematic, schedules and other plans are developed and steps necessary to meet the project’s objectives are put in place. At this stage, the individual pieces of the project called work packages are broken down, individual assignment made and the process for completion clearly delineated (Muller & Turner, 2007). Project schedule, the actual work and the estimated cost of completion are also identified. Anything that might pose a threat to the successful completion of the project is also identified at this stage. Finally all the project stakeholders must be identified at this stage of the project so as to establish a communication plan that describes information needed and the delivery method to be used to keep stakeholders informed (Patel, 2008).

Execution: Execution phase with actual performance of the work of the project. Progress is continuously monitored and appropriate adjustments are made and variances recorded so as to maintain the original project plan. The project manager uses this information to maintain control over the direction of the project by measuring the performance of the project activities comparing the results with the project plan and takes corrective actions as needed (Westland, 2003).

Termination: This occurs when the completed project is transferred to the customer, project documentation is handed over to the business, suppliers’ contracts terminated, project resources released and the project closure communicated to all Stakeholder.

(AustralianJournalofBusinessandManagementResearchVol.1,No.8(01-07)November-20

|  | CRITICAL BARRIERS/PROBLEMS OF IMPLEMENTING EFFECTIVE CONSTRUCTION MANAGEMENT: |
| --- | --- |
| • | Family-controlled industry |
| • | Monopolistic market, in some segments, some high competitive |
| • | Erratic in flow of orders |
| • | Lack of productivity and quality culture |
| • | Shortage of funds low level codification |
| • | Automation-not encouraged |
| • | Low priority of market and commercial activities |
| • | Poor after service |
| • | Complicated government policy, rules and regulations |
| • | Poor infrastructure support/road transport |
| • | Energy shortage |
| • | Poor working conditions, light, ventilation, safety, housekeeping |
| • | Non availability of basic material components (to be imported) |
| • | Unreliable suppliers |
|  | (White &Fortune, 2002) |

CHAPTER THREE

RESEARCH METHODOLOGY

## 3.0	Introduction

This chapter is view of the various approaches to data collection and analysis adopted in conducting this research; it explains the type of research strategy adopted the mode of data collection and the methodology used in carrying out this research. The study focuses on the assessment of construction management techniques in the Nigerian construction industry with Ibadan in Oyo state as a case study.

## 3.1	Research Strategy

Research strategy is defined by Naoum (1999) as the way in which research objectives can be questioned. The type of research adopted for this research is the qualitative research. The purpose for its adoption being the nature of the research, due to the subjective nature of the qualitative approach to research. It emphasizes meanings, experiences e.t.c. The information that was gathered under this research is was two forms; exploratory and attitudinal.

The exploratory research dealt with the area of this research in which I had limited knowledge, it helped in showing how much the average Nigerian tertiary institutions students have entrepreneurial orientation and mindset in their daily academic endeavors.

Attitudinal research as used in this research was used to evaluate the views and opinions of the respondents as regards assessment of construction management techniques.

## 3.2	Research design

The research design employed in this study is descriptive statistics. Exposition is made on the sources of data, method of data collection, sampling and sampling techniques, research instrument and data analysis method used.

## 3.3	Research Population

The study population for this study shall comprise the construction professionals who are in active practices in the study area. The professionals include Architects, Quantity Surveyors, Engineers, Builders e.t.c Information about the professionals were obtained from the register of their various professional bodies to find out the list of those registered with their professional bodies. The list forms the basis for consultation and selection of sample for this study.

## 3.4	Sample frame

A sample is a specimen or part of a whole (population) which is drawn to show what the rest is like (Naoum, 1999). For this research, a sample was drawn from a population and adequate measure was taken to ensure that the characteristics of the sample are the same as its population as a whole.

## 3.5	Sample size

The sample size for a study is the representation of the population to be studied. The sample size for this study was obtained from the register of their various professional bodies. For this study, 10 architects, 10 quantity surveyors, 10 builders, 20 engineers and 15 other professionals giving a total of 65 respondents constituted the sample size for the study

## 3.6	Sampling Technique

For this research, a purposive sampling of the participants in the selected area was conducted. Purposive sampling technique is a method of selection whereby there are no fixed means of selection of respondents but the administrator distributes questionnaire at his/ her convenience or as come in contact. The sample consists of professionals in diverse field of construction- Architects, Quantity Surveyors, Builders, Engineers e.t.c A total of sixty-five questionnaires were administered and sixty were retrieved. The retrieved questionnaires were used for analysis which covers 93% of the administered questionnaires.

## 3.7	Data Collection Instrument

The instruments for the collection of data are the various modes available to extract data and information from respondents. As a result of the nature of the study, the instrument for data collection used for the study was questionnaire. The basic elements of all questionnaires are the questions; therefore, a careful thorough planning was required in the construction of the questions

    - Identification of the first thought question; this is a form of precipitate from the objectives and the literature review. It forms the backbone upon which the questionnaire is constructed and at this stage; quite a number of questions were generated though the order and wording was not of consideration.

    - Formulation of the final questions; at this stage the questions from the initial stage were fine-tuned and divided into two different sections to aid the respondents and also to facilitate easy analysis. The first section identifies the demographic information about the respondents. These include their academic and professional qualifications, years of work experience in service and other relevant information.

The questions contained in the questionnaire consists basically of factual questions which are required to gather facts related to the background of the individual respondents, their age, academic levels and their perception construction management techniques. The other questions which require some level of objectivity for its assessment. For this reason various format were employed in asking questions, some of which include ranking and checklist.

The questionnaire approach was adopted because the purpose of this research is clear enough to be explained in a few paragraph and the respondents can make adequate contribution without ambiguity. Also as the questionnaire approach has the advantage of a wide coverage, wide consultation on the part of the respondent and also economical, hence, it is best suited for this research.

In order to guard against some of the disadvantages associated with the questionnaire approach, which include lack of control over respondent, ambiguity in the structure of the questions,fatigue due to excessive inflow of questionnaire from various researchers e.t.c. an unstructured interview was conducted to increase the reliability of the data and information gathered through the questionnaire approach. The interview was based on abstract from the questionnaire and the respondents gave a wider and comprehensive detail as regards construction management techniques in the construction industry.

## 3.8	Approach/Procedure for Data Collection

The approach adopted for carrying out this research was employed due to the nature of the investigation and the type of data and information that was required and available. The approach adopted for this research is the field work (primary data collection). The field work research refers to the methods of primary data collection and in this case the practical approach used is the problem solving approach. This involved assessing the construction management techniques in the Nigeria construction industry.

## 3.9	Method of Data Analysis

The methods of analysis used in this research were selected due to the type of data available for the analysis and the objectives of the research. Most of the questions were qualitative; hence the descriptive method of analysis is best suited for the analysis. Such methods include the frequency distribution; percentages, tabulations, charts. e.t.c. Likert scales rating was usedwithinterval5to 1 where1representstheleastrankingand 5representsthehighestranking which addressed issues on the objectives of this study. The scale includes very high, high, moderate, low and very low.

# CHAPTER FOUR

ANALYSIS OF DATA AND PRESENTATION OF RESULTS

## 4.0	Introduction

This chapter presents the analysis and results of the data collected. It also explains the method of measurement used, method of coding and the type of analyses carries out. From these analyses, different conclusions are made as regards the assessment of construction management techniques in the Nigeria construction industry.

## 4.1	Levels of Measurement

Measurement is the procedure in which a researcher assigns numerals (numbers or other symbols) to empirical properties (variables) according to rules (Naoum, 1999). In order to select the most appropriate method of analysis, the appropriate level of measurement must be used. The levels of measurement used in this research are the nominal and likert scale.

The nominal scale was used to assign variables into different classification and also to assign variables based on their properties and the Likert scale was used to rank the number of respondentsopinionrangingfrom“veryhigh”to“verylow”Thislevelofmeasurementwasused as it is easier to analyze data in numeric values than in letters of strings.

# 4.2	ANALYSIS AND PRESENTATION OF RESULTS

The descriptive method of data analysis is employed for this research. The method of analysis will follow the structure set out in the questionnaire in order to achieve the objectives of the research

## Table4.2.1: Type of Business

| TYPE OF BUSINESS | NUMBER OF RESPONDENTS | PERCENTAGE |
| --- | --- | --- |
| Consulting | 20 | 33.33 |
| Contracting | 22 | 36.67 |
| Government Institutions | 18 | 30 |
| TOTAL | 60 | 100 |

Source: Field Survey, 2025

From the table above, the number of respondents that is running consulting type of business are 20 (33.33%), those in contracting business are 22 (36.67%), while those in government institution 18(30%). Therefore, the percentage of respondents on contracting type of business is the highest.

## Table 4.2.2: Years of  Experience of the Firm/Organization

| Years of experience | Frequency | Percentage (%) |
| --- | --- | --- |
| 0-5 | 10 | 16.67 |
| 6-10 | 15 | 25 |
| 11-15 | 23 | 38.33 |
| 16-20 | 9 | 15 |
| Above20 | 3 | 5 |
| TOTAL | 50 | 100 |

Source: Field Survey, 2025

Table4.4 shows that the respondents with years of experience between11-15years are the highest with the total number of 23 (38.33 %) out of 60 (100%)

## Table4.2.3RespondentDesignation

| Designation | Frequency | Percentage (%) |
| --- | --- | --- |
| Architect | 10 | 16.67 |
| Quantity Surveyor | 10 | 16.67 |
| Builder | 10 | 16.67 |
| Engineer | 20 | 33.33 |
| Others | 10 | 16.67 |
| TOTAL | 60 | 100 |

Source: Field Survey, 2025

Table 4.4 shows that 10 (16.67%) of the respondents are architects, same for quantity surveyors, builders and others except Engineer which is 20 (33.33%) of the respondents which possess the largest population of the respondents because they include; Structural, Service Engineers e.t.c Table 4.2.4 Respondent Highest Academic Qualification

| Academic Qualification | Frequency | Percentage |
| --- | --- | --- |
| OND | 5 | 8.33 |
| HND | 36 | 60 |
| B.Sc | 16 | 26.67 |
| M.Sc | 2 | 3.33 |
| PhD | 1 | 1.67 |
| TOTAL | 60 | 100 |

Source: Field Survey, 2025

From the above table, 60% (36) of the respondents are HND holder, the population is how ever the largest in this context, while 8.33%(5) of the respondents are OND holders, 26,67%(16) of the respondents are B.Sc degree holders, M.Sc holder are 3.33%(2) of the respondents, while 1.67% (1) of the respondent is a PhD holder.

## Table 4.2.5: Respondent Professional Qualification

| Professional Qualification | Frequency | Percentage (%) |
| --- | --- | --- |
| MNIA | 10 | 16.67 |
| MNIQS/ANIQS | 10 | 16.67 |
| MNIOB/ANIOB | 10 | 16.67 |
| MNSE | 20 | 33.33 |
| Others | 10 | 16.67 |
| TOTAL | 60 | 100 |

Source: Field Survey, 2025

Table 4.6 shows the professional qualification of the respondents as a member of various professional bodies ranging from Member Nigeria Institute of Architects, Member Nigeria Institute of Quantity Surveyors, Member Nigeria Institute of Building, and Member Nigeria Society of Engineers having the highest percentage of respondents.

## Table 4.2.6: Type of  Project Handled by Respondents

| Type of project handled | Frequency | Percentage (%) |
| --- | --- | --- |
| Residential Building | 38 | 63.33 |
| Corporate building | 10 | 16.67 |
| Petro chemical plants | 02 | 3.37 |
| Civil Engineering works | 07 | 11.67 |
| Others (Industrial, Religious, foundations) | 03 | 5 |
| TOTAL | 60 | 100 |

Source: Field Survey, 2025

From table 4.7 largest percentages of the respondent 63.33% (38) had actually handled residential building to a large extent, more so, on corporate building. This can be interpreted that these professionals was in the know and use of construction management techniques. Petro-chemical was not all that handled by these professional as evident from the survey carried out.

## Table4.2.7: Assessment of Construction Management Technique in the Nigeria Construction Industry.

| Construction Management Techniques | RANKING |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | 5 | 4 | 3 | 2 | 1 |
| Materials Management | 12 | 28 | 15 | 3 | 2 |
| Human Resource Management | 9 | 18 | 30 | 3 | - |
| Cost Control and Management | 30 | 16 | 12 | 2 | - |
| Construction Site Control/Quality Management | 32 | 15 | 11 | 2 | - |
| Project planning and Scheduling | 37 | 20 | 2 | - | 1 |
| Time Management | 22 | 18 | 16 | 3 | 1 |
| Safety Management | 23 | 15 | 20 | 2 | - |
| Contract Administration | 21 | 15 | 19 | 3 | 2 |
| Resources Management | 30 | 18 | 10 | - | 2 |
| Equipment and Machine Management | 29 | 22 | 8 | 1 | - |
| Project Scope Management | 33 | 11 | 13 | 2 | 1 |
| Risk Management | 9 | 19 | 29 | 2 | 1 |
| Project Procurement Management | 31 | 16 | 10 | 2 | 1 |
| Professional Management | 26 | 14 | 16 | 3 | 1 |

Source: Field Survey, 2025

Table 4.8 involved the assessment of construction management techniques in the Nigeria Construction Industry where the highest number of respondents for material management is 28 under rank scale of 4 and the lowest is 2 under “very low” ranking scale. Under Human Resources Management, 30 respondents is on 3 ( moderate) ranking scale which tends to be the highest in that scale and the lowest is 3 respondents under the ranking scale of “very low”. The highest under Cost Control and Management is 30 respondents and the lowest is 2 respondents. Under Construction Site Control/ Quality Management, no fewer than 32 respondents constituting the highest number in the ranking scale of 5 gave their view on the subject and the lowest in that context is 1 respondent under the ranking scale of 1.37 respondents shows their awareness and assesses their use on project planning and scheduling as construction management techniques, these means that the highest number of respondents make use of project planning and scheduling techniques in their project execution. Time Management, Safety Management, Contract Administration, Resources Management, Equipment and Machine Management, Project Scope Management has the highest ranking scale of 5 for 22, 23, 21, 30, 29 and 33 respectively. These shows that good number of the respondents makes use of these constructions management techniques very well.

## Table 4.2.8: Impact of Construction Management Tech. on Construction Cost, Time and Quality

| CONSTRUCTION MANAGEMENT TECHNIQUES | COST |  |  |  |  | TIME |  |  |  |  | QUALITY |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 5 | 4 | 3 | 2 | 1 | 5 | 4 | 3 | 2 | 1 | 5 | 4 | 3 | 2 | 1 |
| Materials Management | 30 | 18 | 12 | - | - | 29 | 20 | 11 | - | - | 32 | 11 | 14 | 3 | - |
| Human Resource Management | 35 | 10 | 13 | 2 | - | 31 | 18 | 8 | 2 | 1 | 40 | 20 | - | - | - |
| Cost Control and Management | 28 | 13 | 12 | 5 | 2 | 26 | 15 | 10 | 7 | 2 | 36 | 18 | 5 | - | 2 |
| Construction Site Control/ Quality Management | 40 | 10 | 7 | 3 | - | 29 | 18 | 10 | 2 | 1 | 41 | 9 | 7 | 3 | - |
| Project planning and Scheduling | 34 | 17 | 9 | - | - | 38 | 11 | 11 | - | - | 30 | 18 | 10 | - | 2 |
| Time Management | 36 | 20 | 2 | 1 | 1 | 40 | 12 | 6 | 1 | 1 | 33 | 15 | 10 | 1 | 1 |
| Safety Management | 25 | 22 | 12 | 1 | - | 27 | 20 | 9 | 3 | 1 | 31 | 12 | 8 | 5 | 4 |
| Contract Administration | 31 | 20 | 8 | - | 1 | 22 | 30 | 8 | - | - | 19 | 18 | 20 | 1 | 2 |
| Resources Management | 19 | 32 | 5 | 1 | 3 | 27 | 21 | 8 | 3 | 1 | 29 | 18 | 10 | 2 | 1 |
| Equipment and Machine Management | 29 | 18 | 8 | 4 | 1 | 25 | 23 | 10 | 1 | 1 | 35 | 10 | 13 | 2 | - |
| Project Scope Mgt. | 40 | 11 | 4 | 3 | 2 | 30 | 13 | 12 | 5 | - | 40 | 10 | 7 | 3 | - |
| Risk Management | 26 | 23 | 8 | 4 | 2 | 18 | 19 | 20 | 2 | 1 | 22 | 23 | 12 | 2 | 1 |
| Project Procurement Management | 29 | 18 | 8 | 4 | 1 | 24 | 21 | 10 | 3 | 2 | 38 | 16 | 6 | - | - |
| Professional Management | 30 | 28 | 2 | - | - | 32 | 18 | 7 | 1 | 2 | 36 | 20 | 3 | 1 | - |

Source: Field Survey, 2025

From the above analysis, It was obvious that the construction Management Techniques in the Nigeria Construction Industry had a strong impact on Cost, Time and Quality since fewer respondents with highest number of 4 ticked low and very low, while the largest percentage of the respondents (almost 56) identified and showed that these techniques had a strong impact on cost, time and quality. The project planning and scheduling that shows the project activities against the time estimates reveals that construction management technique had a very solid impact on time factor.

## Table 4.2.9: Factors Affecting Construction Management Techniques in The Nigeria Construction Industry.

| FACTORS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | 5 | 4 | 3 | 2 | 1 |
| Size of the Project | 28 | 21 | 10 | - | 1 |
| Location of the project | 15 | 29 | 7 | 5 | 4 |
| Type of Client | 17 | 6 | 12 | 18 | 7 |
| Source of Finance | 30 | 18 | 10 | 1 | 1 |
| Complexity of the Project | 32 | 15 | 10 | 2 | 1 |
| Vitality of the Material | 28 | 26 | 16 | - | - |
| Poor Planning | 35 | 15 | 9 | 1 | - |
| Accessibility of the project | 12 | 18 | 27 | 3 | - |
| Material Shortage | 26 | 28 | 11 | 4 | 1 |
| Theft or Poor Security | 10 | 11 | 36 | 2 | 1 |
| Quality of Materials | 23 | 12 | 15 | 8 | 2 |
| Cost Of Transportation | 12 | 21 | 17 | 7 | 3 |
| Cost of Storage | 19 | 15 | 10 | 11 | 3 |

Source: Field Survey, 2025

From table 4.10 above, it can be concluded that all the factors listed are those that have adverse effects on the construction management techniques in the Nigeria construction Industry, except fewer factors like location of the project, type of client, accessibility of the project, theft or poor security, cost of transportation and cost of storage that are not all that affecting construction management techniques according to the survey result.

CHAPTER FIVE

SUMMARY, CONCLUSION AND RECOMMENDATION

5.1	SUMMARY

Construction Management has been identified to be an important area that requires much concentration as efficient management of construction project has an adverse effect on the construction performance and productivity. More so, for effective realization of a good value for money and constructing buildings that are cost effective, viable and feasible enough, various construction management techniques needed to be employed as evident from the result of the study carried out to various professionals in the construction field. From the study, it was obvious that the use of construction management techniques is vital as it improves individual and the construction industry especially in the study area. In the previous chapters it was established that construction projects have a specific set of objectives and constraints such as a required time frame for completion. While the relevant technology, institutional arrangements or processes will differ, the management of such projects has much in common with the management of similar types of projects in other specialty or technology domains such as aerospace, pharmaceutical and energy developments. Construction Project Management in compliance chapters one and two of this study is the art of directing and coordinating human and material resources throughout the life of a project by using modern management techniques to achieve predetermined objectives of scope, cost, time, and quality and participation satisfaction.

Project management in construction encompasses a set of objectives which may be accomplished by implementing a series of operations subject to resource constraints. There are potential conflicts between the stated objectives with regard to scope, cost, time and quality, and the constraints imposed on human material and financial resources. These conflicts should be resolved at the onset of a project by making the necessary tradeoffs or creating new alternatives. The Construction Project Management Institute focuses on nine distinct areas requiring construction project manager knowledge and attention:

- Construction Project integration management to ensure that the various project elements are effectively coordinated.

- Construction Projects cope management to ensure that all the work required (and only the required work) is included.

- Construction Project time management to provide an effective project schedule.

- Construction Project cost management to identify needed resources and maintain budget control.

- Construction Project quality management to ensure functional requirements are met.

- Construction Project human resource management to development and effectively employ project personnel.

- Construction Project communications management to ensure effective internal and external communications.

- Construction Project risk management to analyze and mitigate potential risks.

- Construction Project Procurement Management to obtain necessary resources from external sources. Construction planning is a fundamental and challenging activity in the management and execution of construction projects. It involves the choice of technology, the definition of work tasks, the estimation of the required resources and durations for individual tasks, and the identification of any interactions among the different work tasks. A good construction plan is the basis for developing the budget and the schedule for work.

# 5.2	CONCLUSION

Base on the results of the study carried out, Construction management technique is in no doubt a must use for every professionals in the construction industry.

The construction management techniques however used as evident from the respondent professionals in the construction field include Gantt chart, Programme Evaluation and Review Technique ( PERT), Critical Path Method ( CPM), Line of Balance, Work Breakdown Structure, PRINCE 2 , Network Analysis, Graphical Evaluation and Review Technique (GERT), Project Sensitivity Analysis, Cost Benefit Analysis and lot of others and factors such as Size of the project, Location of the project, Type of Client Source of finance , Complexity of the project, Vitality of the materials, Poor planning, Materials storage, Cost of transportation and storage and so on constitute the factors affecting construction Management Techniques in the Nigeria Construction Industry.

It is however concluded that the functions of construction project management for construction generally include the following:

- Specification of project objectives and plans including delineation of scope, budgeting, scheduling, setting performance requirements, and selecting project participants.

- Maximization of efficient resource utilization through procurement of labor, materials and equipment according to the prescribed schedule and plan.

- Implementation of various operations through proper coordination and control of planning, design, estimating, contracting and construction in the entire process.

- Development of effective communications and mechanisms for resolving conflicts among the various participants.

Construction Management Technique in the Nigeria construction industry had a strong impact on Human Resources Management, materials management, Cost control and Management, Construction Site Control/Quality management, Project planning and Scheduling, time management, SAFETY Management, Contract administration, Resources Management, Equipment and Machine Management, Project Scope Management, Risk Management, Project Procurement Management and Professional management base on the result form the findings.

5.3	RECOMMENDATION

Base on the findings from this research, the corresponding results and the summary above, the following recommendation is given to the professionals in the Nigerian Construction Industries as regards the effective use and implementation of construction professionals.

    - Construction Professionals should Endeavour to make use of the construction management techniques like Critical Path Method, Programme Evaluation and Review Technique (PERT), Work Breakdown Structure, Network Analysis and soon to allow them maximize their potentials to the fullest

    - They should engage in extensive training of some if not all of these techniques and also ensure that they are proficient in their use.

    - Construction professional should reduce the normal paper work that they have been adopting all the while to the adoption of construction management techniques so as to enhance faster, safer and economical construction.

    - Adequateplanningshouldbeputforwardtoreducewasteandunforeseenconditions

    - Quality materials should be used and ensured during construction process in other to increase the reliability spirit on the professionals.

    - Cost of transportation and storage should be checkmated to reduce the problem of material procurement and delivery.

    - The size of the project should be verified in other to determine the best construction technique to be used.

    - More access to finance should be sourced for at regular interval to reduce the problem of insolvency which leads to abandonment.

REFERENCES

Abbasi,Y.G & AlMharmah (2000)‘Project MANAGEMENT Practice by the public sector in a developing country’ International Journal of Project Management,18(3), pp 105-109

Adedeji A.O (1989): Inflation of production planning techniques on the performance of Construction firms in Nigeria. Journal of the federation of Building Contractor in Nigeria. 13 (1), 3-24

Akpan E.O.P and Chizea E.F, (2002); Project Management Theory and Practice. FUTO Press Ltd, Owerri- Nigeria.

Arnabodi M., Azzone G., & Savoldelhi A. (2004) ‘managing public sector project: the case of the Italian Treasury Ministry’ International Journal of ProjectManagenent,22(3),pp 213-223.

Idoro, G.I & Patunola – Ajayi J.B. (2009) ‘Evaluating the strategies for marketing project Management system in the Nigerian Construction Industry’. Nordic Journal of Surveying and Real Estate Research, 6 (2). Pp 25-36

Lewis, J.P. (2007), ‘Fundamentals of Project Management’, 3rd ed, New York: AMACOM Muller, R& Turner, R. (2007)‘MatchingtheProject manager’sleadershipstyletoproject type’.

International Journzala of Project M,anagement, 25(4), pp. 21-32, DOI: 10.1016/j.ijproman.2006.04.003, Science Direct Database, [Online]. Available from: http://www.sciencedirect.com.ezproxy.liv.ac.uk/Insight/viewPDF.ijproman?(Accessed:1

September, 2010)

Nwachukwu C.C, Echeme, I.I and Okoli, M.N (2010) “Project Management Factor Indexes; A Constraint to Project Implementation Success in the Construction Sector of a developing Economy”EuropeanJournalofScientificResearch’JulyeditionISSN1450–216X Vol. 43. No. 3, pp 392 – 405 United Kingdom.

OparaN.(1986):ConstructionManagemntControlandPlanning.ConstructionEconomics, 12- 15

Patel, B.M (2008) ‘Project Management: Strategic financial planning, evaluation and control’.

New Delhi, Vikas Publishing House PV TLtd.

Pinto, J.K (2007) Project Management: Achieving competitive Advantage, Upper Sddle River, NJ; Pearson Education.

Stukenbrucj L.C and Zomorrodian, A (1987) ‘Project Management: the promise for developing countries’ Project Management, 5 (3), pp. 167-175

Westland A. (2003) ‘Project Management Life cycle’, London, Kogan Rage Limited. White, D&Fortune, J (2002) ‘Current practice in project management–an empirical study’

International Journal of Project Management,20(6).Pp.1-11.

Wysocki, R.K (2009) ‘Effective Project Management’: traditional, agile extreme, 5thed, Indianapolis, IN: Wiley Publishing.