KWARA STATE POLYTECHNIC

CHALLENGES OF COST MANAGEMENT FOR INFRASTRUCTURE DEVELOPMENT IN KWARA STATE

By

OLAITAN ABDULWAHAB OLUWADAMILARE

HND/23/FT/QTS/0064

A FINAL-YEAR PROJECT SUBMITTED TO QUANTITY SURVEYING DEPARTMENT

IN PARTIAL FULFILLMENT OF THE REQUIREMENT FOR THE AWARD OF HIGHER NATIONAL DIPLOMA (HND) IN QUANTITY SURVEYING.

JULY2025

# DEDICATION

This project is dedicated to the Almighty Allah, the Most Gracious, the Most Merciful, for granting me life, strength, wisdom, and the opportunity to complete this academic journey.

To my beloved parents and guardians, whose prayers, love, and unwavering support have been my greatest source of motivation thank you for believing in me even when the road was tough.

To my siblings and family members, thank you for your encouragement and kind words throughout this journey.

I also dedicate this work to all the lecturers and mentors who guided me with their knowledge and wisdom, and to my colleagues and friends whose companionship and collaboration made the process more meaningful.

Finally, this work is dedicated to every student who dares to dream, perseveres through challenges, and strives for excellence in the pursuit of knowledge.

# DECLARATION

I hereby declare that this Research work, which I submit to the Department of Quantity Surveying, Institute of environmental studies, Kwara state polytechnic, Ilorin, Kwara state, Nigeria, examination in consideration of the award of a Higher National Diplomain Quantity Surveying in an original work undertaken by me Olaitan Abdulwahab Oluwadamilare.

---------------------------------------------------					---------------------------

Olaitan Abdulwahab Oluwadamilare								DATE

(HND/23/FT/QTS/0062)

# ACKNOWLEDGEMENTS

First and foremost, I express my deepest gratitude to Almighty Allah, the source of my strength, knowledge, and perseverance, for granting me the wisdom and ability to successfully complete this research work.

My sincere appreciation goes to my project supervisor Q.S Ashia Omar Muazu, whose invaluable guidance, constructive feedback, and constant encouragement contributed significantly to the quality and completion of this study. Your support and academic mentorship have been instrumental throughout this journey.

I extend my heartfelt thanks to the Head of Department, academic staff, and management of the Department of Quantity Surveying, Kwara State Polytechnic, Ilorin, for providing a conducive learning environment and access to relevant resources.

Special thanks to all the respondents and professionals in the construction industry who took the time to participate in the survey and share their experiences. Your input was vital to the success of this research.

To my beloved family, thank you for your unwavering love, prayers, and emotional support. Your belief in my potential kept me going even in the most challenging moments. I am especially grateful to my wife and daughter for their patience, love, and understanding during the many late nights and long days dedicated to this project.

To my friends and colleagues, thank you for the shared experiences, moral support, and constant encouragement that helped me stay focused and determined.

Lastly, I acknowledge everyone who contributed in one way or another to the successful completion of this project. May Allah reward you all abundantly.

# TABLE OF CONTENTS

CERTIFICATION	2

DEDICATION	3

DECLARATION	4

ACKNOWLEDGEMENTS	5

TABLE OF CONTENTS	6

ABSTRACT	9

CHAPTER ONE	10

INTRODUCTION	10

1.1	BACKGROUND TO THE STUDY	10

1.2 STATEMENT OF RESEARCH PROBLEM	11

1.2	RESEARCH QUESTIONS	12

1.4 AIM AND OBJECTIVES	13

1.4.1 Aim	13

1.4.1	Objectives of the Study	13

1.5 SCOPE AND LIMITATION	13

1.5.1 Scope of the Study	13

1.5.2 Limitations of the Study	14

1.6 JUSTIFICATION FOR THE STUDY	15

1.7	DEFINATION OF TERMS	16

CHAPTER TWO	19

LITERATURE REVIEW	19

2.1 Infrastructure Development in Construction Industry	19

2.2 Concept of Cost Management in Infrastructure Projects	20

2.2.1 Key Concepts and Practices in Cost Management	Error! Bookmark not defined.

2.3 Importance of Cost Management in Infrastructure Development	21

2.4 Challenges of Cost Management in Infrastructure Development	21

2.5 Challenges of Cost Management in Developing Economies	Error! Bookmark not defined.

2.6 Specific Cost Management Challenges in Kwara State	23

2.7 Impact of Cost Management Challenges on Project Delivery	25

2.8. Strategies for Improving Cost Management	26

2.9 Summary of Literature Review	28

CHAPTER THREE	30

RESEARCH METHODOLOGY	30

3.1 A brief outline of the chapter	30

3.2 Research design	30

3.3 Population of the Study	31

3.4 Sample Size and Sampling Technique	32

3.5 Method of Data Collection	32

3.7 Method of Data Analysis	32

3.8 Validity and Reliability of Instrument	32

3.9 Ethical Considerations	32

CHAPTER FOUR	33

DATA ANALYSIS, RESULTS AND DISCUSSIONS	33

4.1 A brief introduction to the chapter	33

4.2 Response Rate	33

4.3 Characteristics of Respondents	34

4.3.1 Professional Background	34

4.3.2 Years of Experience	35

4.3.3 Sector of Employment	36

4.3.4 Summary	36

4.4 Presentation and analysis of data according to research questions	37

4.4.1 Major challenges of cost management in infrastructure development projects in Kwara State	37

4.4.2 Impact of Cost Management Challenges on Project Delivery	38

4.4.3 Effectiveness of Current Cost Management Practices	39

4.5 Discussion of Findings	41

4.6 Summary of Chapter Four	43

CHAPTER FIVE	45

SUMMARY, CONCLUSION AND RECOMMENDATION	45

5.1 Summary of the Findings	45

5.2 Conclusion	46

5.3 Recommendations	47

5.3.1	Strengthen Budget Planning and Allocation	47

5.3.2	Ensure Timely Release of Funds	47

5.3.3	Adopt Value Management Techniques	48

5.3.4	Enhance Planning and Scope Definition	48

5.3.5	Strengthen Cost Monitoring and Auditing Systems	48

5.3.6	Promote Stakeholder Engagement	49

5.3.7	Professional Development and Capacity Building	49

5.4 Suggestions for Further Research	49

5.4.1 Comparative Studies Between Different Nigerian States	49

5.4.2 In-Depth Investigation into the Role of Corruption and Political Influence	50

5.4.3 Exploration of Digital Technologies in Cost Control	50

5.4.4 Case Studies of Successfully Delivered Infrastructure Projects	50

5.4.5 Evaluation of the Role of Quantity Surveyors and Cost Professionals	51

5.4.6 Investigation into Community Participation and Stakeholder Engagement	51

APPENDICES	52

REFERENCES	56

# ABSTRACT

Effective cost management remains a critical factor in the successful delivery of infrastructure projects, particularly in developing regions such as Kwara State, Nigeria. This study investigates the key challenges affecting cost management in infrastructure development within the state. It explores the root causes of cost overruns, budget shortfalls, and inefficiencies that commonly hinder project execution and financial sustainability.

The research focuses on public and privately driven infrastructure projects, including roads, bridges, schools, hospitals, and other essential facilities. Through the administration of structured questionnaires and interviews with stakeholders such as contractors, consultants, government officials, and project managers, relevant data were collected and analyzed using descriptive statistical methods.

Findings from the study reveal that poor project planning, irregular funding, weak regulatory oversight, inflation, and lack of technical expertise are among the major contributors to ineffective cost management. Additionally, issues related to data availability, political interference, and economic instability further exacerbate the situation.

The study concludes that addressing these challenges requires a combination of improved planning processes, transparent procurement systems, timely fund disbursement, professional capacity building, and stronger institutional frameworks. By identifying and analyzing these barriers, the research provides actionable insights that can guide policymakers, construction professionals, and development stakeholders in enhancing cost control mechanisms for infrastructure development in Kwara State and similar contexts.

# CHAPTER ONE

# INTRODUCTION

## BACKGROUND TO THE STUDY

Infrastructure development is a cornerstone of economic growth and societal advancement, providing the essential facilities and services that support daily life and economic activities (Anood. A 2014). In Kwara State, Nigeria, effective cost management in infrastructure projects is crucial to ensure the optimal use of limited resources and the successful completion of development initiatives (Amuda-Yusuf, G., et al2017). However, the state faces significant challenges in this regard, leading to project delays, cost overruns, and, in some cases, project abandonment.

The complexities of cost management in infrastructure development are influenced by various factors, including inadequate planning, funding constraints, bureaucratic delays, and corruption (Akorli, K.S. 2017). These challenges not only inflate project costs but also impede the timely delivery of essential infrastructure, thereby affecting the socio-economic development of the region. Understanding and addressing these challenges are imperative for improving infrastructure delivery and fostering sustainable development in Kwara State.

Kwara State, located in the North-Central region of Nigeria, has been striving to enhance its infrastructure to meet the growing needs of its population and stimulate economic growth. Despite these efforts, the state encounters numerous obstacles in managing the costs associated with infrastructure projects (Taghipour M. 2015).

A study focusing on infrastructure projects in Kwara State identified critical risk factors affecting project delivery, including government policy instability, economic fluctuations, and social risks These external factors exacerbate the challenges of cost management, leading to budget overruns and project delays (Hemesy M. 2019).

Additionally, the lack of technical expertise and inadequate stakeholder engagement further complicate cost management efforts.A case study on infrastructure projects in Nigeria highlighted significant barriers such as funding constraints, bureaucratic delays, and corruption, which are prevalent issues in Kwara State as well.These challenges result in inefficient resource allocation and increased project costs (Adu E. 2015).

Moreover, the absence of integrated cost management solutions has been identified as a key factor contributing to the unsustainable delivery of infrastructure projects (Adu E. 2015).The Nigerian Institute of Quantity Surveyors emphasizes the need for comprehensive cost management strategies to address these challenges and ensure the successful execution of infrastructure projects

Therefore, the challenges of cost management in infrastructure development within Kwara State are multifaceted, involving external risks, internal inefficiencies, and systemic issues (Hemesy M. 2019).Addressing these challenges requires a holistic approach that encompasses effective planning, stakeholder engagement, and the implementation of integrated cost management solutions to achieve sustainable infrastructure development (El-Sayegh SM. 2018)

## 1.2 STATEMENT OF RESEARCH PROBLEM

Infrastructure development is a critical driver of socio-economic progress, yet it often faces numerous challenges, particularly in resource-constrained environments such as Kwara State, Nigeria (Emuze F, Kadangwe S. 2014). One of the most significant challenges is effective cost management, which is essential for the timely and successful delivery of infrastructure projects. However, persistent issues such as cost overruns, delays, and inefficient resource allocation hinder the realization of these goals (Fadun, O. S., and Saka, S. T. 2018).

In Kwara State, the problem is exacerbated by factors such as inadequate project planning, funding constraints, inflation, and weak regulatory oversight. Studies have shown that these challenges often result in increased project costs, delayed completion, and, in extreme cases, project abandonment (Rameezdeen R. 2017). For example, infrastructure projects in Nigeria have been reported to suffer from poor cost control mechanisms, leading to financial losses and reduced public trust in government-led initiatives.

The lack of technical expertise and modern cost management practices further compounds the issue. Many project stakeholders lack access to advanced tools and methodologies for budgeting, cost monitoring, and risk management (Ghada Badawi, Nawawy 2016). Additionally, external factors such as economic instability and fluctuating exchange rates significantly impact project costs, making effective cost management even more challenging (Ghada Badawi, Nawawy2016).

Despite the critical nature of this issue, there is limited research focusing on the unique cost management challenges faced in Kwara State. Existing studies tend to generalize the problem across Nigeria, without addressing the specific socio-economic and political factors influencing cost management in the state (Fadun, O. S., and Saka, S. T. 2018). This gap in knowledge makes it difficult to develop targeted solutions that cater to the unique needs of Kwara State.

This research seeks to address this gap by investigating the specific challenges of cost management in infrastructure development in Kwara State. The study aims to identify the root causes of these challenges and provide actionable recommendations for improving cost management practices, ensuring more efficient and sustainable infrastructure delivery in the state.

## RESEARCH QUESTIONS

- What is the importance of cost management in infrastructure development?

- What are the primary challenges associated with cost management in infrastructure development projects in Kwara State?

- What is the impact of cost management challenges on the timely and cost-effective delivery of infrastructure projects?

- What arethe strategies for improving the current cost management practices employed in infrastructure projects within the state?

## 1.4 AIM AND OBJECTIVES

### 1.4.1 Aim

The aim of this study is to examine the challenges of cost management for infrastructure development in Kwara State, with a view to identifying the root causes, evaluating their impacts on project delivery, and proposing strategies for improved cost management practices.

### Objectives of the Study

- To identify the importance of cost management in infrastructure development?

- To identify the primary challenges associated with cost management in infrastructure development projects in Kwara State.

- To evaluate the impact of cost management challenges on the timely and cost-effective delivery of infrastructure projects.

- To assess the strategies for improving the current cost management practices employed in infrastructure projects within the state.

## 1.5 SCOPE AND LIMITATION

### 1.5.1 Scope of the Study

This study is centered on exploring the challenges associated with cost management in infrastructure development within Kwara State, Nigeria. The research critically examines the key factors responsible for cost-related issues in infrastructure projects, including inadequate project planning, limited funding, regulatory bottlenecks, and external economic pressures. These factors are consistent with findings from existing literature, particularly the work of Fadun and Saka (2018), which highlights similar cost management challenges in the Nigerian construction sector.

The study specifically focuses on infrastructure projects such as roads, bridges, schools, hospitals, and other public utilities, executed by both government agencies and private sector stakeholders within the state. By narrowing the research scope to these types of projects, the study aims to provide a focused and practical analysis of cost management practices and the institutional, economic, and technical factors affecting them. Through this approach, the study seeks to generate insights that can inform more effective project planning, cost control strategies, and policy development for infrastructure delivery in Kwara State.

### 1.5.2 Limitations of the Study

While the study offers valuable insights into the cost management challenges in Kwara State, it is subject to several limitations that should be acknowledged.

Firstly, the research isgeographically limited to Kwara State. As such, it may not fully reflect or represent the cost management realities of other states or regions in Nigeria, which may differ significantly due to variations in governance structures, economic conditions, and institutional frameworks.

Secondly, there are potential constraints in accessing reliable and current data. Infrastructure project records, particularly in the public sector, may be incomplete, outdated, or unavailable due to bureaucratic inefficiencies, lack of transparency, or poor documentation practices. This could limit the scope of data analysis and the accuracy of the study’s conclusions.

The study also relies on the participation of key stakeholders, including contractors, government officials, consultants, and project managers. The accuracy and richness of the data collected are heavily dependent on their willingness to respond to surveys and interviews. Limited engagement or response bias from these groups could affect the comprehensiveness and reliability of the findings.

Another limitation stems from the time constraints associated with the research. The limited duration available for fieldwork, data collection, and analysis may restrict the ability to conduct in-depth studies on large-scale or long-term projects, especially those with evolving cost dynamics.

In addition, the study is conducted in a context of economic volatility, characterized by rising inflation, fluctuating foreign exchange rates, and political uncertainty. These external factors can significantly influence infrastructure costs and may vary during the research period, potentially affecting the consistency and general applicability of the findings.

Finally, although the research aims to provide practical recommendations, the generalizability of its outcomes is limited. The unique socio-economic and political context of Kwara State means that the findings may not be directly transferable to other Nigerian states or regions facing different realities in terms of resources, policies, or construction industry structures.

Despite these limitations, this study makes a meaningful contribution by highlighting key cost management issues in infrastructure development and proposing actionable strategies to mitigate them within the context of Kwara State.

## 1.6 JUSTIFICATION FOR THE STUDY

Effective cost management is a cornerstone of successful infrastructure development, ensuring that projects are delivered within budget, on time, and to the desired quality standards (Lawal A, Elkanah A. 2015). In Kwara State, Nigeria, the challenges associated with cost management have led to frequent project delays, cost overruns, and, in some cases, project abandonment (Idris, S. Awodele, A.O. & Amuda-Yusuf, G 2019). These issues have significant implications for the socio-economic development of the state, as they hinder the delivery of critical infrastructure needed to support economic growth and improve the quality of life for residents.This study is justified for several reasons:

Addressing Socio-Economic Development Needs:Infrastructure development plays a vital role in boosting economic activities, creating employment opportunities, and enhancing the quality of life. By investigating the challenges of cost management, this study aims to contribute to the efficient allocation of resources, thereby enabling timely and cost-effective project delivery that supports Kwara State’s development goals.

Bridging Knowledge Gaps:While existing research on infrastructure development in Nigeria has identified cost management as a critical issue, few studies focus specifically on the unique socio-economic and political challenges faced in Kwara State. This research seeks to fill this gap by providing a detailed analysis of the local context and proposing tailored solutions.

Practical Implications for Stakeholders:The findings of this study will be valuable to key stakeholders, including government agencies, contractors, project managers, and quantity surveyors. By identifying the root causes of cost management challenges and recommending actionable strategies, the study will help stakeholders implement effective practices that minimize waste and enhance project efficiency.

Policy Development and Implementation:This research has the potential to inform policy decisions related to infrastructure planning, funding, and regulation. The insights generated can guide policymakers in designing frameworks that address cost management challenges and foster sustainable development.

Contributing to the Body of Knowledge:The study will contribute to academic literature on cost management in infrastructure development, providing a reference for future research in Kwara State and beyond.

Promoting Accountability and Transparency:By highlighting issues such as funding constraints, corruption, and inefficiencies, this study can encourage greater accountability and transparency in the planning and execution of infrastructure projects in the state.

In conclusion, this study is essential for addressing the persistent challenges of cost management in Kwara State, with the potential to drive improvements in infrastructure delivery and contribute to the broader development agenda.

## DEFINATION OF TERMS

    - Cost Management:
Cost management refers to the process of planning, estimating, budgeting, monitoring, and controlling costs to ensure that a project is completed within the approved budget. It encompasses techniques and tools for forecasting and managing expenditures to achieve financial efficiency in project delivery.

    - Infrastructure Development:
Infrastructure development involves the construction, maintenance, and improvement of foundational physical and organizational structures, such as roads, bridges, schools, hospitals, water supply systems, and energy facilities, that are necessary for the functioning of a society and economy.

    - Challenges:
Challenges refer to obstacles, difficulties, or issues that hinder the efficient and effective execution of processes, such as financial constraints, regulatory hurdles, lack of skilled personnel, and economic fluctuations in cost management for infrastructure projects.

    - Project Planning:
Project planning is the process of defining the objectives, scope, timelines, and resources required for a project. It involves creating detailed schedules, budgets, and risk management plans to ensure the successful execution of infrastructure development.

    - Cost Overrun:
Cost overrun occurs when the actual expenses of a project exceed the original budget estimate due to factors such as poor planning, unexpected delays, or unforeseen economic changes.

    - Funding Constraints:
Funding constraints refer to the limitations or inadequacies in the financial resources available for completing a project. These constraints can lead to delays, reduced scope, or incomplete infrastructure projects.

    - Stakeholders:
Stakeholders are individuals, groups, or organizations with an interest in the outcome of a project. In the context of infrastructure development, stakeholders include government agencies, contractors, consultants, project managers, and the community at large.

    - Economic Volatility:
Economic volatility refers to unpredictable and rapid changes in economic factors, such as inflation, exchange rates, and interest rates, which can significantly impact the costs of infrastructure projects.

    - Kwara State:
Kwara State is one of the 36 states in Nigeria, located in the North-Central geopolitical zone. It serves as the geographical focus of this research, with its unique socio-economic, cultural, and political environment influencing infrastructure development.

    - Sustainable Development:
Sustainable development refers to the development of infrastructure and other resources in a manner that meets present needs without compromising the ability of future generations to meet their own needs. This involves the efficient use of resources, environmental conservation, and long-term planning.

    - Corruption:
Corruption in the context of infrastructure development refers to unethical practices such as bribery, misappropriation of funds, and manipulation of contracts that undermine cost management and project efficiency.

    - Quantity Surveying:
Quantity surveying is a profession within the construction and infrastructure sectors that focuses on managing costs and contracts throughout the lifecycle of a project to ensure value for money and financial accountability.

# CHAPTER TWO

# LITERATURE REVIEW

## 2.1 Infrastructure Development in Construction Industry

Infrastructure development in Kwara State has evolved alongside Nigeria’s broader economic and political transitions since its creation in 1967. Initially, infrastructure expansion was primarily driven by federal government allocations and donor funding. The post-independence era witnessed significant investments in public utilities such as roads, schools, hospitals, and water supply systems, especially during the oil boom of the 1970s. However, these projects were often implemented without adequate cost control mechanisms, leading to inefficiencies and cost overruns (Amuda-Yusuf et al., 2017).

During the military regimes of the 1980s and 1990s, infrastructure development in the state experienced stagnation due to economic downturns, political instability, and corruption. Many projects were either abandoned or delivered with compromised quality as a result of inadequate budgetary provisions and poor financial management (Idris et al., 2019).

With the return to democratic governance in 1999, renewed efforts were made to improve infrastructure in the state. Successive administrations introduced capital development plans and strategic frameworks targeting transportation, education, and healthcare. However, these initiatives continued to face challenges related to cost estimation inaccuracies, funding gaps, and weak monitoring and evaluation systems (Fadun & Saka, 2018).

In recent years, the state government has increased its reliance on public-private partnerships (PPPs) and donor agency support to fund major infrastructure projects. Nonetheless, the effectiveness of cost management practices remains a critical issue. Delays in project execution, inflation-induced budget escalations, and contractor inefficiencies persist, reflecting a systemic weakness in cost control, procurement practices, and stakeholder coordination.

Efforts by professional bodies such as the Nigerian Institute of Quantity Surveyors (NIQS) to promote cost transparency and accountability in project delivery have not been fully integrated into government practices. This historical trend underscores the pressing need for comprehensive, locally-adapted cost management frameworks to support sustainable infrastructure development in Kwara State.

## 2.2 Concept of Cost Management in Infrastructure Projects

Cost management in infrastructure projects refers to the process of planning, estimating, budgeting, financing, funding, managing, and controlling project costs to ensure that the project is completed within the approved budget and scope (Project Management Institute, 2014). It encompasses a series of activities and tools aimed at ensuring cost efficiency and financial accountability throughout the project life cycle, from feasibility studies and design to construction and commissioning.

Effective cost management is essential to achieving project objectives and optimizing the allocation of limited resources, especially in resource-constrained settings like Kwara State. It involves setting cost baselines, conducting value engineering, performing cost-benefit analysis, and continuously monitoring expenditures against forecasts (Goh & Abdul-Rahman, 2013). According to Lawal and Elkanah (2015), well-implemented cost management practices help reduce the risk of cost overruns, prevent financial wastage, and support timely project delivery.

In infrastructure development, cost management plays a pivotal role not only in financial planning but also in ensuring the long-term sustainability of the project. Without proper cost control measures, projects may suffer from delays, scope creep, budget escalation, or even abandonment. For instance, Hemesy (2019) notes that many public sector infrastructure projects fail to achieve value for money due to poor cost estimation and ineffective financial oversight.

Additionally, cost management must adapt to dynamic external conditions such as inflation, exchange rate volatility, and material price fluctuations. These factors are particularly relevant in developing countries, where economic instability can significantly alter project costs after the initial planning stage (Fernando et al., 2017).

Therefore, a strategic approach to cost management in infrastructure projects requires a combination of technical tools, stakeholder engagement, transparent procurement practices, and regular financial audits to ensure that resources are efficiently used and project goals are met.

## 2.3 Importance of Cost Management in Infrastructure Development

Effective cost management plays a critical role in the successful delivery of infrastructure projects. One of its foremost benefits is ensuring project success, as staying within budget is vital for meeting financial feasibility and performance expectations. Projects that adhere to their cost plans are more likely to be completed on time and deliver intended outcomes (Sharma, 2020).

Another key benefit is resource efficiency. When costs are properly managed, resources are allocated wisely, and wastage is minimized, which enhances productivity and value delivery. Furthermore, comprehensive cost management aids in risk mitigation. By identifying financial risks early and maintaining cost control mechanisms, project teams can prevent budget overruns and avoidable delays (Wuni et al., 2020).

Additionally, cost transparency builds stakeholder confidence. Demonstrating that a project is financially disciplined reassures funders, government agencies, and the public that resources are being managed responsibly. This in turn boosts support and cooperation. Lastly, efficient cost management contributes to organizational profitability, as budget adherence ensures better margins and financial sustainability for contracting and consulting firms (Iqbal et al., 2015).

## 2.4 Challenges of Cost Management in Infrastructure Development

Despite its importance, several challenges continue to hinder effective cost management in infrastructure projects, especially in developing regions like Kwara State. One major challenge is uncertainty. Projects often face unpredictable conditions such as design modifications, fluctuating material prices, and unforeseen site complications, all of which can derail initial cost estimates (Hemesy, 2019).

Another persistent issue is Changes in project scope, client requirements, or environmental conditions change management. require adjustments in planning and budgeting. Without an established process to handle these changes, projects become vulnerable to cost escalations. Additionally, external factors such as inflation, currency fluctuations, labor unrest, and material shortages pose significant threats to cost stability (Fernando et al., 2017).

Furthermore, poor cost data, limited access to cost control technologies, lack of skilled personnel, and bureaucratic inefficiencies all contribute to the inability to maintain cost discipline. These challenges underscore the need for proactive cost planning, stakeholder collaboration, and the integration of modern cost management systems in infrastructure development.

A fundamental challenge is inadequate project planning. Many infrastructure projects in developing countries commence without thorough feasibility studies or cost-benefit analyses. As a result, there is often a disconnect between project scope and available financial resources. Mahamid (2013) noted that weak initial planning frequently leads to inaccurate cost estimates and unrealistic timelines, thereby increasing the likelihood of cost overruns and schedule delays.

Inflation and currency fluctuations also play a critical role in derailing cost management efforts. In economies with high inflation rates, the cost of construction materials, equipment, and labor can escalate rapidly during the execution phase, often outpacing the approved budget. Fernando et al. (2017) emphasized that foreign exchange volatility in countries like Nigeria makes it difficult to control costs, especially when materials are imported or when contracts are priced in foreign currencies.

Moreover, corruption and financial mismanagement significantly impede cost efficiency. In many developing nations, procurement irregularities, contract inflation, and diversion of public funds are rampant. According to Nouman et al. (2021), corruption is a systemic challenge that distorts cost estimation and compromises the integrity of project delivery. This leads to inflated costs, substandard work, and public distrust.

Another critical issue is poor coordination among stakeholders. Infrastructure projects typically involve multiple stakeholders, including government ministries, contractors, consultants, and financiers. In the absence of a collaborative framework, conflicting interests and lack of effective communication result in misalignment, rework, and cost duplication (Chileshe & Yirenkyi-Fianko, 2011). These challenges are often exacerbated by weak institutional capacity and unclear roles and responsibilities among stakeholders.

Lack of technical expertise and modern cost control tools further complicates cost management in developing economies. Many project personnel lack adequate training in project financial management, value engineering, and risk-based budgeting. Ghada Badawi and Nawawy (2016) highlighted that the limited use of cost forecasting software and lack of exposure to best practices hinder effective financial oversight.

In the Nigerian context, bureaucratic delays and regulatory inefficiencies present additional constraints. Approval processes for payments, project variations, and contract revisions are often slow and cumbersome, causing project delays and increasing administrative costs. Fadun and Saka (2018) identified weak monitoring systems and inconsistent regulatory enforcement as key contributors to poor cost control in Nigerian infrastructure projects.

In summary, the challenges of cost management in developing economies are multifaceted and systemic. Addressing them requires a combination of institutional reforms, capacity building, stakeholder engagement, and the adoption of modern project management tools. Without these interventions, cost inefficiencies will continue to undermine the delivery of critical infrastructure needed for development.

## 2.5Challenges Associated with Cost Management in Infrastructure Development Projects in Kwara State.

Kwara State, situated in the North-Central region of Nigeria, shares several cost management challenges common across developing economies but also faces unique socio-political and institutional constraints that complicate infrastructure project delivery. While the state government continues to prioritize capital investment in road networks, schools, healthcare facilities, and public utilities, the management of project costs remains a persistent problem.

One of the major challenges is inconsistent government policies and frequent administrative changes. Shifts in leadership or political priorities often result in the suspension, alteration, or reallocation of funds for ongoing projects. Amuda-Yusuf et al. (2017) noted that political instability in Nigerian states, including Kwara, frequently leads to disruptions in infrastructure planning and budgeting, thereby inflating costs and delaying implementation timelines.

Funding constraints are another dominant issue affecting cost management in Kwara State. Many infrastructure projects are underfunded from the onset, while others suffer from irregular disbursement of funds. This scenario creates gaps between budget approval and actual execution, often requiring re-budgeting and leading to cost escalations. According to El-Sayegh and Mansour (2015), underfunding is a major factor behind delays and abandonment of public projects in developing countries.

Closely linked to funding is the problem of delayed payments to contractors and consultants. When payments are not released on time, contractors are forced to slow down or halt work, leading to time overruns and increased overhead costs. This also affects the cash flow of contractors, who may respond by inflating costs to account for payment uncertainties (Idris et al., 2019).

Corruption and lack of transparency in the procurement and contract administration processes are also prevalent. Cases of contract inflation, favoritism in contractor selection, and misappropriation of public funds reduce the efficiency of cost control mechanisms. Nouman et al. (2021) highlighted that in many Nigerian states, including Kwara, corruption remains one of the leading causes of cost overruns and substandard project outcomes.

In addition, inadequate and unreliable data for cost estimation hampers accurate budgeting and forecasting. Project managers and quantity surveyors often work with outdated rates or incomplete information, resulting in inaccurate cost estimates. This problem is further compounded by poor record-keeping practices and lack of access to standardized costing databases (Ghada Badawi &Nawawy, 2016).

Lack of integration among key stakeholders presents another significant challenge. Infrastructure projects involve various actors such as government ministries, local councils, contractors, consultants, and community representatives. However, poor communication and coordination among these stakeholders often result in scope misalignment, duplicated efforts, and disputes, all of which increase project costs (Chileshe & Yirenkyi-Fianko, 2011).

Finally, weak contract management practices also contribute to cost inefficiencies. Contracts are often awarded without rigorous evaluation of contractor capacity or performance history. Moreover, change orders are poorly managed, and contract clauses related to cost variations are not properly enforced. These issues undermine accountability and lead to financial leakages (Fadun & Saka, 2018).

In conclusion, the cost management challenges in Kwara State are multifaceted and deeply rooted in governance, financial planning, and institutional capacity. Addressing these issues requires systemic reforms that emphasize transparency, timely funding, stakeholder engagement, and professional cost management practices.

## 2.6 Impact of Cost Management Challenges on Project Delivery

Cost management challenges have significant and often detrimental effects on the successful delivery of infrastructure projects. When financial control systems are weak or absent, projects experience a cascade of problems, including prolonged timelines, budget overruns, compromised construction quality, and, in extreme cases, total abandonment. These issues not only delay the realization of project benefits but also erode public trust in government and development agencies.

One of the most immediate and visible impacts of poor cost management is project delay. When costs exceed the initial estimates, additional time is required to source supplementary funds, renegotiate contracts, or revise project scopes. This causes disruptions to project schedules, especially when interim payments to contractors are delayed due to cash flow shortages or bureaucratic processes. According to Mahamid (2013), schedule delays often stem from inflation-induced cost escalations and funding gaps that result from inaccurate cost forecasting.

Budget overruns are another critical consequence. In many cases, projects begin without robust cost estimation or contingency planning, and as unforeseen circumstances arise—such as material price hikes or design changes—the approved budget becomes inadequate. Fernando et al. (2017) assert that contractors in developing countries frequently experience budget shortfalls due to a lack of early-stage cost analysis and inflation risks.

The quality of infrastructure is also compromised when projects face financial constraints. When costs spiral beyond control, contractors may resort to using substandard materials or reducing scope to stay within budget limits. This leads to poor-quality outputs that fail to meet performance standards, often requiring costly repairs or reconstructions. As observed by Ghada Badawi and Nawawy (2016), compromised project quality due to cost-related constraints is a common problem in infrastructure delivery in resource-scarce environments.

In more severe instances, project abandonment becomes inevitable. Once a project becomes financially unviable or politically unattractive due to excessive cost overruns or controversies, it is either suspended or terminated. Rameezdeen et al. (2017) noted that abandoned projects are not only financial losses but also represent lost opportunities for social and economic advancement, particularly in sectors like healthcare, education, and transportation.

Another far-reaching impact is the misallocation of scarce public resources. When projects exceed their budget, funds that could have been used for other development initiatives are diverted, creating opportunity costs. This often disrupts state-level budgeting cycles and limits the government’s ability to finance new projects. El-Sayegh (2018) emphasized that cost mismanagement leads to resource inefficiencies and reduces the overall return on investment in public infrastructure.

Furthermore, persistent cost management failures lead to a decline in public and investor confidence. Taxpayers, development partners, and private sector stakeholders are less likely to support future infrastructure initiatives if existing projects consistently fall short of cost and performance expectations. This lack of trust undermines collaboration, stifles innovation, and limits funding opportunities.

Finally, these challenges collectively hinder long-term development planning. Infrastructure is a cornerstone of economic growth, and its failure to meet planned targets stalls regional development goals. Without a reliable system for managing costs, future projects are likely to inherit the same inefficiencies, perpetuating a cycle of underperformance in the construction sector (Fadun & Saka, 2018).

## 2.7 Strategies for Improving Cost Management

Addressing the challenges of cost management in infrastructure projects requires a combination of strategic, technical, and institutional reforms. Numerous studies have proposed diverse strategies to enhance cost efficiency, especially in developing economies where project delivery is frequently threatened by inefficiencies, corruption, and capacity constraints.

One of the foremost strategies is improved project planning and cost forecasting. Accurate forecasting during the pre-construction phase helps in identifying potential cost drivers and allows for the incorporation of contingencies to manage uncertainties. According to Mahamid (2013), using historical data, market trends, and risk-adjusted models in cost estimation can significantly improve budgeting accuracy and reduce the likelihood of cost overruns.

Enhanced stakeholder collaboration is also essential. Infrastructure projects typically involve multiple actorsincluding government agencies, contractors, consultants, and community memberseach with different expectations and interests. Establishing clear communication channels, joint decision-making mechanisms, and feedback loops helps reduce conflicts and improve financial accountability (Chileshe & Yirenkyi-Fianko, 2011). Project success depends on aligning stakeholder roles, responsibilities, and expectations throughout the lifecycle.

Another critical strategy involves the adoption of modern technologies for cost tracking and control. Tools such as Building Information Modeling (BIM), project management software, and real-time cost monitoring systems enable accurate tracking of expenses and progress. Ghada Badawi and Nawawy (2016) emphasized that integrating digital tools into cost management systems reduces manual errors, enhances transparency, and supports data-driven decision-making.

Capacity building and professional training are also crucial for strengthening cost management practices. In many developing regions, project personnel lack adequate knowledge of financial planning, cost control techniques, and risk management. Regular training programs, certifications, and professional development initiatives help build a skilled workforce capable of implementing best practices in cost estimation and control (Iqbal et al., 2015).

Furthermore, the implementation of integrated cost management systems can provide a comprehensive approach to financial control. Such systems combine planning, estimation, budgeting, and monitoring into a centralized framework, allowing project managers to track cost performance in real-time and make timely corrections (El-Sayegh, 2018). This approach fosters accountability and promotes informed decision-making at all project stages.

In countries like Nigeria, strengthening regulatory enforcement and procurement processes is essential. Effective implementation of public procurement laws, independent auditing, and regular project evaluations ensure that cost estimates are realistic and that expenditures are aligned with project scope and quality standards. Fernando et al. (2017) observed that strict regulatory oversight can reduce contract inflation and promote value for money.

Lastly, anti-corruption initiatives must be prioritized. Transparent bidding processes, open contract databases, and the active involvement of civil society can help deter unethical practices that inflate project costs. According to Nouman et al. (2021), eliminating corruption from infrastructure delivery systems can significantly improve cost efficiency and project outcomes.

In conclusion, while cost management challenges are complex and multifaceted, their resolution lies in a proactive combination of technological innovation, policy reform, stakeholder engagement, and institutional strengthening. These strategies not only enhance cost efficiency but also improve the overall sustainability and impact of infrastructure development projects.

## 2.8 Summary of Literature Review

This chapter has reviewed extensive literature on cost management in infrastructure development, with a focus on the prevailing challenges and potential solutions, particularly within developing economies such as Nigeria, and more specifically, Kwara State. The literature confirms that cost management is an indispensable component of project success. It plays a central role in ensuring that infrastructure projects are delivered within budget, on schedule, and according to specified quality standards.

However, despite its importance, effective cost management is often undermined by numerous challenges. In developing countries, these include but are not limited to inadequate planning, inflation, currency fluctuations, corruption, poor contract administration, and insufficient stakeholder coordination. The lack of technical capacity and the underutilization of cost management tools and techniques further compound the situation. Studies such as those by El-Sayegh (2018), Ghada Badawi &Nawawy (2016), and Fernando et al. (2017) have consistently emphasized the detrimental impact of these issues on project performance.

In the context of Kwara State, the literature identifies specific localized barriers such as inconsistent government policies, funding delays, poor data for cost estimation, and weak institutional oversight. These issues often lead to budget overruns, project abandonment, and misallocation of scarce public resources, thereby stalling socio-economic development and eroding public trust (Idris et al., 2019; Amuda-Yusuf et al., 2017).

The review also underscores the need for a holistic and strategic approach to cost management. This involves not only the use of advanced planning and forecasting techniques but also the integration of technology, stakeholder engagement, transparency mechanisms, and continuous professional training. Modern solutions such as cost management software, digital procurement platforms, and building information modeling (BIM) offer promising avenues for improving financial control and efficiency in project delivery.

Ultimately, the literature demonstrates that sustainable infrastructure development cannot be achieved without addressing the root causes of cost mismanagement. Effective cost control, stakeholder accountability, robust planning, and the institutionalization of anti-corruption measures are essential to unlocking the full potential of infrastructure investment. These measures, if well implemented, will enhance project delivery and support long-term development goals in Kwara State and similar environments.

# CHAPTER THREE

# RESEARCH METHODOLOGY

## 3.1A brief outline of the chapter

This chapter presents the methodology adopted in carrying out the research on the challenges of cost management for infrastructure development in Kwara State. It provides a systematic explanation of the processes used in gathering, analyzing, and interpreting data relevant to the research objectives and questions.

The chapter begins with a restatement of the research questions and hypothesis that guide the study. It then discusses the research design adopted, which provides the framework for the entire investigation. The chapter also defines the population of the study, the sample frame, and the sample size, as well as the sampling technique used to select respondents.

Additionally, the instruments used for data collection are described, along with the procedures for testing their validity and reliability to ensure accuracy and consistency. The chapter further outlines how data were collected, processed, and analyzed to derive meaningful findings. Finally, the limitations encountered in the course of applying the chosen methodology are acknowledged, providing context for the interpretation of the research results.

## 3.2Research design

This study adopts a descriptive survey research design, which is suitable for collecting, analyzing, and interpreting data related to the current status, opinions, and practices surrounding cost management in infrastructure projects. A descriptive design is appropriate for this research because it enables the researcher to gather factual information from a sample population and describe the prevailing challenges without manipulating variables.

According to Creswell (2014), descriptive survey research is used when a researcher seeks to obtain information that describes the existing conditions or identifies standards against which future conditions can be compared. In this study, the design facilitates a structured approach to explore the experiences, perceptions, and professional practices of construction stakeholders, including quantity surveyors, engineers, project managers, contractors, and government officials.

This design allows for both quantitative and qualitative insights, as the questionnaire administered to respondents includes closed-ended questions for statistical analysis as well as open-ended items to capture expert opinions and suggestions. The data generated from this process provides an evidence-based understanding of the effectiveness and challenges of cost management strategies in infrastructure delivery across Kwara State.

3.3 Population of the Study
The research population refers to the total set of individuals, groups, or entities that possess the characteristics relevant to the research objectives and from which a sample is drawn for data collection. For this study, the population comprises construction industry stakeholders involved in infrastructure development projects across Kwara State.

Specifically, this includes:Quantity Surveyors, Civil, Mechanical, and Electrical Engineers, Project Managers, Construction Contractors, Officials from the Ministry of Works and Transport, Local Government Engineers, Consultants and Supervisors, Community Representatives engaged in infrastructure oversight

These professionals are directly involved in planning, budgeting, executing, supervising, and managing construction activities within the public and private sectors. They are most suited to provide credible insights into the cost management challenges faced in infrastructure development.

According to Asika (2006), a research population must be clearly defined and should include individuals who are well-positioned to provide reliable and relevant data to address the research questions. In line with this, the choice of construction professionals in Kwara State ensures that the information collected will be practical, context-specific, and reflective of the operational realities on project sites.

The geographical focus on Kwara State is based on its significant engagement in infrastructural development at the state and local government levels, particularly in road construction, public building projects, and other civil engineering works. The researcher’s access to local institutions, professional bodies, and ministries within the state further justifies the selection.

3.4 Sample Size and Sampling Technique
A sample size of 100 respondents will be selected using purposive sampling. This non-probability sampling method is chosen because it allows the researcher to select individuals with direct experience in cost management for infrastructure projects. Emphasis will be placed on selecting participants from ongoing and completed projects across major towns such as Ilorin, Offa, and Omu-Aran.

3.5 Method of Data Collection
The questionnaires will be administered physically and electronically to reach a wider audience within the construction sector. Physical distribution will take place on project sites and government offices, while electronic copies will be shared via email and WhatsApp groups relevant to industry professionals in the state. A well-structured questionnaire was used to obtain data from the respondents. The questionnaire have close-ended question to ensure consistency of respondents feedback based on five point Likert scale

3.7 Method of Data Analysis
Data collected will be coded and analyzed using descriptive statistics such as frequency tables, percentages, and mean scores. Statistical analysis will be carried out using Microsoft Excel and SPSS to determine the most prevalent cost management challenges and the effectiveness of existing practices.

3.8 Validity and Reliability of Instrument
To ensure content validity, the questionnaire will be reviewed by academic experts and construction professionals.The Cronbach’s Alpha coefficient will be calculated to assess the reliability of the questionnaire.

3.9 Ethical Considerations
Respondents will be informed about the purpose of the research, and their participation will be voluntary. Anonymity and confidentiality will be strictly maintained, and data will be used solely for academic purposes.

# CHAPTER FOUR

# DATA ANALYSIS, RESULTS AND DISCUSSIONS

## 4.1 A brief introduction to the chapter

This chapter presents a detailed analysis, interpretation, and discussion of the data obtained from the field survey conducted for this study. The data were collected through structured questionnaires administered to construction professionals actively involved in infrastructure development across Kwara State. These include Quantity Surveyors, Engineers, Architects, and Project Managers from both public and private sector organizations.

The main objective of this chapter is to examine the challenges associated with cost management in infrastructure development projects within the state. The analysis is structured around the study’s research objectives and questions. Descriptive statistical tools such as frequency tables, percentages, mean scores, and rankings are used to present the responses in a clear and concise manner.

In addition, relevant literature is cited to compare the study’s findings with existing knowledge in the field. This comparative approach helps to validate the results and provide deeper insight into recurring issues affecting effective cost control and project delivery in the construction industry, particularly in Kwara State. By integrating field data with established studies, the chapter highlights key cost management challenges, their implications for infrastructure development, and potential strategies for improvement.

Ultimately, the insights from this chapter serve as the basis for the conclusions and recommendations in subsequent chapters, providing practical guidance for stakeholders involved in planning, budgeting, and executing infrastructure projects in the region.

## 4.2 Response Rate

To ensure the credibility and representativeness of the study, a total of 100 structured questionnaires were administered to selected construction professionals who are actively involved in infrastructure development projects across various localities in Kwara State. These professionals included Quantity Surveyors, Civil Engineers, Architects, Project Managers, and others with relevant experience in public and private sector construction.

Out of the 100 questionnaires distributed, 92 were completed and returned, yielding a 92% response rate. This is considered highly satisfactory in research, as a response rate above 70% is generally regarded as adequate for meaningful analysis (Mugenda & Mugenda, 2003). The high response rate in this study enhances the reliability, validity, and generalizability of the research findings.

This response rate reflects not only the commitment of the respondents to the research objectives but also indicates the relevance of the topic within the construction industry in Kwara State. It also suggests that the participants had adequate knowledge and interest in the subject matter, which contributed to the completeness and quality of the data gathered.

Table 4.1 response rate

| Questionnaires Distributed | Returned | Usable Responses | Response Rate |
| --- | --- | --- | --- |
| 100 | 92 | 92 | 92% |

In conclusion, the high return rate provides a strong foundation for the subsequent data analysis, ensuring that the findings of the study are based on a robust and sufficiently large sample of relevant stakeholders in the construction sector.

## 4.3 Characteristics of Respondents

This section presents the demographic characteristics of the respondents who participated in the study. Analyzing their professional backgrounds, years of experience, and sector of employment provides essential context for interpreting their perspectives on cost management challenges in infrastructure development within Kwara State. These characteristics are important as they influence how respondents perceive, understand, and manage cost-related issues in construction projects.

### 4.3.1 Professional Background

The distribution of respondents based on their professional discipline reveals a balanced representation of key stakeholders in the construction industry. Quantity Surveyors constituted the highest proportion (35%), followed by Civil Engineers (27%), Architects (20%), and Project Managers (18%). This diversity ensures that the views gathered reflect a holistic understanding of the cost management process from design to execution.

Table 4.2 Professional Background

| Professional Background | Frequency | Percentage (%) |
| --- | --- | --- |
| Quantity Surveyors | 32 | 35% |
| Civil Engineers | 25 | 27% |
| Architects | 18 | 20% |
| Project Managers | 17 | 18% |
| Total | 92 | 100% |

### 4.3.2 Years of Experience

Respondents were asked to indicate their years of experience in the construction industry. This is significant because experience often correlates with depth of knowledge and familiarity with cost management practices. The largest group (46%) had between 6–10 years of experience, suggesting a strong mid-career workforce. About 33% had over 10 years of experience, implying maturity in professional practice.

Table 4.3 Years of Experience

| Years of Experience | Frequency | Percentage (%) |
| --- | --- | --- |
| 1–5 years | 20 | 22% |
| 6–10 years | 42 | 46% |
| 11–15 years | 18 | 20% |
| Above 15 years | 12 | 13% |
| Total | 92 | 100% |

### 4.3.3 Sector of Employment

Respondents were also categorized based on whether they worked in the public or private sector. A higher proportion (59%) were from the private sector, while 41% represented various government agencies or parastatals. This mix ensures that the study captures the nuances of cost management challenges in both sectors, which often operate under different regulatory, financial, and operational conditions.

Table 4.4 Sector of Employment

| Sector of Employment | Frequency | Percentage (%) |
| --- | --- | --- |
| Public Sector | 38 | 41% |
| Private Sector | 54 | 59% |
| Total | 92 | 100% |

### 4.3.4 Summary

The demographic profile of respondents shows a wide representation of construction professionals, most of whom have significant years of experience and are involved in both public and private sector infrastructure projects. This diversity enhances the reliability of the data, as it provides a broad and inclusive understanding of the challenges affecting cost management in Kwara State’s construction industry.

## 4.4 Presentation and analysis of data according to research questions

### 4.4.1Major challenges of cost management in infrastructure development projects in Kwara State

The analysis indicates that inadequate budget allocation is the most significant challenge, with a mean score of 4.49. This suggests that many infrastructure projects in Kwara State suffer from underfunding or unrealistic financial planning, which hampers proper execution and completion. Closely following is the delay in payment to contractors (mean = 4.37), a critical issue that often disrupts project cash flow, leads to site abandonment, and affects contractor motivation and performance.

Inflation and market price fluctuations were ranked third (mean = 4.25), reflecting the economic instability and unpredictability of construction material costs in Nigeria. Frequent changes in the prices of essential construction inputs make cost control highly challenging, especially in long-term projects.

Poor planning and scope definition also emerged as a notable challenge (mean = 4.13). Inadequately defined project scopes can result in cost escalation due to scope creep, contract variations, and misalignment between project expectations and actual execution.

Corruption and political interference (mean = 4.02) remain pervasive in public infrastructure delivery, leading to misappropriation of funds, award of contracts to unqualified firms, and unnecessary cost inflations. Inaccurate cost estimation (mean = 3.95), while the least ranked among the six, still presents a significant challenge. This issue often arises from reliance on outdated data, insufficient site investigation, and limited forecasting tools.

These findings are consistent with earlier studies. Notably, Aibinu and Jagboro (2002) identified delayed payments and inaccurate estimates as two of the most common causes of cost overruns in Nigerian construction projects. Their work emphasized the need for robust financial planning, timely disbursement of funds, and the engagement of skilled professionalsespecially Quantity Surveyorsto ensure accurate and realistic project budgeting.

Overall, the data highlight the multi-dimensional nature of cost management challenges in Kwara State, underscoring the need for a strategic, transparent, and data-driven approach to infrastructure project planning and execution.

Table 4.5 major challenges of cost management

| Challenges | Mean Score | Ranking |
| --- | --- | --- |
| Inadequate budget allocation | 4.49 | 1st |
| Delay in payment to contractors | 4.37 | 2nd |
| Inflation and market price fluctuations | 4.25 | 3rd |
| Poor planning and scope definition | 4.13 | 4th |
| Corruption and political interference | 4.02 | 5th |
| Inaccurate cost estimation | 3.95 | 6th |

### 4.4.2 Impact of Cost Management Challenges on Project Delivery

The results show a high level of agreement among respondents on the negative effects of poor cost management on project outcomes. The highest-rated impact is project abandonment (mean = 4.51), indicating that many infrastructure projects are often left uncompleted when funds run out due to poor budgeting, inaccurate forecasting, or unforeseen costs. This finding supports earlier research by Omoregie and Radford (2006), which identified inadequate financial control as a major reason for project abandonment in Nigeria’s public sector.

Closely following is the issue of delays in project delivery (mean = 4.43). This suggests that cost overruns frequently disrupt construction timelines, causing contractors to halt or slow down work while awaiting additional funding or approvals. These disruptions not only lead to increased project duration but also increase total expenditure, validating the observations of Aibinu and Jagboro (2002) who identified delays as a recurring outcome of cost-related issues in the Nigerian construction sector.

The third ranked impact is reduction in project quality (mean = 4.26). Respondents agree that cost management issues often force contractors to cut corners in order to stay within budget—leading to the use of substandard materials, design compromises, or poor workmanship. This ultimately affects the functionality, safety, and sustainability of the completed infrastructure.

Finally, loss of public confidence in infrastructure delivery was also acknowledged as a significant consequence (mean = 4.20). When projects exceed their budgets or remain incomplete, stakeholdersincluding citizens, funders, and regulatory bodieslose faith in the transparency and efficiency of government institutions or construction firms involved. This can hinder future collaboration, funding, and support for public projects.

Overall, the analysis demonstrates that cost management challenges have far-reaching effects on project delivery in Kwara State, affecting timelines, quality, stakeholder trust, and in many cases, leading to outright abandonment of infrastructure developments. Addressing these challenges is therefore critical to achieving sustainable development goals and improving the credibility of construction delivery systems.

Table 4.5 Impact of Cost Management Challenges on Project Delivery

| Statement | Mean Score | Ranking |
| --- | --- | --- |
| Poor cost management contributes to project abandonment. | 4.51 | 1st |
| Cost overruns result in delays in project delivery. | 4.43 | 2nd |
| Cost management challenges reduce the quality of completed projects. | 4.26 | 3rd |
| Failure to complete projects within budget affects public confidence. | 4.20 | 4th |

### 4.4.3 Effectiveness of Current Cost Management Practices

The findings reveal a moderate perception of the effectiveness of current cost management practices in Kwara State. With a mean score of 3.82, budgeting and financial control systems are perceived as the most effective among the listed practices. This suggests that most infrastructure projects have a basic framework for financial planning and expenditure tracking. However, the score also implies that these systems may not be robust enough to manage dynamic cost challenges such as inflation and funding delays.

The second-highest rated practice is cost monitoring and evaluation throughout the project lifecycle (mean = 3.70). This indicates that periodic cost reviews and performance tracking are present in many projects, but there is still a gap in the consistency and comprehensiveness of these evaluations, especially in relation to real-time data capture and feedback mechanisms.

Stakeholder engagement in cost planning and control ranked third (mean = 3.61), highlighting some level of collaboration between project owners, consultants, and contractors. However, this score suggests that stakeholder involvement is not yet fully institutionalized or participatory, especially during early planning and design stages where critical cost decisions are made.

Cost audits and accountability mechanisms received a mean score of 3.52, reflecting the presence of auditing frameworks, particularly in government-funded projects. Nonetheless, the relatively low score hints at weak enforcement and possible institutional limitations that undermine the impact of these mechanisms on ensuring transparency and controlling corruption.

Finally, the lowest-rated practice is the consistent use of value management techniques (mean = 3.40). This indicates that modern tools such as value engineering and life-cycle costing are not widely adopted in infrastructure projects within the state. The underutilization of these techniques suggests a missed opportunity to enhance cost efficiency and optimize the value derived from limited project funds.

These findings align with earlier research by Memon et al. (2010), who reported that value management remains underexploited in many developing countries, despite its effectiveness in improving project outcomes when properly applied.

Table 4.6: Effectiveness of Current Cost Management Practices

| Statement | Mean Score | Ranking |
| --- | --- | --- |
| Budgeting and financial control systems are effective in current infrastructure projects. | 3.82 | 1st |
| There is adequate monitoring and evaluation of cost throughout the project lifecycle. | 3.70 | 2nd |
| Stakeholders are effectively engaged in cost planning and control. | 3.61 | 3rd |
| Cost audits and accountability mechanisms are in place and effective. | 3.52 | 4th |
| Value management techniques are consistently used to improve cost performance. | 3.40 | 5th |

## 4.5 Discussion of Findings

The analysis reveals that inadequate budgeting, payment delays, inflation, and poor planning are the top challenges facing infrastructure cost management in Kwara State. These findings corroborate previous studies by Omoregie & Radford (2006), who found that financial mismanagement and poor planning were among the root causes of project failure.The consequences identifiedsuch as abandonment, delays, and quality reduction—highlight the need for proactive cost control. Additionally, the preference for employing professional Quantity Surveyors and using modern tools reflects a growing awareness among practitioners about the value of professionalism and digital transformation in cost management (Memon et al., 2010).

The findings from the analysis of the questionnaire responses provide significant insights into the cost management challenges facing infrastructure development in Kwara State. The study identifies inadequate budget allocation, delay in payment to contractors, inflation and market price fluctuations, and poor planning and scope definition as the most critical issues affecting cost performance in public and private sector infrastructure projects.

These findings are consistent with the work of Omoregie and Radford (2006), who emphasized that financial mismanagement and poor project planning are central to the frequent failures observed in infrastructure projects across Nigeria. Similarly, Aibinu and Jagboro (2002) previously highlighted delayed payments and cost estimation inaccuracies as major contributors to cost overruns and disruptions in project delivery. In the current study, the respondents confirmed that delays in funding disbursement often stall construction progress, escalate costs, and lead to strained relationships among project stakeholders.

The study also reveals that price instability, largely driven by inflation and volatile exchange rates, makes it difficult to maintain accurate cost projections over the project lifecycle. This economic uncertainty compounds the challenges of effective budgeting and often necessitates contract variations, which further delay project delivery and increase overall expenditure.

Additionally, poor scope definition and planning contribute significantly to cost management failures. When project scopes are not clearly articulated at the design stage, it leads to scope creep, misallocation of resources, and costly revisions during construction. These issues could have been mitigated through comprehensive feasibility studies, stakeholder consultations, and early involvement of cost professionals.

The consequences of these challenges are severe and far-reaching. The most cited outcomes include project abandonment, delayed project completion, reduction in the quality of infrastructure, and erosion of public trust in government or implementing agencies. These effects not only waste public resources but also hinder socio-economic development and undermine public confidence in infrastructure delivery systems. This aligns with findings from Oyedele (2013), who noted that poor cost control leads to underperforming assets that fail to meet user needs or technical standards.

On a positive note, the study also reveals a growing awareness among construction professionals in Kwara State of the importance of deploying more structured and modern cost management approaches. Respondents indicated that engaging professional Quantity Surveyors, improving stakeholder involvement in cost planning, and embracing digital tools and value management techniques are critical to reversing the current trend.

This observation is supported by Memon et al. (2010), who argued that the integration of value management and technology-driven systems in cost control can lead to more efficient use of project funds, reduced waste, and better decision-making throughout the project lifecycle. However, the study also found that value management practices remain underutilized in Kwara State, highlighting the need for professional training, awareness creation, and institutional support to promote its adoption.

In conclusion, the discussion of findings underscores that effective cost management in infrastructure development is multifaceted. It requires a combination of timely and adequate funding, accurate cost estimation, professional input, stakeholder engagement, and the use of innovative tools to ensure projects are delivered on time, within budget, and to the desired quality standards. Addressing these areas is essential for enhancing infrastructure delivery and ensuring sustainable development across Kwara State

## 4.6 Summary of Chapter Four

This chapter presented the analysis of data collected from 92 respondents on the challenges of cost management in infrastructure development within Kwara State. The findings show that financial limitations, inflation, and poor planning dominate the cost management issues. The chapter also discussed the consequences of these challenges and provided practical strategies for improvement, based on both primary data and literature support.

This chapter presented a comprehensive analysis of the data collected from 92 construction professionals across Kwara State regarding the challenges of cost management in infrastructure development projects. The responses were gathered through structured questionnaires and analyzed using descriptive statistical methods, including mean scores and rankings, to address the research questions in alignment with the study objectives.

The analysis revealed that financial limitations, such as inadequate budget allocations and delays in payment to contractors, are the most critical cost management challenges affecting infrastructure delivery in the state. These challenges are compounded by economic instability, particularly inflation and market price fluctuations, which make accurate budgeting and cost forecasting difficult. Additionally, poor planning, including weak scope definition and unrealistic project timelines, emerged as key contributors to cost overruns and inefficiencies.

The chapter further explored the consequences of ineffective cost management, with respondents overwhelmingly agreeing that such challenges often lead to project abandonment, delays in completion, reduction in construction quality, and a general loss of public confidence in project delivery processes. These impacts not only result in the waste of financial resources but also hinder the achievement of critical development goals and erode trust in public institutions and contractors.

Furthermore, the study assessed the effectiveness of current cost management practices, revealing moderate performance in areas such as budgeting, cost monitoring, and stakeholder engagement. However, practices such as value management and cost auditing were rated less effective, indicating a need for improvement in the adoption of proactive, innovative, and professionally-driven cost control strategies.

The findings were supported and compared with existing literature, including the works of Omoregie & Radford (2006), Aibinu&Jagboro (2002), and Memon et al. (2010), to reinforce the credibility and relevance of the results. These comparisons highlighted recurring themes in construction cost challenges within developing economies and provided a benchmark for understanding the local context in Kwara State.

In conclusion, the chapter underscored the urgent need for strengthening cost management frameworks, improving professional capacity, enhancing transparency, and leveraging modern cost management tools and techniques to improve infrastructure project outcomes. These insights form the basis for the summary, conclusion, and recommendations presented in the next chapter.

# CHAPTER FIVE

# SUMMARY, CONCLUSION AND RECOMMENDATION

## 5.1 Summary of the Findings

This study investigated the challenges of cost management in infrastructure development within Kwara State, Nigeria, with the aim of identifying the major cost-related problems, their impact on project delivery, and evaluating the effectiveness of current cost management practices. A total of 100 questionnaires were distributed, out of which 92 valid responses were received and analyzed.

The key findings from the study are summarized as follows:

- Inadequate budget allocation, delay in payment to contractors, and market price fluctuations (inflation) were identified as the most significant challenges confronting cost management in infrastructure projects. These issues often lead to financial shortfalls, inefficient resource allocation, and compromised project execution.

- Poor planning and scope definition, as well as corruption and political interference, were also highlighted as recurring challenges that affect the credibility and effectiveness of project cost control systems.

- The impacts of poor cost management were found to be severe, with project abandonment, delays, quality reduction, and loss of public confidence being the most prominent consequences.

- Regarding the effectiveness of existing cost management practices, the study revealed moderate effectiveness in budgeting, financial control, and cost monitoring. However, areas such as value management, cost auditing, and stakeholder involvement were identified as needing significant improvement.

The findings were consistent with previous studies (e.g., Omoregie & Radford, 2006; Aibinu&Jagboro, 2002; Memon et al., 2010), indicating that the issues identified are systemic and persistent in the Nigerian construction industry.

## 5.2 Conclusion

Based on the data collected and analyzed, this study concludes that cost management in infrastructure development projects across Kwara State faces a range of persistent and deeply rooted challenges. These issues continue to obstruct the successful delivery of public and private construction initiatives, often leading to inefficiencies, cost overruns, and substandard project outcomes.

Among the most pressing challenges identified are inadequate funding mechanisms, which often stem from poor budget forecasting, unrealistic financial planning, or political constraints. Many infrastructure projects are initiated without clear, sufficient, or timely financial provisions, leading to funding gaps that disrupt the execution process.

Additionally, delayed financial disbursements, particularly from government institutions and funding bodies, further exacerbate project inefficiencies. These delays affect cash flow, hinder contractor performance, cause work stoppages, and often result in contractual disputes that delay or halt project progress.

Unstable market conditions, driven by factors such as inflation, currency fluctuations, and inconsistent supply chains, were also highlighted as a major constraint. These economic uncertainties make cost prediction unreliable and introduce unexpected financial burdens during the project lifecycle. Consequently, initial budgets often prove inadequate by the time construction activities are fully underway.

Another significant issue is weak project planning and scope definition. Inadequate feasibility studies, poor stakeholder coordination, and vague design documentation often result in cost variations, rework, and poor resource management. These planning flaws can ultimately escalate project costs beyond control.Collectively, these challenges not only hinder the timely and cost-effective completion of infrastructure projects but also undermine the overall quality, durability, and functionality of the delivered facilities. The ripple effect includes wasted public funds, prolonged socio-economic setbacks, and reduced user satisfaction. In the case of government-funded projects, this often leads to a loss of public confidence in institutions responsible for infrastructure provision.

Although there is evidence of existing cost management frameworks—such as budgeting procedures, financial monitoring, and stakeholder reviews—their implementation across Kwara State remains largely inconsistent and ineffectively enforced. In several cases, these frameworks exist in policy but are not followed through in practice due to lack of capacity, political interference, or absence of regulatory accountability.

Therefore, the study emphasizes the urgent need for a robust, transparent, and professionally driven cost control system. Such a system should integrate modern cost management tools (e.g., cost forecasting software, Building Information Modelling), institutionalized stakeholder collaboration, and the consistent engagement of professional Quantity Surveyors and other competent project managers. These professionals are well-positioned to provide cost planning, evaluation, and control services throughout the project lifecycle, ensuring resources are utilized optimally and within scope.

To enhance efficiency and sustainability in infrastructure delivery, the study advocates for the modernization of cost management approaches in Kwara State, backed by appropriate policy reforms, professional training, and the use of innovative digital technologies.

## 5.3 Recommendations

In light of the research findings and conclusion, the following comprehensive recommendations are proposed to address the challenges of cost management in infrastructure development projects across Kwara State. These measures aim to improve financial efficiency, minimize cost overruns, and ensure timely and quality project delivery.

    - Strengthen Budget Planning and Allocation
There is an urgent need for government agencies, funding institutions, and private project sponsors to improve the accuracy and adequacy of budget estimates. Budget planning should be based on comprehensive feasibility studies, market analysis, and inflation forecasting. By incorporating risk analysis and contingency planning into budget frameworks, project stakeholders can better anticipate and absorb financial uncertainties. Effective budget planning must also involve experienced Quantity Surveyors who can develop realistic cost models and ensure alignment between budget and actual project requirements.

    - Ensure Timely Release of Funds
One of the most critical issues facing project execution is the delay in the release of funds, especially in publicly funded projects. These delays disrupt workflow, demotivate contractors, and contribute to inflated costs. To resolve this, institutional reforms must be introduced to streamline fund disbursement processes and remove bureaucratic bottlenecks. Clear timelines and financial milestones should be embedded in project agreements, and funding should be tied to verifiable work progress. Establishing project escrow accounts or milestone-based disbursements may also enhance efficiency and reduce payment delays.

    - Adopt Value Management Techniques
Value Management (VM), including value engineering and life-cycle costing, should be integrated into the planning and execution phases of all major infrastructure projects. These techniques allow project teams to evaluate functions, identify unnecessary costs, and optimize the relationship between project cost and performance. Training and workshops should be organized to build VM capacity among professionals in both public and private sectors. Encouraging the routine use of VM will lead to more cost-efficient designs, improved resource allocation, and better long-term infrastructure outcomes.

    - Enhance Planning and Scope Definition
Poor project planning and vague scope definitions are major drivers of cost overruns. To counter this, all projects should begin with detailed feasibility studies, environmental and social impact assessments, and technical investigations. Early-stage planning should also involve thorough stakeholder consultations to ensure that all requirements and expectations are clearly defined and documented. A well-articulated scope helps prevent mid-project changes, contract variations, and unnecessary delays—thereby reducing cost escalation.

    - Strengthen Cost Monitoring and Auditing Systems
Effective cost control depends on real-time monitoring, regular audits, and the availability of accurate financial data. Project owners should implement independent cost auditing frameworks that operate throughout the project lifecycle—from design through to completion. The use of digital tools and project management software such as Enterprise Resource Planning (ERP), BIM (Building Information Modelling), and cost tracking dashboards should be encouraged. These systems improve transparency, reduce fraud, and enable early detection of financial irregularities or overspending.

    - Promote Stakeholder Engagement
Meaningful involvement of all key stakeholdersincluding clients, consultants, contractors, financiers, and local community representativesis essential for effective cost planning and control. Stakeholder engagement enhances transparency, accountability, and shared ownership of project goals. Regular meetings, review sessions, and joint decision-making platforms should be institutionalized to ensure all parties have input in budgeting, scope changes, procurement strategies, and progress tracking.

    - Professional Development and Capacity Building
Sustainable improvement in cost management practices requires continuous investment in human capital development. Professional development programs, workshops, and certifications should be provided for project managers, Quantity Surveyors, engineers, and government officials involved in project delivery. Training should focus on emerging trends, global best practices, technological tools, and financial risk management. In addition, institutions such as the Nigerian Institute of Quantity Surveyors (NIQS) and regulatory bodies should play a more active role in enforcing professional standards and ethical conduct in cost-related functions.

Implementing these recommendations holistically will significantly enhance the efficiency, transparency, and success rate of infrastructure development projects in Kwara State. It will also position the construction industry to better respond to economic challenges, deliver value for money, and gain public trust in infrastructure governance.

## 5.4 Suggestions for Further Research

Although this study has provided valuable insights into the key challenges and current practices of cost management in infrastructure development within Kwara State, it also uncovered areas that require deeper exploration. To broaden the knowledge base and develop more effective cost control strategies, the following directions for future research are recommended

5.4.1 Comparative Studies Between Different Nigerian States
Future research could undertake a comparative analysis of cost management practices across various Nigerian states. Such studies would help identify regional variations in cost-related challenges, budget performance, procurement methods, and policy implementation. Understanding the differences between relatively successful states and those with higher failure rates could reveal best practices and contextual factors influencing infrastructure delivery. This would also aid policymakers in benchmarking and adapting cost control models that are effective in similar socio-economic environments.

5.4.2 In-Depth Investigation into the Role of Corruption and Political Influence
One of the subtle but powerful influences on cost performance in infrastructure projects is corruption and political interference. Further qualitative and quantitative research is needed to uncover the specific ways in which political decisions, contract manipulation, favoritism, and lack of transparency affect cost management outcomes. Exploring this area can provide evidence-based recommendations for strengthening accountability mechanisms, improving governance structures, and promoting ethical practices in the construction industry, especially in public sector projects.

5.4.3 Exploration of Digital Technologies in Cost Control
As the construction industry continues to evolve, the integration of digital tools and innovations is becoming increasingly vital for efficient cost management. Future research should examine the adoption, challenges, and benefits of technologies such as Building Information Modelling (BIM), Enterprise Resource Planning (ERP), Cost Management Software, Artificial Intelligence (AI), and e-Procurement systems in infrastructure project delivery. This line of inquiry can help identify how these tools enhance cost transparency, reduce human errors, improve forecasting, and support real-time decision-making.

5.4.4 Case Studies of Successfully Delivered Infrastructure Projects
While many studies tend to focus on failures and challenges, it is equally important to document and analyze successful infrastructure projects that were delivered on time, within budget, and to high quality standards. Case studies within Kwara State and beyond can provide valuable insights into practical strategies, leadership approaches, project team dynamics, and cost-saving techniques that contributed to their success. These lessons can serve as models for future projects and training materials for construction professionals.

5.4.5 Evaluation of the Role of Quantity Surveyors and Cost Professionals
Further research may also explore the extent of involvement, challenges, and effectiveness of Quantity Surveyors and other cost professionals in infrastructure development projects across Nigeria. Such studies would assess their impact on cost control, the adequacy of their training, and how professional practices can be better supported through legislation and institutional reforms.

5.4.6 Investigation into Community Participation and Stakeholder Engagement
Cost management is often affected by stakeholder dynamics and community responses to projects. Future studies could investigate how local community involvement, public-private partnerships, and client-consultant-contractor collaboration influence cost outcomes. Understanding the social aspect of cost control may lead to more inclusive and sustainable infrastructure planning.

# APPENDICES

QUESTIONNAIRE

Department of Quantity Surveying,

Institute of Environmental Studies

Kwara state Polytechnic, Ilorin.

Kwara State.

Dear Sir/Madam,

RESEARCH QUESTIONNAIRE:  Challenges of Cost Management for Infrastructure Development in Kwara State

I, OLAITAN Abdulwahab Oluwadamilare, an undergraduate student of Quantity Surveying Department, at the Kwara state polytechnic, Ilorin, I am undertaking my final year research thesis in partial fulfilment of the requirement for the award of Higher National diploma.

While appreciating your busy schedule, with all due respect I humbly solicit that your spare time to help respond to the attached questionnaire which is crucial to the success of my on-going research titled above.

Your response will be treated with confidentiality and used only for the purpose of this research work.

Thank you for your anticipated cooperation

Yours sincerely

OLAITAN Abdulwahab Oluwadamilare
HND/23/QTS/FT/0064

Abdulwahaboluwadamilare64@gmail.com
09090638584

Instructions

- For multiple-choice questions in Section 1, select one option (tick the box).

- For the statements in Sections 2–4, indicate your level of agreement on the 5-point Likert scale provided (1 = Strongly Disagree; 5 = Strongly Agree).

SECTION A: DEMOGRAPHIC INFORMATION
(Please tick [✓] or fill as appropriate)

- Gender:
 ☐ Male  ☐ Female

- Age:
 ☐ 18–25  ☐ 26–35  ☐ 36–45  ☐ 46 and above

- Educational Qualification:
 ☐ OND/NCE  ☐ HND/B. Sc  ☐ M.Sc./MBA  ☐ Ph.D.

- Profession/Occupation:
 ☐ Quantity Surveyor  ☐ Civil Engineer  ☐ Project Manager  ☐ Government Official
 ☐ Contractor  ☐ Other (please specify): ___________________

- Years of Experience in Infrastructure Projects:
 ☐ Less than 5 years  ☐ 5–10 years  ☐ 11–15 years  ☐ Above 15 years

SECTION B: CHALLENGES ASSOCIATED WITH COST MANAGEMENT
(Please rate the following statements using the scale below)
1 – Strongly Disagree | 2 – Disagree | 3 – Neutral | 4 – Agree | 5 – Strongly Agree

| S/N | Statement | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Inadequate project cost planning is a major challenge in Kwara State infrastructure development. | ☐ | ☐ | ☐ | ☐ | ☐ |
| 2 | Corruption and mismanagement contribute significantly to cost overruns. | ☐ | ☐ | ☐ | ☐ | ☐ |
| 3 | Delay in payment to contractors affects cost management. | ☐ | ☐ | ☐ | ☐ | ☐ |
| 4 | Inflation and fluctuation in material prices hinder effective cost control. | ☐ | ☐ | ☐ | ☐ | ☐ |
| 5 | Lack of skilled cost management professionals’ impacts cost efficiency. | ☐ | ☐ | ☐ | ☐ | ☐ |
| 6 | Inaccurate cost estimation leads to budget shortfalls. | ☐ | ☐ | ☐ | ☐ | ☐ |

SECTION C: IMPACT OF COST MANAGEMENT CHALLENGES ON PROJECT DELIVERY

| S/N | Statement | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Poor cost management contributes to project abandonment. | ☐ | ☐ | ☐ | ☐ | ☐ |
| 2 | Cost overruns result in delays in project delivery. | ☐ | ☐ | ☐ | ☐ | ☐ |
| 3 | Cost management challenges reduce the quality of completed projects. | ☐ | ☐ | ☐ | ☐ | ☐ |
| 4 | Failure to complete projects within budget affects public confidence. | ☐ | ☐ | ☐ | ☐ | ☐ |

SECTION D: EFFECTIVENESS OF CURRENT COST MANAGEMENT PRACTICES

| S/N | Statement | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Budgeting and financial control systems are effective in current infrastructure projects. | ☐ | ☐ | ☐ | ☐ | ☐ |
| 2 | There is adequate monitoring and evaluation of cost throughout the project lifecycle. | ☐ | ☐ | ☐ | ☐ | ☐ |
| 3 | Value management techniques are consistently used to improve cost performance. | ☐ | ☐ | ☐ | ☐ | ☐ |
| 4 | Cost audits and accountability mechanisms are in place and effective. | ☐ | ☐ | ☐ | ☐ | ☐ |
| 5 | Stakeholders are effectively engaged in cost planning and control. | ☐ | ☐ | ☐ | ☐ | ☐ |

Thank you for completing the questionnaire. Your input is valuable to this research.

# REFERENCES

Agyeman, A. Jr., Gyamfi, T.A., and Akorli, K.S. (2017). Consultant Identification on Critical Risk Factors Affecting Construction Idris USEP: Journal of Research Information in Civil Engineering, Vol.19, No.2, 2022 et al 4437 Project Execution in Ghana. Advances in Social Sciences Research Journal, 4(100) 150-164

Amuda-Yusuf, G., Adebiyi, R. T., Olowa, T. O. O., Oladapo, I. B., Olorunoje, L. O., & Idris, S. (2017). Evaluation and ranking of risk factors impacting cost and time performance of mechanical and electrical services projects. Journal of Environmental Design & Management, 9(2), 93–106.

Badawi, G., &Nawawy, M. (2016). A model for evaluation of delays in construction projects. International Journal of Innovative Research in Science, Engineering and Technology, 5(3).

Chileshe, N., & Yirenkyi-Fianko, A. B. (2011). Perceptions of threat risk frequency and impact on construction projects in Ghana: Opinion survey findings. Journal of Construction in Developing Countries, 16(2), 115–149.

El-Sayegh, S. M. (2018). Risk assessment and allocation in the UAE construction industry. International Journal of Project Management, 26(4), 431–438.

El-Sayegh, S. M., & Mansour, M. H. (2015). Risk assessment and allocation in highway construction projects in the UAE. Journal of Management in Engineering, 31(6), 431–438.

Fadun, O. S., & Saka, S. T. (2018). Risk management in the construction industry: Analysis of critical success factors of construction projects in Nigeria. International Journal of Development and Management Review, 13(1).

Fernando, C. K., Hosseini, M. R., Zavadskas, E. K., Perera, B. A. K. S., &Rameezdeen, R. (2017). Managing financial risks affecting construction contractors. International Journal of Strategic Property Management, 21(2), 212–224.

Ghada Badawi, &Nawawy, M. (2016). A model for evaluation of delays in construction projects. International Journal of Innovative Research in Science, Engineering and Technology, 5(3).

Goh, C.S., & Abdul-Rahman, H. (2013). The identification and management of major risks in the Malaysian construction industry. Journal of Construction in Developing Countries, 18(1), 19–32.

Hemesy, M. (2019). A new hybrid multi-criteria decision-making model to prioritize risks in the construction process. International Journal of Construction Management.

Idris, S., Awodele, A. O., & Amuda-Yusuf, G. (2019). Evaluation of risk factors affecting cost and time performance of civil engineering projects in Kwara State. Environmental Technology & Science Journal, 10(1), 129–140.

Iqbal, S., Choudhry, R. M., Holschemacher, K., Ali, A., &Tamosaitiene, J. (2015). Risk management in construction projects. Technology and Economic Development of Economy, 21(1), 65–78.

Lawal, A., & Elkanah, A. (2015). Factors Influencing the Performance of Construction Projects in Akure, Nigeria. International Journal of Civil Engineering and Construction Estate Management, 3(4), 57–67.

Nouman Khadim, Jaffar, S. T. A., Musarat, M. A., & Ilyas, U. (2021). Effects of corruption on infrastructure projects in developing countries. International Journal on Emerging Technologies, 12(1), 284–295.

PMI (Project Management Institute). (2014). A Guide to the Project Management Body of Knowledge (PMBOK Guide), 5th Edition.

Project Management Institute (2014). A Guide to the Project Management Body of Knowledge (PMBOK Guide), 5th Edition.

Sharma, S. (2020). Risk Identification and Management in Building and Infrastructure Projects.M.Tech Thesis, JUIT India.

Wuni, I. Y., Shen, G. Q., Osei-Kyei, R., & Agyeman-Yeboah, S. (2020). Modeling the critical risk factors for modular integrated construction projects. International Journal of Construction Management.